## Slide 1: XRN4828 - Nov 19 Release - Status Update
7th August | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up, Initiation and Design phases complete Build phase commenced on 1st July and is on track to be completed in early August System Test phase is now in progress and on track. UAT preparation in progress. Change Pack issued on 12th July requesting approval to exclude the Meter to Unconverted Index Validation from the report associated to XRN4621. Two responses received approving the proposal with no further comments raised. Funding: BER for full delivery approved in April 2019, BER for XRN4866 UIG Recommendation approved at ChMC on 12th June. |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that the implementation of November 19 is delayed as resources required to support the release are moved to support the Implementation of MOD 700 |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Design Completion – 12/07/19
Build & Unit Test Completion – 02/08/19
System & UAT Completion – 27/09/19
Regression Test Completion - 11/10/19
Implementation – 08/11/19 TBC
PIS Completion – 06/12/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT
PT
Test Cont.
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 08/11/19 - TBC
IDR