## Slide 1: UKLink Change Congestion and Release Options

## Slide 2: Agenda
Summary of planned releases and congestion
Walkthrough of options
Recommendations
Analysis

## Slide 3: Standard Release Schedule
Xoserve’s primary purpose must be to maintain the stability of the UKLink Platform.
The schedule of 2 Major and up to 3 Minor Releases a year was put in place to enable efficient delivery of customer change whilst protecting the stability of the UKLink.
The timeline below demonstrates the standard planned UKLink Releases between Jan 2020 and Jan 2022.
2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MiR D6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | MiR D7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | MiR D8 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | MiR D8 |  |  |  |  | 
June 20 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nov 2020 Major Release - Retro |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 2021 Major Release - CSS Consequential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  | Nov 21 Major Release |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 4: Current Position
Over 2020 and 2021 there are reduced opportunities to deliver customer change due to Retro and CSSC projects:
    Occupying Release windows
    Occupying Dev/Test/MT environments
    Utilising both Xoserve and customer resources
This increases the complexity and therefore the risk profile for delivery of BAU changes to UKLink
Other factors affecting release scheduling are DSG solution option selection and MOD approval timescales
With the above in mind, Xoserve have analysed each known unallocated UKLink change proposal to determine options for release scheduling and delivery prior to CSSC implementation (June 2021).

## Slide 5: Release Approach Options
The next slides outline three different release approach options, to deliver the proposed XRNs, based on the analysis detailed in the previous slides. Key points to note:
There are at least 34 changes in total, open on the UK Link Platform. 15 changes are in delivery. 19 changes* are currently not allocated to a Release.
For Option 1, there is a Major Release in June 20. Minor Releases will be scheduled according to demand and best fit
For Option 2, the 5 changes that must be delivered via a Major Release are appended on the back of Nov 20 due to no June 20 Major Release. Multiple Minor Releases will deliver the other changes. All of the changes with BW impacts have been added to MiR 9 to allow the most time for approval from Xoserve Operations and customers.
For Option 3, scope candidates will be taken from the June Release and appended to the November Release based on, risk profile, best fit and resource constraints.
* The detailed analysis of these 19 changes can be found in the Analysis section of this deck.

## Slide 6: Option 1 – June 20 Major Release
EUC | MiR 5 | Nov 19 | Doc | MiR 6 | June 20 (candidates) |  |  | Nov 20 | CSS | Nov 21
4655 | 4871A | 4621 4679 4725 4866 | 4851 4955 | 4897 4899 | 4645 4691 4692 4716 4772 | 4780B 4801 4850 4865 4871B | 4888 4930 4931 4932 4941 | Retro (4914) | CSSC (4854) | Tbc
2019 |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
EUC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mir D5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nov 19 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | MiR D6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 20 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Retro (Nov 20 Major Release) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Consequential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov 21 Major Release |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 7: Option 1 - Risks
Dedicated environments may not be available for June 20. Candidates will be impact assessed for co-existence options once solution options agreed
SME Resource availability, particularly for SPAA changes
Scope not yet approved. Already 4 weeks behind standard 12 month Major Release plan
Scope or Testing (quality) will be reduced by any further delay in June 20 scope approval if Release date remains as June 26th
Issue of Change Packs reliant on scope being confirmed before Detailed Design starts (09/09).

## Slide 8: Option 2 – Minor Releases and Retro+
EUC | MiR 5 | Nov 19 | Doc | MiR 6 | MiR 7 | MiR 8 | MiR 9 | Nov 20 | CSS | Nov 21
 |  |  |  | Candidates |  |  |  |  |  | 
4655 | 4871A | 4621 4679 4725 4866 | 4851 4955 | 4897 4899 | 4645 4716 4801 | 4865 4888 4772 4930 4931 | 4691 4692 | Retro (4914) 4780B 4850 4871B 4941 4932 | CSSC (4854) | Tbc
2019 |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
EUC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mir D5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nov 19 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | MiR D6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | MiR D7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | MiR D8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | MiR D9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Retro (Nov 20 Major Release) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Nov 20 Major BAU Scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Consequential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov 21 Major Release |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 9: Risks – Option 2
Dedicated environments for Minor Releases may not be available. Impact assessments required as each solution option is approved to determine best fit
SME Resource availability, particularly for SPAA changes
4 concurrent Minor Releases sharing the same resources introduces greater delivery risk
Contractual changes, to incorporate BW will require budget reallocation approvals
Minor Release PIS windows shortened/overlapping increasing the risk to the Production UKLink service
Potential conflicts with BAU defect fix releases increasing the risk to the Production service
Retro and CSSC in Market trials at same time placing high demand on Xoserve and customer resources. Adding additional scope to Retro will exasperate this
Retro delivery scope increased by adding changes to the Nov 20 Release – risk around delivery and testing complexity
PIS for Retro could be complicated by additional scope items.

## Slide 10: Option 3 – June and Retro+
EUC | MiR 5 | Nov 19 | Doc | MiR 6 | Jun 20 (candidates) |  |  | Nov 20 | CSS | Nov 21
4655 | 4871A | 4621 4679 4725 4866 | 4851 4955 | 4897 4899 | 4645 4691 4692 4716 4772 | 4780B 4801 4850 4865 4871B | 4888 4930 4931 4932 4941 | Retro (4914) Extra scope tbc from June list | CSSC (4854) | Tbc
2019 |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
EUC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MiR D5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Nov 19 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | Document |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | MiR D6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 20 Major Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Retro (Nov 20 Major Release) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Nov 20 Major BAU Scope |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Consequential |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov 21 Major Release |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 11: Risks – Option 3
Dedicated environments for June 20 and Retro may not be available. Impact assessments required as each solution option is approved to determine best fit
SME Resource availability, particularly for SPAA changes
Minor Release schedule may require scaling back as release windows would be significantly reduced to allow for PIS and BAU defect fix releases
Retro and CSSC in Market trials at same time placing high demand on Xoserve and customer resources. Adding additional scope to Retro will exasperate this
Retro delivery scope increased by adding changes to the Nov 20 Release – risk around delivery complexity
PIS for Retro could be complicated by additional scope items.

## Slide 12: Recommendation
Xoserve recommends pursuing Option 1 – June 20 Major Release as this option presents the least risk to UKLink service.

## Slide 13: Analysis

## Slide 14: Scope of Analysis
The starting position anticipates there to be 16 changes to be delivered that will require a major release, based on any of the following criteria being met:
  Market trials required
  Performance testing required
  Change Packs required (6 months prior to implementation)
  Changes to non-ISU system(s) required (BW, MarketFlow, CMS, etc…)
To provide the most efficient delivery options Xoserve have reviewed release candidates against the following criteria:
  Efficiencies:
    Common code objects
    Common processes
    Common testing
  Opportunities to deliver change more frequently - moving from Major to Minor Release by:
    Performing Design Phase and delivering Change Packs for File Format Changes 7 months before a Minor Release
    Extending the scope of Minor Releases in include BW changes
    Identifying and potential accepting the risks of not Performance Testing changes
    Providing alternatives to Market Trials
  Risks associated with the delivery options have also been highlighted.

## Slide 15
Proposed UK Link Release Candidates XRNs
XRN | Title | HLSO Status | DSG – preferred solution | ChMC – agreed solution | Systems Impacted | Impacted Process(es)
4645 | Rejection of incrementing reads submitted for an isolated supply Meter Point (RGMA flows) | In progress | - | - | SAP ISU, SAP PO | RGMA
4691 | CSEPs: IGT and GT File Formats (CGI Files) | Yes | Yes | Yes | SAP PO, SAP ISU | SPAA
4692 | CSEPs: IGT and GT File Formats (CIN Files) | Yes | Solution to be agreed | - | SAP PO, SAP ISU | SPAA
4772 | Composite Weather Variable (CWV) improvements | Yes | Yes | Yes | SAP PO, SAP ISU | AQ
4780(b) | Introduction of Meter Asset Provider Identity (MAP ID) in the UK Link system (CSSC) | Yes | Solution to be agreed | - | MarketFlow, SAP PO, SAP ISU | SPAA, RGMA
4801 | Additional information to be made available on DES | In progress | - | - | SAP ISU, DES | 
4850 | Notification of customer contact details to Transporters | In progress | Solution to be agreed | - | SAP PO, SAP ISU | SPAA
4865 | Amendment to treatment and reporting of CYCL reads | Yes | Solution to be agreed | - | MarketFlow, SAP PO, SAP ISU | Metering (Reads)
4871(b) | Modification 665 – Changes to Ratchet Regime | In progress | - | - | DES, SAP PO, SAP ISU | SPAA, Invoicing
4888 | Removing duplicate address update validation for IGT Supply Meter Points via Contact Management Service (CMS) | Yes | Solution to be agreed | - | CMS, SAP ISU | SPAA
4941 | Auto updates to meter read frequency (MOD692) | Yes | Solution to be agreed | - | SAP PO, SAP ISU | RGMA, SPAA, AQ
4930 | Requirement to inform shipper of meter link code change | Yes | Solution to be agreed | - | DES, SAP ISU | SPAA, RGMA
4931 | Submission of space in mandatory data on multiple SPA files | No | - | - | MarketFlow, SAP PO, SAP ISU | SPAA
4932 | Improvements to the quality of the conversion factor values held on the Supply Point Register (MOD681) | Yes | Solution to be agreed | - | SAP ISU | RGMA, SPAA, AQ
4896 | Failure to supply gas system and template amendment | In progress | - | - | SAP ISU | Invoicing – other
4923 | AQ calculation for RGMA (ONUPD) Estimate Reads | Yes | Solution to be agreed | - | SAP PO, SAP ISU | AQ
4716 | Increased Field Length – “Updated by” data item | Yes | Yes | Yes | MarketFlow, SAP PO, SAP ISU | SPAA
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In progress | - | - | MarketFlow, SAP PO, SAP ISU | 
4955 | Amendment of MDD PSR Codes and Needs Code Descriptions | Yes | Solution to be agreed | - | SAP ISU | SPAA

## Slide 16: Recommended Changes – Major to Minor
The following 5 changes could be delivered in Minor Releases, with expected minimal challenges from HLSOs or Customer:
Risk: Output of Detailed Impact Assessments could change the recommendation.
XRN | XRN Title
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows)
4865 | Amendment to Treatment and Reporting of CYCL Reads
4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
4930 | Requirement to inform shipper of meter link code change
4931 | Submission of space in mandatory data on multiple SPA files

## Slide 17: Recommended Changes – Major to Minor (File Format Changes)
XRN Ref | CR Title | Market Trials | Perf Testing | Cust Change Required | File Format | BW Changes
4691 | CSEP's - IGT and GT File Formats - CGI Files* | N | N | Y | Y | N
4692 | CSEPs - IGT and GT file Formats (CIN Files)* | N | N | Y | Y | N
4772 | Composite Weather Variable (CWV) Improvements** | N | N | Y | Y | Y
The following XRNS’s 4691, 4692 and 4772 could be completed as a Minor Release if agreed with customers.
*4691/4692 Would require confirmation that market trials & performance testing are not required by customers.
** Would be need to be aligned to a major release date.
Risk: If delivered as Minor Release(s) Market Trials would not be offered. Therefore alternative method of proving testing would be required.
Risk: Change packs would need to be delivered 6 months prior to implementation meaning project team would need to shut-down scope at same time. MiR scope usually confirmed 3 months prior to implementation.

## Slide 18: Recommended Changes – Major to Minor (Business Warehouse & CMS)
XRN Ref | CR Title | Market Trials | Perf Testing | Cust Change Required | File Format | BW/CMS Changes
4772 | Composite Weather Variable (CWV) Improvements | N | N | Y | Y | Y
4801 | Additional information to be made viewable on DES | N | N | N | N | Y
4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) |  |  |  |  | Y
4925 | Incorrect display of read and asset information on DES | N | N | N | N | Y
The following XRNS’s 4772, 4801 and 4925 could be completed as a Minor Release if contractual changes are made to incorporate BW changes into the Minor Release Contract.
Risk: The existing Minor Release budget would not be able to accommodate additional spend required to deliver BW changes. Funding would need to be moved from UKLink Change Budget.

## Slide 19: Recommended Changes – Major Candidates
The following XRNSs 4850, 4780-B, 4871-B , 4904, 4932 and 4941 are recommended to remain as major release candidates as they require extensive customer testing.
In addition, XRN 4850 delivers a new service that presents end customer data to external parties and so will require extensive testing and a high level of involvement and assurance from Security. This means that it must be delivered as a Major Release.
XRN Ref | CR Title | Market Trials | Perf Testing | Cust Change Required | File Format | BW Changes
4850 | Notification of Customer Contact Details to Transporters | Y | Y | Y | Y | N
4780 - B | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | Y | N | N | N | Y
4871 - B | Modification 0665 - Changes to Ratchet Regime | Y | N | Y | Y | N
4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | N | Y | N | N | N
4941 | Auto updates to meter read frequency (MOD0692) | N | Y | ? | N | N