## UNC Issue Register
UIG Workgroup: UIG Taskforce Recommendations Tracker Last Update:20/6/19
Issue Ref. | Issue Title | Issue Priority (H/M/L) | Status | Option (Taskforce recommendations in bold) | Level of Support (number) | Industry view on Option | Supporting Comments/Issues and blockers | Option/Action Owner | Next Steps/Actions/Timescales | Status Date | Status Summary/Update
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as a Do Nothing Option. | 2019-02-26 | CLOSED
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, encourage action to re-confirm. CDSP to monitor monthly and notify relevant Shippers | 17 | high |  | Xoserve | 08/04/19 agreed in UIG WG to close as completed action as report in place from April 2019. XRN4867 in testing target date for delivery is April for March MI. In Progress: Short to medium. Adhoc report highlighting sites passed to Advocates w/c 4th to follow up with shippers effected. LJ raised internal Change Request to automate this report monthly 6/2/19.XRN4867. | 2019-04-09 | CLOSED
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 3. PAC reporting and monitoring – add new reports to Performance Assurance Report Register | 13 | med | 1. Visibility required at PAC. | PAC | 29/04/19 agreed at UIG WG to monitor in July 8/4/19 agreed at UIG WG to keep open and monitor until we understand from PAC meeting 9/4/19 how long PAC want to see this report for. Upon creation of XRN4867 UIG task force to anonymise the data and share with PAC for a short period of time e.g. 3 months. If this is required long term by PAC a formal PAC CP will need to be raised. Took to mtg 12/02/19 - agreed to progress. PAFA to take to PAC mtg 12/02/19 Xoserve to place on PAC agenda for further discussion. Medium (Mod 0660 now approved). Requires a CP to create reports | 2019-04-29 | IN PROGRESS XOSERVE & PAC - REVIEW JULY
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 4. Notify Ofgem of individual sites and Shippers | 12 | med | 1. Possible a PAC role. | PAC | 29/04/19 agreed at UIG WG to monitor in July 08/04/19 agreed at UIG WG to keep open and monitor in line with PAC reporting This is dependant on option 3 (line 6) | 2019-04-29 | IN PROGRESS XOSERVE & PAC - REVIEW JULY
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 5. Improve NDM Profiles for EUC09, e.g. create WAR Band EUCs | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as option 6 will have a mod drafted therefore this would not be required. | 2019-02-26 | CLOSED
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 6.UNC Mod: Reduce the qualifying period for Class 1 (currently 18 months or 6 consecutive calculations) | 0 | No Support |  | Xoserve | 24/06/19 & 21/05/2019 & 29/04/19 agreed at UIG WG to continue to monitor until mod has progressed. 08/04/2019 agreed at UIG WG to keep open and monitor mod progression. Sponsor is BG Mod drafted agenda item 9th April UIG work group Xoserve to draft Mod/issue paper | 2019-06-24 | IN PROGRESS MOD raised 0690s, British Gas have sponsored
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 7. UNC Mod: CDSP automatically converts sites to Class 1 after qualifying period, CDSP arranges for fitting of Daily Read Equipment | 0 | No Support |  | Xoserve | 24/06/19 & 21/05/2019 29/04/19 agreed at UIG WG to continue to monitor until mod has progressed. 08/04/2019 agreed at UIG WG to keep open and monitor mod progression. Sponsor is BG Mod drafted agenda item 9th April UIG work group Xoserve to draft Mod/issue paper | 2019-06-24 | IN PROGRESS MOD raised 0691s, British Gas have sponsored
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 8. UNC Mod: Use the UIG Weighting Factors to create a incentive to change to Class 1 (i.e. increased rate for Classes 2 to 4). | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as option 6 will have a mod drafted therefore this would not be required. | 2019-02-26 | CLOSED
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 9. UNC Mod: Create financial penalties for sites which have not been re-confirmed to Class 1 | 4 | low |  |  | Agreed to be closed at UIG WG 26/2/19 as option 6 will have a mod drafted therefore this would not be required. | 2019-02-26 | CLOSED
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 10. UNC Mod: Automatically change meter read frequency to Monthly when AQ increases above 293,000 | 14 | med |  | Xoserve | 24/06/19 - Agreed to monitor until mod is delivered, this is being reviewed under the Distribution Work Group, there is potential for this to be split into 2 seperate Mod's, Louise H is considering. 21/05/19 - agreed to monitor until mod is delivered 29/04/19 agreed at UIG WG to continue to monitor until mod has progressed. Louse H confirmed this will be raised at next Panel meeting. 08/04/2019 agreed at UIG WG to keep open and monitor mod progression. Sponsor is BG Mod drafted agenda item 9th April UIG work group Xoserve to draft Mod/issue paper | 2019-06-24 | IN PROGRESS MOD 0692 Total have sponsored
3.2.1 | NDM Sites in End User Category 09 (AQ >58.6m kWh) |  |  | 11. Ability for large sites to be in Class 2 before they are able to be Class 1 | 4 | low |  | Xoserve | Agreed to be reviewed July at UIG WG 26/2/19 | 2019-02-26 | REVIEW JULY
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as Do Nothing option | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 2. CDSP Analyse Read Rejections for asset mismatches. Highlight mismatched asset details to Shippers to review and either resubmit the read with the correct assets or the update the asset details on UK Link as appropriate. | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 and to go with option 6 | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 3. CDSP NDM Sample validation – arrange site visits for a representative sample of the Xoserve managed sample sites to validate the daily read equipment is functioning normally and consistent with the physical asset setup on site and consistent with UK Link | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 and to go with option 6 | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 4. CDSP to Review NDM Sample Site selection and validation process. This is underway following the implementation of UNC Modification 0645S (Mandating the provision of NDM Sample Data) | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 and to go with option 6 | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 5. Xoserve defect resolution of issues impacting consumption calculations (BAU activity captured here for completeness) | 0 | No Support | 1. BAU so voting not required for continued support. |  | Agreed to be closed at UIG WG 26/2/19 ONGOING BAU MANAGEMENT OF AQ DEFECTS | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 6. UNC Mod: CDSP Reconcile a representative sample of UK Link Asset Data (not the NDM Sample Data). Investigate mismatched asset details and update the appropriate user's records where necessary. This will give an indication of the potential level of asset data quality issues on UK Link. | 6 | low | 1. Can this be done from portfolio snapshot (SBl) - UNC 431 subject to permissions. | Xoserve | 29/04/19 agreed that as this is mod 0651 is going into capture we should review this and consider the data items in August. 08/04/19 agreed at UIG WG that the task force will bring to next meeting an aligned list of data items to understand if MOD 0651 will address all data items Mod approved. A CP will be presented at Change Management Committee on Wednesday 10th April – where Mod 0651 will be formally moved into the Capture phase to agree requirements and solution options with impacted parties. The indicative plan is that an enduring Retrospective Data Update solution is to be implemented in November 2020, however we still need to understand where the Data Cleansing Exercise sits, and are not in a position yet to confirm timescales and detailed plan – this will be clarified once requirements have been confirmed and solution options have been approved. Agreed to review in April, post 0651 Mod decision at UIG WG 26/2/19 ACTION - to investigate 431 report (Workgroup does not believe it does) Low-Medium. Would potentially require UNC modification, sponsorship from shippers and / or the regulator and / or commercial arrangement with MAMs / the DCC / MRAs and or End User support. UPDATE: Confirmed 431 is not at data level required and cannot be used. | 2019-04-29 | REVIEW AUGUST
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 7a. UNC Mod: Asset Data Cleanse – CDSP to Reconcile entire UK Link Asset Data portfolio. Investigate mismatched asset details and update the appropriate user’s records where necessary. Assumes no approval of 0651 | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 and to go with option 6 | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 7b Use UNC Mod 0651 - Changes to the Retrospective Data Update provisions reports if mod approved | 9 | med | 1. General comment - issue in relation to the need for data cleansing activities (LW). | Xoserve | 29/04/19 agreed that as this is mod 0651 is going into capture we should review this and consider the data items in August. 08/04/19 agreed at UIG WG that the task force will bring to next meeting an aligned list of data items to understand if MOD 0651 will address all data items Mod approved. A CP will be presented at Change Management Committee on Wednesday 10th April – where Mod 0651 will be formally moved into the Capture phase to agree requirements and solution options with impacted parties. The indicative plan is that an enduring Retrospective Data Update solution is to be implemented in November 2020, however we still need to understand where the Data Cleansing Exercise sits, and are not in a position yet to confirm timescales and detailed plan – this will be clarified once requirements have been confirmed and solution options have been approved. Agreed to review in April, post 0651 Mod decision at UIG WG 26/2/19 To assess further following approval of 0651, to work out next steps | 2019-04-29 | REVIEW AUGUST
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 8. UNC Mod: Require validation of Meter Asset Details whenever an actual read taken by a Meter Read Agent. Mismatches flagged to the shipper for investigation and update where appropriate | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 and to go with option 6 | 2019-02-26 | CLOSED
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 9. UNC Mod/s: CDSP to obtain smart meter readings and asset data direct from the DCC rather than the shipper. Would also potentially need a data cleanse exercise to align asset data between the DCC and UK Link to minimise asset based read rejections | 2 | low |  | Xoserve | UIG WG 24/06 LJ updated that FC has contacted DWG and are awaiting response, will bring update to next meeting July. Agreed at UIG WG 09/04/19 to review again in June, Mark B to share a contact at DWG to understand how electricity are progressing with this approach Agreed UIG WG 26/2/19 to review April (POST OPTION 6 & 7B) Would require multiple UNC Modifications, Changes to the Smart Energy Code and system / file flow changes | 2019-06-24 | REVIEW JULY
3.2.2 | Inaccurate / Out of date AQs - Sample sites with different consumption patterns or levels compared with UK Link |  |  | 10. PAC investigation of read rejections reports | 4 | low | 1. New option proposed in meeting. | PAC | UIG WG 24/06/19 LJ updated this is part of the shipper performance pack drop approach which was presented in change & DSG. Agreed in UIG WG 8/4/19 & 29/04/19 to continue to monitor until change is implemented This recommendation is already covered under XRN4876(being managed by ES) therefore no additional changes need to be raised. Dates TBC PAFA to take to PAC mtg 12/02/19 Although limited support it was suggested that it is taken to PAC for discussion/completeness. | 2019-06-24 | REVIEW AUGUST IN PROGRESS UNDER XRN4876
1 | Use of estimates for Daily Metered (DM) Sites | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as do Nothing option | 2019-02-26 | CLOSED
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 2. Engagement with DMSPs – monitor read rejections for Class 1. Resurrect previous initiatives to monitor and help resolution Engagement with Shippers – monitor read rejections for Class 2. Provide encouragement for action to be taken. CDSP to monitor monthly and notify relevant Shippers/DMSPs | 13 | med |  | Xoserve | UIG WG 24/06/19 LJ this is in the data stack rank to be started in October. Propose review in November 2019. Agreed in UIG WG 21/05 to monitor until XRN4868 is completed. Agreed in UIG WG 08/04 to continue to monitor until completed. LJ 26/3/19 solution document being shared to close out capture and move to delivery, target date tbc. LJ 7/2/19 - CR raised to develop reporting CR4868 Low to medium – requires Shipper/DMSP co-operation If UNC Mod 0647 goes ahead (Opening Class 1 Reads to Competition) could Class 1 read performance drop further? | 2019-06-24 | REVIEW NOVEMBER IN PROGRESS UNDER XRN4868
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 3. Notify Ofgem of individual sites and associated Shippers | 13 | med |  | Xoserve | UIG WG 24/06/19 reviewed in line with option2 as above. Agreed in UIG WG 21/05 to monitor until XRN4868 is completed Agreed UIG WG 08/04 to review in May when CR is progressed. Review April once CR is delivered. Low to medium – requires Shipper co-operation unless Ofgem can apply any financial leverage | 2019-06-24 | REVIEW NOVEMBER IN PROGRESS UNDER XRN4868
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 4. PAC reporting and monitoring – PAC to engage with Shippers on basis of existing and/or new reports in Performance Assurance Report Register. Consideration of any additional reporting to PAC |  | No Support | 1. BAU as part of PAC reporting. | PAC | UIG WG 24/06/19 LJ updated this is part of the shipper performance pack drop approach which was presented in change & DSG. Agreed in UIG WG 08/04 to keep monitoring until change is implemented. This recommendation is already in hand under XRN4795 ES therefore no additional changes are required. Date TBC PAFA to take to PAC mg 12/02/19 (to consider any additional/amendments to reports) Although no support it was suggested that it is taken to PAC for discussion/completeness. | 2019-06-24 | REVIEW AUGUST IN PROGRESS UNDER XRN4795
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 5. UNC Mod: Review DMSP read incentive framework (Class 1) | 2 | low |  |  | Agreed to be closed at UIG WG 26/2/19 as all other options are being considered. | 2019-02-26 | CLOSED
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 6. UNC Mod:Reduce the duration for the Class 2 Must Read trigger & extend to include Class 1 | 5 | low | 1. Option challenged by GDNs as there is already an obligation to provide reads(CW). 2. Monthly must read could work where there is an asset failure - would need a mod (CW). 3. Does not have long lead time (CW). | Xoserve | Agreed UIG WG 08/04 to review in August. Agreed to be reviewed April at UIG WG 26/2/19 (POST OPTIONS 2,3&4.) | 2019-04-08 | REVIEW AUGUST
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 7. UNC Mod: Introduce incentives or liabilities for low submission rates for Class 2, and/or extend Class 1 liabilities to apply to Shippers | 11 | med | 1. npower mod is it going to be withdrawn? 2. Recommendation to include with option 8. | PAC | Agreed to review in line with MOD UIG WG 24/06/19 Agreed to be closed as there is now a drated incentrives mod which requires a sponsor therefore this line is duplicated Agreed in UIG WG 08/04 to review in May in line with MOD 664 (this mod will be withdrawn by Npower but may be sponsored by another shipper whereby they may consider the UIG sharing mechanism for penalties as an alternative approach. 26/3/19 mtg to be held with Xoserve and Scottish power to consider FC's proposal using UIG sharing mechanism for penalties UIG WG 26/2/19 Xoserve to discuss with Npower alternative suggestions to current Mod 664. PAFA to take to PAC mtg 12/02/19. SCP to progress 0674 that gives powers to PAC and step 2 is for PAC to consider introducing such an incentive UNC Mod timescales plus system changes | 2019-06-24 | CLOSED
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 8. UNC Mod: CDSP obtains reads by installing AMR | 0 | No Support | 1. Recommendation to consider with 7. | PAC | Agreed to close at UIG WG 26/2/19 as this would be up to PAC if they wanted to consider this as an option to low performance. To consider including this line with above hence IN PROGRESS STATUS SUGGESTED | 2019-02-26 | CLOSED
1 | Use of estimates for Daily Metered (DM) Sites |  |  | 9. UNC Mod: Amend the industry processes to allow CDSP to obtain the reads directly from the read provider (DMSP/DCC etc.) | 2 | low |  | Xoserve | UIG WG 24/06/19 LJ mod 0647 is being withdrawn and replaced with 0694R, agreed in WG to Close down. Agreed in UIG WG 08/04 to review in June in line with progression of MOD 0647. Task Force to engage with Strategy to understand what consideration has been made with regards to Xoserve & DCC future relationship, mtg 28/3/19. Still on Xoserve's radar for progression. | 2019-06-24 | CLOSED
12.1 & 12.3 | Site-specific conversion factors | Low | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed to be closed at UIG WG 26/2/19 as do Nothing option | 2019-02-26 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 2. CDSP Engagement with Shippers – highlight the individual sites, provide support, encourage action to update correction factors. CDSP to monitor monthly and notify relevant Shippers | 13 | med |  | Xoserve | Agreed in UIG WG 24/06/19 & 08/04 29/04 to continue to monitor this in line with EON raised mod 0681. LJ 7/2/19 - Existing MI available in Shipper performance packs with MPRN level data. Advocates to highlight impact to UIG & engage with individual shippers. This applies to all options involving customer engagement - call for Xoserve to develop a strategy/timescales for a co-ordinated engagement with Shippers (possibly new reports with priority rating) and possible escalation routes (if performance is not improved) To coincide with Change Proposal (XRN 4789) looking to review and streamline Shipper reports | 2019-06-24 | IN PROGRESS MOD0681 RAISED
12.1 & 12.3 | Site-specific conversion factors |  |  | 3. PAC reporting and monitoring – add new reports to Performance Assurance Report Register for 12.3 (already exists for 12.1) | 9 | med | 1. Dependent on other changes. | PAC | UIG WG 24/06/19 LJ updated this is part of the shipper performance pack drop approach which was presented in change & DSG. Agreed in UIG WG 08/04 & 29/04 to continue to monitor until change has been implemented. This recommendation is already being covered under XRN4876 ES and therefore no further changes are required. Dates TBC PAFA to take to PAC mtg 12/02/19. To consider extension of reporting to include issue 12.3, as part of a future PAC meeting. | 2019-04-26 | REVIEW AUGUST IN PROGRESS UNDER XRN4876
12.1 & 12.3 | Site-specific conversion factors |  |  | 4. Notify Ofgem of individual sites and Shippers | 3 | low |  | Xoserve | Agreed in UIG WG 08/04 to review in July. Agreed UIG WG 26/2/19 to review in April. Consider after PAC reporting reviewed | 2019-04-08 | REVIEW JULY
12.1 & 12.3 | Site-specific conversion factors |  |  | 5. Allow CF to be amended via Supply Point update (as alternative to RGMA updates) | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 9 is chosen solution. | 2019-02-26 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 6. UNC Mod: UNC Mod to introduce incentives or penalties on inappropriate CFs as an addition to the existing PAC reports | 3 | low |  | Xoserve | Agreed in UIG WG 28/04/19 that this can now be closed and a new line added to cover the new incentives mod to be drafted by Xoserve which could cover a number of areas of concern, CF's being one of them. Agreed UIG WG 08/04 to review next meeting. Agreed UIG WG 26/2/19 to monitor in line with option 3 Pac reporting. Medium/long – system changes | 2019-04-29 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 7. UNC Mod: New process to allow CDSP to liaise with MAM to obtain the new correction factor – either update UK Link or provide to Shipper to update | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 9 is chosen solution. | 2019-02-26 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 8. UNC Mod: New process to allow CDSP to trigger either a desktop process or a site visit to obtain the new correction factor – either update UK Link or provide to Shipper to update | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 9 is chosen solution. | 2019-02-26 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 9a. UNC Mod: Use the last non-standard CF (if present) if the site AQ increases above 732,000 | 10 | med | 1. Consider with 10 and 11. | E.ON UK | Agreed in UIG WG 24/06/19 & 08/04 & 29/04/19 to monitor each meeting until Mod progressed. Mod0681 raised and submitted Agreed UIG WG 26/02/19 & with Kirsty EON Xoserve will start drafting the MOD capture and share for review - FC Sponsor = EON Long – UNC Mod timescales plus system changes Xoserve happy to provide support to detail MOD | 2019-06-24 | IN PROGRESS MOD0681 RAISED
12.1 & 12.3 | Site-specific conversion factors |  |  | 9b. UNC Mod: Introduce incentives or penalties as an addition to the new PAC reports | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 9 is solution. Long – UNC Mod timescales plus system changes | 2019-02-26 | CLOSED
12.1 & 12.3 | Site-specific conversion factors |  |  | 10. UNC Mod: Default the Conversion Factor to standard when the AQ drops below 732,000 | 11 | med | 1. Consider with 9a and 11. | E.ON UK | Agreed in UIG WG 24/06/19 & 08/04 & 29/04 to monitor each meeting until Mod progressed Mod0681 raised and submitted Agreed UIG WG 26/02/19 & with Kirsty EON Xoserve will start drafting the MOD capture and share for review - FC Sponsor = EON Long – UNC Mod timescales plus system changes Xoserve happy to provide support to detail MOD | 2019-06-24 | IN PROGRESS MOD0681 RAISED
12.1 & 12.3 | Site-specific conversion factors |  |  | 11.Change Proposal: Hold the standard CF as a central parameter rather than against meter points – ensures that calculation always uses correct value | 8 | med | 1. Consider with 10 and 9a. | E.ON UK | Agreed in UIG WG 24/06/19 & 08/04 & 29/04 to monitor each meeting until Mod progressed Mod0681 raised and submitted Agreed UIG WG 26/02/19 & with Kirsty EON Xoserve will start drafting the MOD capture and share for review - FC Sponsor = EON Long – UNC Mod timescales plus system changes Xoserve happy to provide support to detail MOD | 2019-06-24 | IN PROGRESS MOD0681 RAISED
12.2 | Standard conversion factors | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed UIG WG 26/02/19 to close as do nothing option. | 2019-02-26 | CLOSED
12.2 | Standard conversion factors |  |  | 2. Use actual LDZ temperatures to convert consumptions used to develop the NDM Profiles (ALPs and DAFs) – to be further refined at DESC forum | 3 | low |  | Xoserve | 24/06/19 suggested to monitor while review group running 0694R 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 Consider further at follow up UIG WG FC to add further details to recommendations for future consideration. Short/medium – pending DESC review | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 3. Influencing strategy to amend Thermal Energy Regulations | 0 | No Support |  | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 4. UNC Mod: Add a new LDZ level factor to the volume-to-energy conversion formula to account for the net difference in energy. The factor could either be a fixed value reviewed periodically, or calculated daily using actual LDZ weather | 0 | No Support |  | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 5. Amend AUGE process to re-distribute UIG based on estimated impacts of conversion factors (forecast basis) | 1 | low |  | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29.04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 Consider further at follow up UIG WG FC to add further details to recommendations for future consideration. | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 6. UNC Mod: to introduce retrospective adjustment to allocations based on actual weather for the year | 0 | No Support |  | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 7. UNC Mod: Introduce an LDZ level conversion factor (permanent/per year/per month) | 0 | No Support | 1. Linked to option 4 | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 8. Amend UNC/legislation to require site specific conversion for every site | 0 | No Support | 1. Could this be done for smart metering as a long term solution? (MB) | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 9. Suggested by Shipper: UNC Mod: Create a new category of Energy, treated similarly to Shrinkage, where a percentage of daily throughput is allocated as a Correction Factor error. The percentage of energy would be set at LDZ level based on daily profiled seasonal normal temperature, and then retrospectively trued-up based on the actual LDZ temperature. | 4 | low | 1. Is a distinction needed between internally and externally located meters? | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 Consider further at follow up UIG WG FC to add further details to recommendations for future consideration. | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
12.2 | Standard conversion factors |  |  | 10. LDZ level adjustment of input gas. (SBl) | 4 | low |  | Xoserve | 24/06/19 suggested to monitor while review group running 21/05/19 - Scottish Power confirmed that this will be taken to June's Panel meeting. Agreed at UIG WG 08/04 & 29/04 that this will be sponsored by Scottish Power Mark B, agreed to monitor until the mod is progressed. Mod Drafted Agreed at UIG WG 26/2/19 Xoserve to Draft Mod to create a review group for 12.2 Consider further at follow up UIG WG FC to add further details to recommendations for future consideration. | 2019-06-24 | IN PROGRESS REVIEW GROUP 0693R RAISED
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as do nothing option. | 2019-02-26 | CLOSED
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 2. Engagement with Shippers around monitoring read rejections and how CDSP can support through industry processes. We have shared specific sites we have identified with the Customer Account Managers and CDSP will work with the Shippers to resolve | 12 | med | 1. In progress. | Xoserve | Agreed UIG WG 08/04 to close down as BAU process in place. LJ 07/02/19 Read rejections are already included in the shipper performance packs. Advocates to engage with customers to understand issues and highlight the impact to UIG. To be defined. | 2019-04-08 | CLOSED
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 3. XRN4690 will prevent the AQ defaulting to 1 where there is a negative consumption value held on UK Link. Additionally, we could run impacted MPRNs through the AQ correction tool once the code fix is deployed rather than waiting for rolling AQ to increase the AQ back to a suitable level | 9 | med |  | Xoserve | Agreed at UIG WG 26/2/19 to review in July. XRN4690 is in progress, 2 reports delivered, next one due July, further to follow throughout the year. Medium. Would likely require user approval to correct their Aqs | 2019-02-26 | REVIEW JULY
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 4. There is an issue where a shipper cannot submit an AQ correction because there has not recently been an AQ calculation, but the shipper cannot submit a read because it is rejecting for AQ tolerance reasons. This would leave the shipper in a loop unable to correct the AQ. There is a pending change (XRN4803) to allow the AQ to be corrected in this scenario | N/A | high |  | Xoserve | Agreed at UIG WG 26/2/19 to review in July. XRN4803 will be implemented as part of a Minor release target July 2019. This change is already underway and so will not be part of the recommendations but is captured here for completeness | 2019-02-26 | REVIEW JULY
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 5. Enhance PAC reporting around AQ corrections to include more detail and highlight areas of potential concern. PAC have visibility of AQ corrections and this will be enhanced to show the split between AQ increases and decreases and highlight any unusual activity | 10 | med |  | PAC | UIG WG 24/06/19 LJ updated this is part of the shipper performance pack drop approach which was presented in change & DSG. Agreed in UIG WG 8/4 & 29/04 to monitor until change is implemented. This recommendation is already covered under XRN4876 ES therefore no further change is required. Dates TBC PAFA to take to PAC mtg 12/02/19 (To consider if existing reporting is adequate or further details are required.) Existing Agenda item for PAC - Xoserve to work with PAFA to define proposal for next meeting. In progress; Medium | 2019-06-24 | REVIEW AUGUST IN PROGRESS UNDER XRN4876
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 6. UNC Mod: We have been advised that some shippers are setting AQs to <10 using the AQ correction process where the site is vacant. We could raise a change to create a Vacancy flag on UK Link which would stop the AQ contributing to allocation, resulting in a benefit to the shipper without putting the AQ at risk........ | 2 | low | 1. Any further proposal would need to consider points raised by Ofgem in relation to (Mod 0282) |  | Agreed UIG WG 26/2/19 to close as this is covered under option 5 as the increase and decrease of AQ will be visible in the PAC reporting. Would require a UNC Modification and system changes. | 2019-02-26 | CLOSED
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 7. Raise a change so that where an AQ is corrected by the Shipper and a read received within [6] months with a metered consumption that is out of line with the corrected AQ, the AQ correction will be overridden by the usual AQ calculation process and the Shipper notified. | 0 | No Support |  | Xoserve | Agreed in UIG WG 26/2/19 to review in December (if UIG WG no longer in existence at that point this would need to be captured elsewhere) | 2019-02-26 | REVIEW DECEMBER
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 8. UNC Mod: Raise a change to shorten the required read period for AQ calculation to [3] months where the AQ is <[100] until a sufficient read history is available to calculate normally, | 0 | No Support | 1. Use of previous reads where an AQ correction has been used in the calculation. | Xoserve | Agreed in UIG WG 26/2/19 to review in December (if UIG WG no longer in existence at that point this would need to be captured elsewhere) | 2019-02-26 | REVIEW DECEMBER
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 9. UNC Mod: Create new “Vacant Site” AQ correction reason code and logic to allow an AQ correction where the AQ is 1 without the need to have a recently accepted read on UK Link | 0 | No Support | 1. See Mod 0282 (2011) | Xoserve | Agreed in UIG WG 26/2/19 to review in December (if UIG WG no longer in existence at that point this would need to be captured elsewhere) | 2019-02-26 | REVIEW DECEMBER
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 10. UNC Mod: Reducing the AQ below [100] kWh or by [95%] would trigger a requirement to provide a read or a site visit to obtain a read within [30] Days or the AQ correction would revert to the previous prevailing value. If the provided read energy does not align with the amended AQ then the AQ will revert to the previous prevailing value. If a subsequently submitted read calculates energy materially different from the deemed energy, the AQ will revert to the previous prevailing value and the site will be back billed | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close, future AQ related recommendations will be generated. | 2019-02-26 | CLOSED
3.2.8 | Inaccurate/Out of date AQs - Sample sites consuming energy with a UK Link AQ of 1 |  |  | 11. Increased validation (ES) - tighten up validation around an AQ correction | 1 | low |  |  | Agreed UIG WG 26/2/19 to close, future AQ related recommendations will be generated. | 2019-02-26 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read | Medium | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed UIG WG 26/2/2019 to close as do nothing option. | 2019-02-26 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, and shippers to raise tickets so CDSP can manually enter reads by exception | 15 | med |  | Xoserve | Agreed in UIG WG 8/4 to close as the manual work around is now in place and therefore no further customer engagement is required. LJ 26/03/19 short term and long term solution in place, short term April target date - XRN4853, long term Nov target date - XRN4866. Both in hand and therefore no monitoring or engagement required. LJ 07/01/19 2XCP'S raised to create manual work around and system solution. Initial engagement with shippers to highlight the issue to be performed by the customer advocates. Low to medium – requires Shipper to work around UK Link validation issue | 2019-04-08 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 3. Users can increment the uncorrected read so it is higher than the read currently held on UK Link without going through the Zeros. The uncorrected read is not used for billing or AQ calculation so these process will not be impacted. There could be an impact on asset exchanges as the uncorrected read recorded on site will differ from that held on UK Link. As RGMA flows are normally pass through files, these may reject requiring the shipper to modify the uncorrected exchange reading | 0 | No Support |  |  | Agreed at UIG WG 26/2/19 to close. | 2019-02-26 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 4. Shipper could submit a cosmetic corrector exchange alongside the lower uncorrected reading as this file format contains uncorrected TTZ count. Subsequent readings would then load normally assuming other validation checks pass | 0 | No Support |  |  | Agreed at UIG WG 26/2/19 to close as option 5,6&7 being developed. | 2019-02-26 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 5. CDSP to monitor rejections for this rejection code. CDSP will manually load the read to UK Link if the read has passed all other validations. Subsequent reads will load normally if they pass validation checks | 13 | med |  | Xoserve | Agreed UIG WG 8/4 to review in November when system change is scheduled. LJ 26/03/2019 manual work around to go live in April 2019. LJ 07/02/19 CP Raised XRN4853 to create the manual loading of rejected reads for MRE00458. CDSP resource required to maintain this process Workaround option: Short to medium | 2019-04-08 | REVIEW NOVEMBER
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 6. The uncorrected read will be an optional field following the November 2019 UK Link release implementation, so it can be blank and the corrected read will load | 0 | No Support |  | Xoserve | Agreed UIG WG 26/2/19 to review in November once change has been implemented | 2019-02-26 | REVIEW NOVEMBER
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 7. Raise change to UK Link to remove validation on the uncorrected read as it is not used for billing | 0 | No Support |  | Xoserve | Agreed UIG WG 8/4 to review in November when system change is scheduled. Agreed UIG WG 26/2/19 to review in November once change has been implemented LJ 07/02/2019 CP Raised XRN4866 to remove validation, to be considered to be incorporated with above change under option 6 (XRN4621) | 2019-04-08 | REVIEW NOVEMBER
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 8. Raise a change to add an Uncorrected TTZ count to the incoming and outgoing read file format and any associated logic to ISU | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 5,6&7 being developed. | 2019-02-26 | CLOSED
3.1 | AQ Calculation errors - Reads rejected because uncorrected read value is lower than previous uncorrected read |  |  | 9. Raise a change to alter the read load logic to derive the TTZ count for uncorrected reads. We would increment the uncorrected read TTZ count by 1 and load the read when the uncorrected read is lower than the previous uncorrected read and all other validation checks pass | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as option 5,6&7 being developed. Medium to Long CP required | 2019-02-26 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs | Medium | Live | 1. No action (“Do Nothing” option) or Park |  | No Support | No vote made as in progress. |  | Agreed UIG WG 26/2/19 to close as do nothing option. | 2019-02-26 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 2. Engagement with Shippers – highlight the individual sites, provide support, encourage read submission and use of the WAR Band Update process where reads not submitted in the winter acceptance periods |  | No Support | No vote made as in progress. | Xoserve | Agreed UIG WG 26/2/19 to close as completed. COMPLETED IN DEC 2018 VIA ADVOCATES FOR TOP 10 SHIPPERS In progress; Short to medium | 2019-02-26 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 3. The WAR Band calculation can fail where the Meter Read Frequency is not Monthly for a site in a WAR Band eligible EUC. Meter Read Frequency should be added to the reports proposed in Modification proposal 0652 so shippers are aware where the MRF needs to be updated before the WAR Band can be applied |  | No Support | No vote made as in progress. | Xoserve | Agreed UIG WG 26/2/19 to close. COMPLETED REQUESTED AS PART OF CAPTURE 0652. In progress; Medium | 2019-02-26 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 4. A new report to monitor sites which cross in to a WAR Band eligible EUC following Rolling AQ calculation. Proactively engage with Shippers to use the WAR Update process when needed |  | No Support | No vote made as in progress. | Xoserve | Agreed UIG WG 26/2/19 to review Dec in line with MOD652. LJ 07/02/19 Take back to 26th Feb UIG group to understand if there is a real requirement for this over and above the existing WAR Band changes before taking action. In progress; Medium | 2019-02-26 | REVIEW DECEMBER
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 5. Notify Customer Account Managers when the T51 (WAR Band Calculation Failures) report is available so CDSP can proactively manage Next Steps with Customers |  | No Support | No vote made as in progress. | Xoserve | UIG WG 24/06/19 T51 files sent this can be closed down 21/05/2019 LJ took action to confirm that this has been done, if yes close this down. Agreed UIG WG 26/2/19 to review in May This file is generated in MAY T51, Advocates to proactively highlight this file to each customer in a timely way and refer to the impact of UIG progress; Medium | 2019-06-24 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 6. CDSP to fix the Read Variance issue in UK Link |  | No Support | No vote made as in progress. | Xoserve | Agreed at UIG WH 21/05/2019 to close as this fix was deployed early May. Agreed UIG WG 26/2/19 to review in May Defect 1247 will be resolved before mid May ready for next consumption window. In progress; Medium | 2019-05-21 | CLOSED
2 | Low take-up of Winter Annual Ratio (WAR) Band EUCs |  |  | 7. Notify/escalate to Ofgem/PAC | 5 | low | 1. Dependent on progress of actions 2-6 and allowing processes to mature for example reporting arising from UNC 0652. | Xoserve | Agreed UIG WG 26/2/19 to review in November To be reviewed when other options are completed | 2019-02-26 | REVIEW NOVEMBER
13.2.2 | Accuracy of NDM Algorithm - Use of weather data - Sensitivity of components of the composite weather variable | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as do nothing option. | 2019-02-26 | CLOSED
13.2.2 | Accuracy of NDM Algorithm - Use of weather data - Sensitivity of components of the composite weather variable |  |  | 2. Provide Sensitivity analysis results to the Demand Estimation team for assessment and incorporation into SNCWV review via the Demand Estimation Subcommittee | 14 | med | 1. BAU as part of DESC work but any changes will not be implemented until Oct 2020. 2. Suggests areas in algorithm that DESC would not normally consider. |  | Agreed UIG WG 26/2/19 to close as this has been passed to DESC who have accepted this issue for review. Update 14/2/19 post DESC mtg: DESC have agreed to review this and consider as part of this years CWV formula review. DESC Mtg 11th Feb to be reviewed 2019 to be used in model 2020 to be applied to gas year 20/21 if DESC approve recommendation and make the changes. Long – may inform the current SNCWV review which will be implemented October 2020 | 2019-02-26 | CLOSED
13.2.5 | Accuracy of NDM algorithm - Use of additional weather data in the composite weather variable | High | Live | 1. No action (“Do Nothing” option) or Park | 0 | No Support |  |  | Agreed UIG WG 26/2/19 to close as do nothing option. | 2019-02-26 | CLOSED
13.2.5 | Accuracy of NDM algorithm - Use of additional weather data in the composite weather variable |  |  | 2. Next DESC review of Composite Weather Variable (CWV) formula to include the four other commonly available weather data items. | 14 | med | 1. BAU as part of DESC work but any changes will not be implemented until Oct 2020. |  | Agreed UIG WG 26/2/19 to close as this has been passed to DESC who have accepted this issue for review. Update 14/2/19 post DESC mtg: DESC have agreed to review this and consider as part of this years CWV formula review. DESC Mtg 11th Feb to be reviewed 2019 to be used in model 2020 to be applied to gas year 20/21 if DESC approve recommendation and make the changes. Medium/long – may inform the current SNCWV review which will be implemented October 2020 | 2019-02-26 | CLOSED
13.2.5 | Accuracy of NDM algorithm - Use of additional weather data in the composite weather variable |  |  | 3. Replace NDM Allocation formula with a weather-based regression formula |  | No Support | 1. Did not vote, as it is a matter for DESC to consider as part of weather data/variable work. |  | Agreed UIG WG 26/2/19 to close. | 2019-02-26 | CLOSED
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 1. Notify Ofgem of Shippers that do not achieve their read performance standards. |  |  |  | Xoserve | Agreed at UIG WG 29/04/19 to monitor in line with new drafted mods. Presented at UIG WG 8/4/19 for consideration. All PAC members to highlight this at 9th April meeting. | 2019-04-29 | REVIEW AUGUST
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 2. Use UNC M 5.13.16 transfer read incentive mechanism to improve transfer read submission performance. Incentive charge currently £0.00. |  |  |  | Xoserve | Agreed at UIG WG 29/04/19 to close as other options are being developed. Xoserve drafted mods for 3.2.5 Presented at UIG WG 8/4/19 for consideration, no support was given for this option, therefore need to agree if we can close or pause for review in future. | 2019-04-29 | CLOSED
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 3. Review the appropriateness of current Meter Read tolerances – would there be benefit in including seasonal flex to enable more legitimate consumptions to lead during higher usage periods? |  |  |  | Xoserve | UIG WG 24/06/19 - LJ presented that whilst there is a reduction in the number of tollerance rejections since the implimentation of the changes in November, there is still a seasonal trend to tollerance rejections. Agreement reached that this level of rejections is still not acceptable and now needs to be re-visited and new tollerances agreed which consider seasonal values and or ALPs consideratoin UIG WG 21/05/19 LJ carried forward to next meeting. Agreed at UIG WG 29/04/19 for Xoserve to review if the recent read rejection stats have changed now that the new tolerances are in use. Presented at UIG WG 8/4/19 for consideration. New tolerances have been implemented recently. Need to understand if the volumes of rejections are still an issue post the new tolerances implemented. Xoserve could re-investigate the level of rejections at a later date and re-consider this recommendation option, need to agree appropriate month to review at next UIG WG mtg end of April. | 2019-06-24 | IN PROGRESS
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 4. Review Small Supply Point Must Read obligations. We could: • Reduce qualifying period for an SSP Must Read to [15] months • Shift the Must Read obligation from DN to a CDSP managed MRA site visit process • Enable the CDSP to contact End Consumer directly to obtain a Meter Read |  |  |  | Xoserve | Discussed at UIG WG 29/04/19 Xoserve to check Retail Energy Code and consider the rejections on must reads with the information we have. Currently there isn't a view that this mod would be sponsored at this point. 21/05/2019 UIG WG no further discussion on this drafted mod, no interest in sponsorship at present. Presented at UIG WG 8/4/19 for consideration. Support was given for the progression for Xoserve to draft a mod. | 2019-06-24 | IN PROGRESS MOD DRAFTED 3.2.5
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 5. Change the Class 4 maximum Meter Read Frequency to 6 Months. Over 80% of sites currently achieve this standard. |  |  |  | Xoserve | 21/05/2019 UIG WG no further discussion on this drafted mod, no interest in sponsorship at present. Discussed at UIG WH 29/04/19 low level of interest shown, need to check CMA obligations. Presented at UIG WG 8/4/19 for consideration. Support was given for the progression for Xoserve to draft a mod. Consideration would have to be given to the impact to supplier licence conditions. | 2019-06-24 | IN PROGRESS MOD DRAFTED 3.2.5
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 6a Make Class 2 mandatory for sites in EUC [07] and above. These sites should already have remote daily read equipment installed. |  |  |  | Xoserve | UIG WG 24/06/19 LJ 0647 has been withdrawn and replaced with 0694R therefore what do we want to do with this option? Agreed at UIG WG to review July when mod 0647 will have progressed further. Presented at UIG WG 8/4/19 for consideration, agreed to pause and review this option once mod 0647 options have been chosen. Need to agree the next review date at UIG WG end of April. | 2019-06-24 | REVIEW JULY
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 6b *added in 8/4/19 UIG meeting. Reduce the Class 1 qualifying level. |  |  |  | Xoserve | UIG WG 24/06/19 LJ 0647 has been withdrawn and replaced with 0694R therefore what do we want to do with this option? Agreed at UIG WG to review July when mod 0647 will have progressed further. Presented at UIG WG 8/4/19 for consideration, agreed to pause and review this option once mod 0647 options have been chosen. Need to agree the next review date at UIG WG end of April. | 2019-06-24 | REVIEW JULY
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 7. Mandate an actual read on Class change. |  |  |  | Xoserve | Agreed at UIG WG 29/04 to review in November Presented at UIG WG 8/4/19 for consideration, little support given, therefore need to agree if we should review this at a later stage at next UIG WG mtg end of April. | 2019-04-29 | REVIEW NOVEMBER
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 8. Make the ONUPD estimated read replaceable. |  |  |  | Xoserve | Agreed at UIG WG 29/04 to close as no support received to progress with this change. Presented at UIG WG 8/4/19 for consideration, no support was given for this option, therefore need to agree if we can close or pause for review in future. | 2019-04-29 | CLOSED
3.2.5 | Inaccurate / Out of date AQs - Investigate the change in the AQ mix and direction of travel following introduction of Rolling AQ |  |  | 9. Create a UIG based read performance incentive. For Example: Unread AQ /12 * Average Annual UIG% * multiplier of [2] at average SAP for the month. Equal and opposite credit to shippers [that meet performance standards] using UIG reconciliation smear mechanism. |  |  |  |  | 21/05/2019 Agreed in UIG WG that this will be monitored in line with the xoserve drafted mod to introduce incentives. Agreed in UIG WG 29/04/19 that this would be a stand alone mod based on UIG incentives which can be used for multiple topics. Presented at UIG WG 8/4/19 for consideration, agreed to pause and review this option at next UIG WG mtg to understand if this could be used as part of any open existing mods e.g. 0672. | 2019-06-24 | IN PROGRESS MOD DRAFTED 3.2.5

## Lookups
Look Ups
Action Owner | Industry view on option | Priority | Status
PAC | Low Support (1-7) | Low | Live
Brittish Gas | Medium Support (8 -14) | Medium | Closed
Cadent Gas | High Support (15+) | High | Hold
Centrica
Xoserve
ConocoPhillips
Corona Energy
DNVGL
E.ON UK
EDF Energy
Energy 24
Engie
Exxon Mobil
First Utility
Flow Energy
Gazprom
Gemserv Ltd
Interchange
Joint Office
National Grid NTS
Northern Gas Networks
npower
Orsted
RWE Trading GmbH
Scotia Gas Networks
Scottish Power
Smartest Energy
SSE
Statoil UK
Tonik Energy
Total Gas and Power
Utility Warehouse
Wales & West Utilities
Waters Wye
Xoserve