## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0662 | With Workgroup | UNC - Transmission | NTS | Revenue Recovery at Combined ASEPs | 2019-10-01 | Rule & System change | NA | UK Link and Gemini | Potential impacts to UK Link and Gemini. Please note - this is a single event change | NA | Transmission and Shared Services | Steve Pownall | The purpose of this modification is to allow entry capacity booked for the entry of gas into the NTS from storage sites within combined Aggregated System Entry Points (ASEPs), to be treated the same as a “Storage Site” as designated in National Grid’s Licence with respect to the application of any revenue recovery charge based on capacity bookings. The required changes will be captured as part of the EU GB Charging project. Xoserve systems have been impact assessed and the development of the modification solution is relatively simply. Dependent on 0678 decision. Ofgem have agreed to an extension.
Mod 0664 | With Workgroup | UNC -UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | No implementation specified | Rule & System change | NA | UK Link | Impacts on UK Link to bulk transfer invoicing to charge for avoided UIG weighting factors | NA | Retail & Network | Simon Harris | Modification looks to create an obligation for Shippers to move sites with low meter read submission performance from Product Class 2 and 3 into Product Class 4 in the first year of entry to the settlement class. Proposal is to give Shippers a timescale to move sites where there is poor read submission performance. If the move does not occur during the assigned time period, the CDSP will be expected to move the sites. Impacts for invoicing to charge for avoiding UIG weighting factors. ROM was requested but subsequently withdrawn. System impacts are dependent on the outcome of the modification which is currently undecided. Modification adopted by SSE. Modification needs to consider how it interacts with modification 0700. Continue to develop in WG.
Mod 0667 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | South Hook Gas Company Ltd | Inclusion and Amendment of Entry Incremental Capacity Release NPV test in UNC | No implementation specified | Contractual change & potential Rule change | NA | Confirmed as no system impact. | As the modification remains as a contractual change only, there will be no system impacts. | NA | Transmission and Shared Services | Steve Pownall | Modification seeks to insert the Net Present Value test required for Non-IP Entry Incremental Capacity Release into UNC, and amend the mechanics of the test to ensure that it works effectively with the current GB system. Modification should have no impact on central systems as it is purely contractual, moving National Grid methodology into UNC. It was thought that the solution may not only be contractual and could have system impacts and may interact with Modification 0671. Following discussions at Transmission WG, it has been confirmed that there will be 'no impact' to central systems. Panel members voted to implement modification 0667 at the June Panel meeting. Modification is now with Ofgem for a decision. No central system impacts.
Mod 0669R | With Workgroup | UNC -Transmission | NTS | Review of the Gas Deficit Warning (GDW) and Margins Notice (MN) Arrangements | Any Modifications as a result of 0669R will be impact assessed and system implications considered. From the modifications that have come out of the review group, none have impact to central systems. | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to review the processes, timeliness, and information provision associated with National Grid’s gas security of supply notices and to review the name of the Gas Deficit Warning notice. Panel agreed a Working Group should be set up for 6 months to review the processes. There may be process and system impacts dependent on the outcome of the review as Xoserve maintain certain offline GDW business processes but the current proposal does not change these. Modification 0685 has been raised following this Review Group. Panel agreed to WG extension. Second modification has been raised (0689). Central impacts not expected. Review Group report due to be completed in August.
Mod 0670R | With Workgroup | UNC - NTSCMF | NTS | Review of the charging methodology to avoid the inefficient bypass of the NTS | Any Modifications as a result of 0670R will be impact assessed and system implications considered. If Modification is raised, it is likely to have cross-platform impacts (Gemini and SAP ISU). | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to conduct an assessment of the charging methodology that is a feature of the overall Gas Transportation Charging framework to avoid the inefficient bypass of the NTS (currently the NTS Optional Commodity charge). The review assesses the objectives, identify requirements, analyse potential options and propose an enduring proportionate solution. Workgroup will consider consultation responses from 0621, 0635 and 0653. Currently 3 ideas for a charging methodology to avoid the inefficient bypass of the NTS. 2 of the 3 have been raised as alternates to 0678. If a Modification is raised from the review group, it is likely to have central impacts as any new NTS short haul product will be based on NTS capacity rather than commodity
Mod 0671 | With Workgroup | UNC -Transmission | WWU | New Capacity Exchange process at NTS exit points for capacity below baseline | TBC | Rule & System Change | TBC | System Impacts | Gemini system impacts to transfer User's Capacity between NTS Exit Points | TBC | Transmission and Shared Services | Steve Pownall | Modification proposes changes to the User Commitment obligations in TPD Section B to improve the efficiency of NTS Firm Exit Capacity bookings. October Panel issued the Modification to Workgroup due to report back in February 2019. Central systems will be impacted to transfer User's Capacity between NTS Exit Points. ROM response has been provided. Main impacts to Gemini. WG discussions deferred until August.
Mod 0672 | With Workgroup | UNC - UIG | Scottish Power | Target, Measure and Reporting Product Class 4 Read Performance | No implementation specified | Reporting | NA | UK Link | A Change Proposal will be required to deliver the reports specified under the Modification. The incentive regime will need to be developed with considerations around the invoicing element | NA | TBC | Simon Harris | Modification has changed significantly and removed the incentive element. Focus is now on measuring performance. seeks to reduce Unidentified Gas (UIG) volume by providing a target for read submission performance for Product Class 4 sites against total kWh settled. This modification proposes to target and measure performance against an agreed percentage for Energy reconciled after a defined period and provide PAC with a report which will enable them to target shippers whose performance is below the target threshold. The central system impacts are now around creating new reports to measure performance. 2 month extension requested so WG report expected in September.
Mod 0674 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | A Change Proposal will be required to deliver the reports specified under the Modification. The incentive regime will need to be developed with considerations around the invoicing element. | TBC | NA | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any Modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. Discussed again at March Panel and agreed for the Workgroup to be extended to August. Any changes from the review group will be assessed for central impacts. Next meeting is 30 July.
Mod 0677R | With Workgroup | UNC - WG | First Utility | Shipper and Supplier Theft of Gas Reporting Arrangements | Any Modifications as a result of 0677R will be impact assessed and any implications considered. Potential system impacts are within CMS. | [5 empty] | NA | Ellie Rogers | This request is to review and identify any discrepancies in Shippers and Suppliers theft of gas reporting arrangements. Any changes from the review group will be assessed for central impacts. Four month Review Group extension requested and approved by Panel. Now due to report back in October. Solution options are currently being discussed. Central system impacts are possible depending on the solution options.
Mod 0678 (A-J) Urgent | Awaiting Ofgem Decision | 0678 WG | Various proposers | Amendments to Gas Transmission Charging Regime | October 2019 | Rule and System Change | No | UK Link and Gemini | Impact picked up through the Gemini project team | Oct-19 | Transmission and Shared Services | Steve Pownall | Modification proposal is to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges and to deliver compliance with relevant EU codes (notably the EU Tariff Code). There are currently 11 alternates. Modifications look to address the issues highlighted in the Ofgem rejection letter for 0621 and the alternatives. Impacts to be picked up as part of the project team. Urgent status has been granted by Ofgem. Panel did not recommend that 0678 or any of the alternates should be implemented. Panel also indicated no clear majority view on the preference around which Modification better facilitates the Relevant Objectives. Modification and alternates are with Ofgem for a decision. Once decision is confirmed, the central changes will be picked up through the Gemini project team and delivered in October 2019.
Mod 0681S | Approved and awaiting implementation Proposed to be removed from Bubbling Under | UNC - UIG | E.ON | Improvements to the quality of the Conversion Factor values held on the Supply Point Register | TBC | Rule and System Change | No | UK Link | Changes to identify the required sites and automate updates | Jun-20 | Retail & Network | Simon Harris | The purpose of this Modification is to improve the quality of the Conversion Factor data item on the Supply Point Register, which will in turn improve the accuracy of measured energy and therefore AQs. Change Proposal will be raised with the CDSP to deliver the requirements once the modification is suitable developed. Following the consultation period, July Panel voted to approve the implementation of 0681S. Change Proposal with the CDSP - XRN4932 was conditionally approved for inclusion in the June 2020 Release (dependent on the modification outcome). Propose to remove from Bubbling Under as an Change Proposal has been raised and is currently in consideration for June 2020 release.
Mod 0682 | Awaiting Ofgem decision Proposed to be removed from Bubbling Under | DWG | E.ON | Market Participant MDD Migration to UNC Governance from the SPAA | Feb-2020 | Obligation Change | NA | No system impacts | Creation of an obligation on the CDSP to manage the industry Market Participant Identifiers | Feb-20 | NA | Dave Addison | This modification requires that the CDSP manages the gas Market Domain Data for Market Participant Identities which are required to align with the introduction of the Retail Energy Code via the Central Switching Service and to align with the corresponding SPAA Change Proposal 467. No system impacts expected at this stage through this modification as it simply places the obligation on the CDSP in UNC. CP has been raised with the CDSP to deliver the necessary processes. Following the consultation period, July Panel voted to approve the implementation of 0682. To align with the equivalent SPAA change, the modification has gone to Ofgem for a decision. No system impacts expected for the Feb 2020 implementation. Process updates only. Any future system impacts for example the introduction of file flows is expected to be picked up as part of CSS. Proposed to be removed from Bubbling Under.
Mod 0683 | With Workgroup | Transmission | Cadent | Updating the Offtake Arrangements Document (OAD) with recommendations resulting from UNC Request Workgroup 0646R – Review of the Offtake Arrangements Document – Phase 1 | NA | Documentation Change | NA | No system impacts | No central system impacts. Document change only | NA | NA | NA | This modification seeks to update the OAD in order to bring it in line with industry changes made since 2005. The Request 0646R Review of the Offtake Arrangements Document, Workgroup has since identified a number of areas in OAD that can be updated now (Phase 1), with this being the first in a number of modifications. No central system impacts expected.
Mod 0685 | Approved and awaiting implementation Proposed to be removed from Bubbling Under | NA | National Grid | Amendment of the UNC term ‘Gas Deficit Warning’ to ‘Gas Balancing Notification’ | Oct-19 | Documentation Change | NA | Do not believe there are any system impacts | Need to assess but do not believe there are any system impacts | Oct-19 | NA | NA | To change the name of the UNC defined term ‘Gas Deficit Warning’ to ‘Gas Balancing Notification’. This modification is an outcome of the 0669 Review Group. June Panel voted to implemented. Ofgem approved implementation. Expected on 01 October 2019. No system impacts expected. Proposed removal from Bubbling Under.
Mod 0686 (Urgent) | Awaiting Ofgem decision | Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Transmission and Shared Services | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. June Panel did not recommend the implementation of modification 0686. Currently with Ofgem for a decision. Modification must still be assessed to consider a phased implementation of the 0678.
Mod 0687 | With Workgroup | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Impact assessment required but changes to introduce a new charge at the minimum | TBC | Retail & Network | Dave Addison /Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. WG report complete and due to go back August Panel. System impacts expected to introduce a new charge type at the minimum. Three options have been presented, two involve less system change and the other (adding the invoice to the Core invoice) will involve major system changes. The degree of central system impact could vary depending on the preferred solution option. System delivery is expected by April 2019 which will impact the possible solution. The DSC Change Proposal has been raised.
Mod 0688 | With Workgroup | Transmission | Contract Natural Gas (on behalf of ICoSS) | Recovery of Shipper Losses incurred in Supplier of Last Resort events | TBC | System Change | No | TBC | Impact assessment required as it is currently unknown what and if this has central impacts | TBC | TBC | Steve Pownall | A change is proposed to allow Shippers that have incurred unrecoverable costs from shipping for sites where the Supplier is subject to a Supplier of Last Resort event, to recover such costs via Balancing Neutrality Charges. With WG for development. As currently drafted, system changes are likely and need to be assessed fully once the business rules are finalised. Two month extension at the July Panel was requested.
Mod 0689 | With Workgroup | UNC - DWG | Gazprom Energy | Removing the requirement to support Invoice queries before the due date with information from the .AML file | TBC | Rule Change | No | TBC | Impact assessment required as it is currently unknown what and if this has central impacts or if it is processes only | TBC | TBC | Dave Addison /Ellie Rogers | The purpose of this Modification is to allow Shippers to provide alternative supporting data when querying invoices from the CDSP. Seeks to remove obligation on Shippers to use CDSP provided supporting data to challenge an invoice. This is proposed due to the issues with the .AML file output. Modification development on hold until September as the SLAs set by the AML/ASP Taskforce and agreed by the industry are expected to be met by August. Depending on the outcome of this, the modification discussions could continue following the September meeting.
Mod 0690 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | Reduce qualifying period for Class 1 | TBC | Rule and Reporting Change | No | No system impacts | ROM response indicated that the data items required for the PAC report are already available and no system changes are required. | TBC | Data | Simon Harris | This Modification proposes that the qualifying period for the requirement for a meter point to become Class 1 is reduced, to limit the time period when very large sites are subject to NDM Demand Estimation, as opposed to being Daily Metered. The Modification also proposes a new Performance Assurance report of sites which have met the qualifying criteria for Class 1 but are either Class 3 or Class 4. With WG for development to return to August Panel. ROM response indicated that there are no system impacts identified as the data items required for the PAC report are already available. A DSC CP will be required to deliver the report.
Mod 0691 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | TBC | Impact assessment required as system changes are expected as well as new reports | Jun-20 | Retail & Network, Data | Simon Harris | This Modification proposes that where the requirement for a Class 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a [1 month] grace period, that the CDSP would take steps to convert the meter point to Class 1. The Modification also proposes a new Performance Assurance report of sites where the CDSP has taken action, over the previous 12 months. With WG for development to return to August Panel. ROM response has been provided which details two solution options (automated and manual). The automated solution would definitely require a Major Release. It is currently unknown as to whether the manual solution could be a candidate for a Minor Release. This would need to be assessed once the CP is raised.
Mod 0692 | With Workgroup | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | TBC | Rule and System Change | No | TBC | Impact assessment required as system changes are expected | TBC | Retail & Network | Dave Addison /Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. With WG for development and business rules to be finalised. XRN4941 has been raised to deliver the system impacts of the modification. It has been provisionally approved for June 2020 scope but this is dependent on the outcome of the modification. Changes to the CP may be required as the business rules are finalised. .
Mod 0693R | Assigned to Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any Modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | Simon Harris | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). June Panel assigned the modification to WG. First meeting is 20 August. Any potential solutions from the review will need to be assessed for system impacts.
Mod 0694 | With Workgroup | UNC - DWG | WWU | CDSP provision of Class 1 Read service | Any Modifications as a result of 0694R will be impact assessed and system implications considered. | [5 empty] | Retail & Network | Dave Addison /Ellie Rogers | Modification Proposal 0647 proposed that Shippers should become responsible for the provision of Class 1 Reads. Work on that solution has suggested that a better solution may be some form of central provision by the CDSP. This Request is to enable exploration of this option and to develop a proposal that can be raised as a Modification Currently the system impacts look minimal as the service will remain, just the commercial management of it will change.
Mod 0695 | With Workgroup | UNC - DWG | NGN | Obligations on Shippers to pass Transporter compensation payments on to consumers, via Suppliers | Oct-19 | System Change | NA | System Impacts | Addition of a new charge type within an existing invoice | TBC | TBC | Dave Addison /Ellie Rogers | Introduce new obligations onto Shipper Users to ensure that Transporter compensation aimed at consumers is passed to registered suppliers for onward transmission to consumers. Discussed at June DWG and due to return in July for legal text review. Currently impacts appear to be adding a new charge code to an existing invoice. Change Proposal with the DSC will need to be raised to deliver this. Potential to be delivered outside of a Major Release. WG report complete and due to go back to August Panel.
Mod 0696 | With Workgroup | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | System Impacts not expected but offline process required | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required | TBC | Retail & Network | Dave Addison /Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. WG report has been completed. System changes are not expected but a process to correct the capacity charges is necessary.
Mod 0697 | Awaiting Workgroup Assignment | UNC - DWG | Gazprom Energy | Further Realising the Benefit of the Data Permissions Matrix and UNC Consistency Review | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document and process change only | TBC | N/A | Dave Addison /Ellie Rogers | This modification seeks to further realise the benefit of the Data Permissions Matrix reflecting the direction to greater data openness and to rationalise UNC TPD Section V5 and remove inconsistency with the Data Permissions Matrix. At July Panel it was agreed that the modification would be split for just the V5 clean up and the second part to add the 'Research Body' as a new User type. No system impacts of this change but a second modification will be raised.
Mod 0698 | Out for Consultation | UNC - Transmission | National Grid | Improvements to Margins Notice Arrangements | Oct-19 | Rule Change | N/A | No system impacts | No central system impacts | N/A | N/A | Steve Pownall | To make a number of improvements to the arrangements for National Grid NTS provision of Margins Notices (UNC TPD V5.9.3) and introduce a new ‘early warning’ notice as per the recommendations of Request 0669R. Out for consultation until 08 August. No system impacts.
Mod 0699 | With Workgroup | UNC - DWG | Scottish Power | Incentivise Key Areas of Performance using additional UIG Charges | TBC | Reporting and Rule Change | N/A | UK Link impacts | New reports required to assess Shipper performance and potential changes to incentivise performance | N/A | N/A | Dave Addison/ Ellie Rogers | To create a Shipper incentive mechanism, which encourages the achievement of key UNC targets and obligations. A proportion of Unidentified Gas (UIG) charges will be levied each month to Shippers, where performance has not met a set of pre-determined UNC targets. Following the first WG, the modification needs to developed further to understand how it would work. Impacts expected but dependent on the development of the modification.
Mod 0700 (Urgent) | Out for Consultation / With Ofgem | UNC | Gazprom Energy | Enabling large scale utilisation of Class 3 | TBC | Rule and System Change | N/A | UK Link impacts | Changes to UK Link to better manage a high volume of Meter Readings | N/A | N/A | Dave Addison | Following publication of the 2019/20 Unidentified Gas (UIG) Weighting Factors, Shippers’ communications and actions indicate they intend to migrate significant numbers of Supply Meter Points to Class 3. This Modification seeks to ensure that the CDSP has capability to manage the significant increase in Class 3 Supply Meter Point read submissions. The changes in the Modification seek to minimise the impact on the above Shippers by focusing mitigating actions on End User Category (EUC) Band 1 which covers the majority (circa 99%) of Supply Meter Points.