## Slide 1: Amendment Invoice Contract Management Committee Update
14th August 2019

## Slide 2: Summary Resolution Plan
Apr
May
Jun
Jul
Aug
Sept
Mobilise
Oct
Nov onwards
ASP / AML Mismatches
Exceptions
(LSPs)
Exceptions
(SSPs)
Exclusions
Defects
MI / Reporting
Backlog Clearance
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
RCA activities
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
Backlog Clearance
Operating within SLA
Deploy MI solution
Operating within SLA
Today

## Slide 3: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status (ASP only)
Amber
RAG Justification
65 MPRNs out of the 180,617 LSPs that were billed incurred an ASP mismatch, the lowest amount since Nexus go-live, as a result of defect fixes and greater control around exception resolutions. 94.11% of ASP and 90% of AML mismatch correction files issued to customers within SLA of PDD -3 days. Amber until provision of correction files falls in-line with SLA.
90% AML offline correction files issued to customers ahead of payment due date
94% ASP offline correction files issued to customers ahead of payment due date
Mismatch instances are at the lowest since Nexus go-live, however failure to issue all correction files to all customers ahead of Payment Due Date minus 3 business days is causing SLA failure.
Provision of a single ASP file, followed by a single AML file remains a delivery target for January 2020.

## Slide 4: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Amber
RAG Justification
Exception backlog clearance continues to trend downwards. Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Provision of the exception/exclusion MI from 28th Aug’19 will highlight all such exceptions. Amber status because of risks to being able to clear known exceptions within cycle starting from this months July billing cycle (as per SLA).
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
166,903 distinct MPRNs currently have unresolved exceptions within our systems
(269,920 in May’19)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) in development. Currently at risk of being available for next billing cycle.

## Slide 5: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
Amber
RAG Justification
c.15,000 distinct sites released from bill blocks over the last three months. Cataloguing of the majority of exclusion scenarios complete and signed-off by Xoserve business teams. RAG status to remain at Amber until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA.
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
5,043 distinct MPRNs currently have bill blocks placed upon them
(20,466 in May’19)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) in development. Currently at risk of being available for next billing cycle.

## Slide 6: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Defect backlog halved since 1st June with 16 fixes successfully deployed. 17 AML/ASP defects currently open of which 7 were raised in July. All current known defects, identified pre and post revised commercial agreement, on track to be resolved in-line with SLA.
17
Defects currently open and awaiting fix deployment
Defect ID | Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
1331 | DM prime REC charges are not getting calculated & presented within ASP supporting information file | 27/03/2019 | 12/07/2019 | 31/8/2019
1333 | DM REC financial mismatches (Dec-2018 RCA) | 27/03/2019 | 26/07/2019 | 31/8/2019
1334 | RECs processed within D+5 close out are identified to have an inconsistency in terms of mapping the GUID and the REC start/end dates (Dec-2018 RCA) | 27/03/2019 | 30/08/2019 | 31/8/2019
1369 | SAPBW - Class 4 reads showing on 'fallout report' where the read has been made inactive which do not generate a rec - CR315 | 29/04/2019 | 09/08/2019 | 31/8/2019
1377 | AML Credit Issue - Incorrect negative Volume and energy is calculated | 15/05/2019 | 29/08/2019 | 31/8/2019
1395 | Meter Reading is inactive in the production system | 07/06/2019 | 29/08/2019 | 31/8/2019
1396 | AML file missing volume | 10/06/2019 | 23/08/2019 | 06/09/2019
1399 | For Shorthaul sites - incorrect UDQI loaded | 11/06/2019 | 23/08/2019 | 06/09/2019
1405 | AML/ASP issue - SFN on D date and UMR read on (D-1) | 18/06/2019 | 23/08/2019 | 06/09/2019
1412 | June Release - Re: Defect 54993 - Class 3 Rec has populated in correct volumes and energies | 04/07/2019 | 06/09/2019 | 06/09/2019
1414 | SAP - Read profile is incorrectly populated when there is a class change from 1 to 2 or 2 to 1 | 12/07/2019 | 20/09/2019 | 04/10/2019
1415 | SAP - Actual Reads uploaded through the manual Read entry screen has resulted in zero consumption | 15/07/2019 | 04/10/2019 | 04/10/2019
1426 | SAP - The Net value on the billing document for both previous and current have inconstancy with the decimal point values | 23/07/2019 | 04/10/2019 | 04/10/2019
1428 | MR15 exception not genereting for negavite variance volume | 24/07/2019 | 04/10/2019 | 04/10/2019
1429 | RGMA activity has performed both class 3 normal rec and C2C reconciliation. This should have ideally triggered only C2C rec since DRE or AMR at the site. | 24/07/2019 | 04/10/2019 | 04/10/2019
1431 | SAP - ASP Mismatch on Pre go-live variance | 30/07/2019 | 04/10/2019 | 04/10/2019
1436 | SAP-AML Incorrect Formula Period Year SMP AQ | 05/08/2019 | 04/10/2019 | 04/10/2019

## Slide 7: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Amber
RAG Justification
Testing of exception and exclusion reports complete, awaiting transport of reports to production. All reports, including provision of customer monthly summaries, are being targeted to be available from 28th August. Amber status because of the Monthly Customer Reconciliation Counts report remaining outstanding (in development and test at the time of publication).
Open/Unresolved Exception MI tested and signed-off in readiness for July billing cycle
Open/Unresolved Exclusion MI tested and signed-off in readiness for July billing cycle
ASP and AML monthly mismatch summary counts tested and signed-off in readiness for July billing cycle
Open/Unresolved Defects MI operational
Monthly Customer Reconciliation Count MI remains in development and test. At risk of being available for use in August (July billing cycle).

## Slide 8: Summary Resolution One Pager
Mismatches | Exceptions | Exclusions | Defects | MI / Reporting
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age. | Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old. | Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection. | Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised. | All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA |  |  |  | 
September 2019 | August 2019 | July 2019 | August 2019 | August 2019
Current SLA RAG Status |  |  |  | 
Amber | Amber | Amber | Green | Amber
RAG Justification |  |  |  | 
65 MPRNs out of the 180,617 LSPs that were billed incurred an ASP mismatch, the lowest amount since Nexus go-live, as a result of defect fixes and greater control around exception resolutions. 94.11% of ASP and 90% of AML mismatch correction files issued to customers within SLA of PDD -3 days. Amber until provision of correction files falls in-line with SLA. | Exception backlog clearance continues to trend downwards. Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Provision of the exception/exclusion MI from 28th Aug’19 will highlight all such exceptions. Amber status because of risks to being able to clear known exceptions within cycle starting from this months July billing cycle (as per SLA). | c.15,000 distinct sites released from bill blocks over the last three months. Cataloguing of the majority of exclusion scenarios complete and signed-off by Xoserve business teams. RAG status to remain at Amber until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA. | Defect backlog halved since 1st June with 16 fixes successfully deployed. 17 AML/ASP defects currently open of which 7 were raised in July. All current known defects, identified pre and post revised commercial agreement, on track to be resolved in-line with SLA. | Testing of exception and exclusion reports complete, awaiting transport of reports to production. All reports, including provision of customer monthly summaries, are being targeted to be available from 28th August. Amber status because of the Monthly Customer Reconciliation Counts report remaining outstanding (in development and test at the time of publication).