## Slide 1: UIG Task Force Progress Report
Change Management Committee 11/09/19

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Task Force next steps

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Executive Summary Update | w/c 12/06/19 | Complete
Attend July Change Management Committee | 07/09/19 | Complete
Attend July Contract Management Committee | 14/08/19 | Complete
Attend August UIG Work Group | 20/08/19 | Complete
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Support Mod development (All) | 01/03/19 | Ongoing
Development of automated UIG reporting | End of June | R
Attend September UIG Work Group | 23/09/19 | G
Attend September Change Management Committee | 11/09/19 | G
Attend September Contract Management Committee | 18/9/19 | G
Commence UIG Task Force close down/extension options | 01/07/19 | Ongoing
Executive Summary Update | w/c 09/09/19 | G
Attend Work Group 674 | 17/09/19 | G

## Slide 4: Plan on Page new
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
 | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  | 
 | 06/05 | 13/05 | 20/05 | 27/05 | 03/06 | 10/06 | 17/06 | 24/06 | 01/07 | 08/07 | 15/07 | 22/07 | 29/07 | 05/08 | 12/08 | 19/08 | 26/08 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09 | 07/10 | 14/10 | 21/10 | 28/10
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Support Mod development
I
08/05 DSC ChMC
I
12/06 DSC ChMC
I
20&21/05 UIG WG
I
24/06 UIG WG
I
15/05 CoMC
I
19/06 CoMC
I
10/07 DSC ChMC
I
07/08 DSC ChMC
I
11/09 DSC ChMC
I
17/07 CoMC
I
14/08 CoMC
I
18/09 CoMC
I
23/07 UIG WG
I
20/08 UIG WG
I
23/09 UIG WG
w/c 01/06/Exec Summary
w/c 01/07 Exec Summary
w/c 05/08 Exec Summary
w/c 09/09 Exec Summary
Review/draft updates to UIG user guide ongoing
w/c 21/10 Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan
I
09/10 DSC ChMC
I
16/10 CoMC

## Slide 5: Recommendations - where we are
4 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692), 2 sponsored British Gas 0690 & 0691
23 Future review
2 review September
4 lines MOD 0681 – EON
52 CLOSED
As at 30/08/19
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored 0693R
11 do nothing
2 BAU
13 completed
26 other options progressed
7 review November
8 review December
14 finding & recommendations = 95 recommendation lines
2 lines Xoserve drafted MODs 3.2.5
1 line MOD 0699 Scottish Power
6 review October

## Slide 6: Overview Of Task Force Funding

## Slide 7: Task Force Next Steps
Use the UNC UIG Work Group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UNC UIG Work Group timescales..
Supporting MOD development to progress all live and draft modifications.
Formally agree scope and start date for complex machine learning activities with Analytics partner & share outputs with the Industry.
Internal assessment and re-alignment of all task force activities against Xoserve new structure. Detailed output to be shared later this month.