## Slide 1: 7.1 XRN4665 – EUC Release
09/10/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Post Implementation Support (PIS) PIS activities (including First Usage monitoring) continue to be successfully monitored as per plan Key activities completed with evidence provided and assured include; Rolling AQ job for September Annual EUC Assignment job CNF/CFR files successfully validated for pre-gas year run. These will be validated again after October 1st NRL/NNL files job run completed AQI Correction file successfully run containing new EUC bands |  |  | 
Risks and Issues | No key Risks or Issues open that impact the continuation of Post Implementation Support activities for the EUC release |  |  | 
Cost | Project delivery costs are tracking to approved internal budgets (Revised BER to include Financial Risk margin approved at ChMC on 10/07/19) |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
PIS & First Usage monitoring activities commenced as per plan
NRL Issued
T67 Issued

## Slide 3: 7.2 XRN4828 - Nov 19 Release - Status Update
09/10/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | UAT execution completed on 27/09 Regression Testing commenced from 30/09 Performance Test preparation in progress Implementation preparation in progress |  |  | 
Risks and Issues | There are currently no major Risks or Issues impacting the delivery of the November 19 release. |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 4: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
System & UAT Completion – 27/09/19
Regression Test Completion - 11/10/19
Performance Test Completion – 25/10/19
Implementation – 09/11/19
PIS Completion – 06/12/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT & PT
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 09/11/19 - TBC
IDR

## Slide 5: 7.3 XRN4996 - June 20 Release - Status Update
9th October 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Following the completion of Detailed Design Phase, the June 20 implementation date will be proposed to ChMC for approval. Design: Design workshops are continuing. Change Packs: Aiming to deliver the change packs to ChMC in November for approval in December. |  |  | 
Risks and Issues | Risk – There is a risk that due to multiple deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | BER for full delivery to be presented to ChMC in November 19 |  |  | 
Resources | Full project mobilisation completed following appointment of TCS as preferred supplier. Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 6: XRN4996 - June 20 Market Trials
Is Market Trials Required for June 20, is there an appetite for you to participate in this type of testing? Options under consideration:
Full MT for applicable changes
Xoserve to share testing summary from UAT/RT phases
No MT
Project team is currently assessing the duration, feasibility within planned timescales and cost of option A.
We are aiming to present further details of options A & B if you wish to consider these options, which will include dates for the testing phase, duration and cost, at November ChMC.

## Slide 7: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion – 19/09/19
Design Completion – 29/11/19
Build & Unit Test Completion – 31/01/20 (provisional)
System & UAT Completion – 24/04/20 (provisional)
Regression Test Completion – 29/05/20 (provisional)
Implementation – 21/06/20 (provisional)
PIS Completion – 25/09/20 (provisional)

## Slide 8: June 20 Release Summary
June 20 Release consists of 11 changes, Implementation is planned for June 2020:
XRN4691 - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692 - CSEPs: IGT and GT File Formats (CIN Files)
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4780 (B)* - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4871 (B) - Changes to Ratchet Regime (MOD0665)
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4830 – Requirement to Inform Shipper of Meter Link Code Change
XRN4941* - Auto updates to meter read frequency (MOD0692)
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
* Pending Solution/MOD approval by ChMC/DSG for remaining 2 CRs.

## Slide 9: 7.4.1 What do you need to know about Project Retrospective Updates?
Project raised in April 2019
Three main parts to the Project
  Proof of Concept (PoC) exercise, followed by a Data Cleansing and Enduring solution
PoC Requirements have been captured and approved
Regular project updates provided at DSG and Change Management Committee (ChMC)
Solution Options have been ratified with customers and Approval is now sought on recommended High Level Solution
We are now in the mobilisation phase
Encouraging Customers to get involved if possible
You can register your interest in the PoC by getting in touch with the Customer Change team or your Customer Advocate
Onboarding to take place with Shipper volunteers
Agree design and delivery mechanism of datasets
Contracting with selected Vendor
Updates will continue to be provided to DSG and ChMC
Proof of Concept (PoC) phase
Capture phase
Compare and Contrast
Analysis
Collaboration, Triaging and Reporting
Working with Shippers to receive datasets, sharing information and findings at a Portfolio and Market level
Receive Datasets
Requirements shared with industry
Project Updates provided at DSG and Change Management Committees
What’s happened so far?
What’s happening Next?
We are here
Enhance communication and engagement of Proof of Concept exercise
Continue to provide regular project updates to DSG and Change Management Committee
Onboarding
Mobilise phase
October 2019
January 2020

## Slide 10: 7.4.2 XRN4914 – MOD 0651Retrospective Data Update Provision
High Level System Solution Options for Retro Proof of Concept

## Slide 11: Change Overview
XRN4914 - MOD 0651Retrospective Data Update Provision
This change comprises 3 elements; a Proof of Concept (PoC), a Data Cleanse and an Enduring Solution. At this stage our preliminary focus is the Proof of Concept as this will enable us to quantify the type and frequency of data quality issues that exist with Customers against a pre-defined set of Meter Assets data items. The objective of the Proof of Concept is to gain insight on the data issues and support the strategy for the Data Cleanse element. The Proof of Concept is a voluntary exercise which is open to any Shippers willing to participate. Requirements have been drafted to support a flexible solution that allows Shippers to participate at different levels, whilst also ensuring quality reporting and analysis can be obtained. Outputs from the Proof of Concept will include comparison reports with participating Shippers, and market level analysis to aid our understanding of the key issues and the appropriate approach to tackle Data Cleansing.
Solution Options for the Proof of Concept
Xoserve’s Azure Cloud Solution with SAS Analytics and SAS reporting
3rd party Azure Cloud Solution with SAP Business Objects
3rd party Azure Cloud Solution
Xoserve’s Azure Cloud Solution with SAS analytics and Azure Cloud Power BI reporting
1
2
3
4

## Slide 12: Option 1
Description
Data Storage : All the necessary files for data comparison will be provided by Xoserve to vendor in the agreed format and via a secure means. Solution will securely store data in an SFTP which will be uploaded to the Azure platform. These will be stored in flat files and be available for analysis Comparison : A basic repository will be designed and implemented to contain the data to be compared and analysed. Solution will use SAS Data Integration Studio (DIS), on one of the Azure Demand Estimation environments solution for comparison exercise Outputs: The reports for the visualisation of results and deep dive in data will be developed on SAS Visual Analytics.
Timeline | Environment | High Level Cost Estimate
3 - 4 Months | Xoserve’s Azure Cloud Solution | £240k - 290k exc VAT
Solution
Reports
Analytical Toolsets
(SAS DIS)
Basic Repository
in Azure Cloud
UK Link Data
Shipper Data
UK Link / BW
Data
(Selective)
Customer
Data Files
Comparative Algorithms
Exception Reporting
1. Source Data
2. Data Storage
3. Comparison
4. Outputs
5. Integration
Azure Data Factory (ADF)
BW
ISU
Files
1

## Slide 13: Option 2
Description
Data Storage: Extraction tool to be used to extract data from SAP BW and reports will be used for data extraction from SAP ISU into a staging area in Azure SQL Cloud server Comparison : Data processing and reconciliation as part of comparison exercise will use Python for building algorithms Outputs: The reports for the visualisation of results and deep dive in data will be developed on SAP Business Objects.
Timeline | Environment | High Level Cost Estimate
4 – 5 Months | 3rd Party Azure Cloud Solution | £330k - 380k exc VAT
Solution
Reports
Analytical Toolsets
(Azure Cloud)
Enterprise Data Storage
(Azure SQL - Cloud)
UK Link Data
Shipper Data
UK Link / BW
Data
(Selective)
Customer
Data Files
Comparative Algorithms
Exception Reporting
1. Source Data
2. Data Storage
3. Comparison
4. Outputs
5. Integration
Azure Data Factory (ADF) / IQNxt (Data Quality)
BW
ISU
Files
2

## Slide 14: Option 3
Description
Data Storage: Solution will store asset data in both a structured format such as a relational database, and in a raw format in the platform server Comparison : Data processing and reconciliation as part of comparison exercise will use analytical tools in Azure Cloud Outputs: Solution suggested to propose and quote for work that will implement an Enterprise-ready reporting platform tailored to the needs of Xoserve after Comparison exercise is finished.
Timeline | Environment | High Level Cost Estimate
6.5 – 7.5 months | 3rd Party Azure Cloud Solution | £640k – 690k exc VAT
Solution
Reports
Analytical Toolsets
(Azure Cloud)
Azure Cloud
UK Link Data
Shipper Data
UK Link / BW
Data
(Selective)
Customer
Data Files
Comparative Algorithms
Exception Reporting
1. Source Data
2. Data Storage
3. Comparison
4. Outputs
5. Integration
Azure Data Factory (ADF)
BW
ISU
Files
3

## Slide 15: Option 4
Description
Data Storage: Data storage hosted on Azure will be used to store both UK Link/BW and Shipper Data files. Data storage will be funded on a Pay as you Go basis. Azure will provide scalability in terms of processing power, storage and environments Comparison : The existing SAS Platform (currently support Demanding Estimation) will have a direct connection to the data storage to retrieve data. Base SAS jobs will be used to compare data sets and generate any exceptions based on agreed rules. These jobs will be re-usable and can be scheduled if the Retro POC matures into an enduring solution Outputs: Exception reporting will be generated in the agreed formats to provide detail where data is misaligned. Data can be made available through Azure (OneDrive) to deliver outputs to customers.
Solution
Timeline | Environment | High Level Cost Estimate
3 – 4 Months | Xoserve’s Azure Cloud Solution | £220k - 270k exc VAT
Reports
(Azure Cloud)
Analytical Toolsets
(Azure Cloud)
Azure SQL - Cloud
UK Link Data
Shipper Data
UK Link / BW
Data
(Selective)
Customer
Data Files
Comparative Algorithms
Exception Reporting
1. Source Data
2. Data Storage
3. Comparison
4. Outputs
5. Integration
Azure Data Factory (ADF) / Azure Data Quality Services
BW
ISU
Files
4

## Slide 16: Assessment criteria with recommended solution
 | Cost | Resource | Data | Timescales | Risk | Security | Enduring
1 | Cost to deliver this change is forecasted to be in the range £240k – £290k Includes forecast for additional cost for procuring SFTP server | Dedicated Data team resources required Minimum IS Ops resource required 3rd party supplier resources required for comparison and deep dive exercises | As part of this exercise data received and analysed will be stored Xoserve’s cloud platform | Delivery timescale of 3 – 4 months Additional re-work required to transition to enduring solution | Medium confidence level for delivery Risk of not establishing a SFTP mechanism with in timelines | Low security risk assessment required – internal platform already assessed Security risk assessment required on SFTP element | Partially aligns with the enduring solution
2 | Cost to deliver this change is forecasted to be in the range £330k - £380k | Dedicated Data team resources required Minimum IS Ops resource required 3rd party supplier resources required for comparison and deep dive exercises | As part of this exercise data received and analysed will be stored 3rd party’s cloud platform | Delivery timescale of 4 – 5 months Security full risk assessment will take 3-4 weeks Additional re-work required to transition to enduring solution | Low confidence level for delivery Risk of key resources occupied with Class 3 (Mod 700) and other Xoserve commitments | Full security risk assessment required on external hosted platform – would take 3 – 4 weeks Security risk assessment required on SFTP element | Does not align with the enduring solution
3 | Cost to deliver this change is forecasted to be in the range £640k - £690k | Dedicated Data team resources required Minimum IS Ops resource required 3rd party supplier resources required for comparison and deep dive exercises | As part of this exercise data received and analysed will be stored 3rd party’s cloud platform | Delivery time scale of 6 weeks only for comparison exercise Additional 4 months to complete activity Security full risk assessment will take 3-4 weeks Additional re-work required to transition to enduring solution | Low confidence level for delivery No reporting solution provided as part of firm quoting for proof of concept. | Full security risk assessment required on external hosted platform – would take 3 – 4 weeks Security risk assessment required on SFTP element | Does not align with the enduring solution
4 | Cost to deliver this change is forecasted to be in the range £220k - £270k | Dedicated Data team resources required Minimum IS Ops resource required 3rd party supplier resources required for comparison and deep dive exercise | As part of this exercise data received and analysed will be stored Xoserve’s cloud platform | Delivery timescale of 3 -4 months Less re-work required to transition to enduring solution | High confidence level for delivery Creation of data storage is a dependency for Retro proof of concept. Low risk re Security review as internal platform already assessed | Low security risk assessment required – internal platform already assessed | Aligns with enduring solution
Recommended Solution

## Slide 17: Timeline / Cost Overview
Option | Timeline | High Level Cost Estimate
1 | 3 – 4 months | £240k – 290k exc VAT
2 | 4 – 5 months | £330k - 380k exc VAT
3 | 6.5 – 7.5 months | £640k - 690k exc VAT
4 | 3 – 4 months | £220k - 270k exc VAT
Xoserve Recommended Solution

## Slide 18: 7.5 XRN4991 – MOD0700 Status Update
30th September | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | BW (Reporting) Changes: Requirements agreed for reporting changes and design to be presented to PAC on 8th October Engaged with Wipro for delivery plan AMT SPC File Restrictions: Market Flow changes went live 28th Sept; SPC File limits set for those Shippers actively migrating to Class 3 – no global limit set SAP ISU Changes: Performance test; completed and changes went live 28th Sept; received Shipper preferred dates set Inner Tolerance Check: Engaged with Wipro for assigning resource for planning and delivery |  |  | 
Risks and Issues | Risk: There is a risk that the number of Inner Tolerance rejections will increase as a result of this implementation – these rejections will be monitored and a solution has been identified, but will need to be implemented based on criticality Risk: There is a risk that additional funding is required to cover the cost of completing delivery for Inner Tolerance Check and Reporting; expectation is that this will be covered in the agreed risk margin |  |  | 
Cost | The BER has been presented and approved by ChMC on the 11th Sept |  |  | 
Resources | Daily stand-up with all areas; resources being understood and prioritized for Inner Tolerance check and Reporting |  |  | 

## Slide 19: XRN4991 - MOD0700 Timelines
2019
Aug | Sept | Oct
SAP - ISU
Key:
Completed
Slipped / High risk
Medium risk
On-target
Market Flow
Reporting
Design
Build & Test (Unit, System, UAT and Regression)
PIS
Performance Test
11/09: BER Approval
GO LIVE 28/09/19
28/08: Change Pack Approval
Design
Build & Test (Unit & System)
PIS
UAT and Regression
Received from AMT20/09
GO LIVE 28/09/19
Key: dashed line - proposed
today
Inner Tolerance
Planning
Reporting

## Slide 20: 7.6 Retail & Network Change Impact / Platform Update 2019 / 2020 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2019 | 2020
Assumes RETRO will be Nov 2020 Major Release Delivery
Please note that this includes potential activity within UK Link over the next 24 months
Sep-19 / EUC
BER Approval
09/01/19
Nov-19
BER Approval
10/04/18
EQR Approval
06/02/19
RETRO
Potential Activity
Governance Approval dates tbc
On track
At risk
Key
Complete
Feb-20
BER Approval / Change Pack Issue
10/04/19
Jun - 20
Change Pack Issue
Dec-19
Scope Approval
10/07/19
MiR 5
ChMC Scope Approval
10/07/19
EQR Approval
Aug-19
Scope Approval
10/07/19
MiR 6
Scope Approval
Oct-19
MOD 700
Imp Plan / BER Approval Sept-19
BER Approval
Nov-19

## Slide 21: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
MiR 5 | 4871 (A) | Modification 0665 - Changes to Ratchet Regime | In PIS | MiR 5 | Low / Medium | Shippers / DNs
Sept 19 | 4376 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | In PIS | September 2019 | High | NTS
 | 4665 | Creation of new End User Categories (EUC) | In PIS | June/Sep-2019 | High | Shippers
Mod 700 | 4991 | Enabling large scale utilisation of Class 3 - Mod 700 | In PIS | September 2019 | High | Xoserve
Nov-19 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | In Delivery | November 2019 | Medium | Xoserve
 | 4725 | New read reason type for LIS estimate readings | In Delivery | November 2019 | Medium | Xoserve
 | 4621 | Suspension of the validation between meter index and unconverted index | In Delivery | November 2019 | High | Shipper
 | 4866 | UIG Recommendation – removal of validation on uncorrected read | In Delivery | November 2019 | Low | Shipper
Feb-20 | 4955 | Amendments of MDD PSR needs code descriptions | In Delivery | February - 2020 | Low | Shippers / GT/IGTs
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June-2020 | Low | Shippers / DNO
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | In Delivery | June-2020 | Medium | DNs / IGTs
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | In Delivery | June-2020 | Medium | DNs / IGTs
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4780 – B | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | In Project Delivery – Awaiting Solution option Approval | June-2020 | Medium | Shippers
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June-2020 | Low | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June-2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June-2020 | Medium | IGTs / DNO
 | 4871 – B | Modification 0665 – Changes to Ratchet Regime | In Delivery | June-2020 | Medium | DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June-2020 | Low | IGTs
 | 4941 | Auto updates to meter read frequency (MOD0692) | In Project Delivery - awaiting MOD approval | June-2020 | Medium | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | 2021 | High | Shippers

## Slide 22: Change Index – UK Link Unallocated External Impacting Changes
XRN | Change Title | Current Status | Indicative R&N Release | Complexity
4851 | Moving Market Participant Ownership from SPAA to UNC/DSC (Documentation) | CP in Capture | Feb-2020 | TBC
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CP in Capture | Major Release | TBC
4801 | Additional information to be made viewable on DES | HLSO in Review | Major Release | TBC
4896 | Failure to Supply Gas System and Template Amendment | CP in Capture | Major Release | TBC
4923 | AQ Calculation for RGMA (ONUPD) Estimate Reads | CP in Capture | Major Release | TBC
4931 | Submission of Space in Mandatory Data on Multiple SPA Files | CP in Capture | Major Release | TBC
4978 | Notification of Rolling AQ value (following transfer of ownership between M5 and M) | CP in Capture | Major Release | TBC
4990 | Transfer of sites with Low Read Submission Performance from Class 2 and 3 into Class 4 (Mod 664) | CP in Capture | Major Release | TBC
4992 | Creation of new change type to recover last resort supply payment (Mod 0687) | CP in Capture | Major Release | TBC
4914 | Mod 651 - Retrospective Data Update Provisions | Solution Approval | Major Release 2020 | TBC
4716 | Increased Field Length – ‘Updated by’ data item | HLSO in Review | Minor Release | Medium
4854 | Transfer of NDM sampling obligations from Distribution Network Operators to the CDSP | In Capture | Unallocated | TBC
tbc
Feb 2020
Major Release
Retro 2020
Minor Release
Unallocated
KEY

## Slide 23: 7.7 UK Link POAP
Please see attached POAP of the Portfolio roadmap.

## Slide 24: 7.8. Change Assurance Health Check
Any queries raised at the meeting will be taken away and answered in Novembers meeting. If you wish to raise a question beforehand, please email uklink@Xoserve.com

## Slide 25
7.9.1 Customer Impacting Data Changes: XRNs
Change Proposals | Aug 19 | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 19 | Comments
4738: Shipper portfolio update of proposed Formula Year AQ/SOQ |  |  |  |  |  |  | 
4859: Increasing MAM Access to CDSP Data to Mitigate Reduced MAM Appointment Timescales |  |  |  |  |  |  | 
4824: National Grid Transmission Daily Gemini Report |  |  |  |  |  |  | Awaiting Customer Sign off
4860: National ‘Temporary’ UIG Monitoring |  |  |  |  |  |  | 
4946: Reporting on Installed Meters with Conversion Capability |  |  |  |  |  |  | 
4795: Amendments to the PARR (520a) reporting |  |  |  |  |  |  | 
4779: UNC Modification 0657S - Adding AQ reporting to the PARR |  |  |  |  |  |  | 
Capture
**Estimated Delivery
Change can be moved
Delivery dates cannot be moved
Delivery
**Estimated delivery dates will be confirmed on completion of Capture and align to the chosen solution.

## Slide 26
Data Changes: XRNs
Change Proposals | Aug 19 | Sept 19 | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Comments
4789: Updating Shipper Reporting Packs and glossary |  |  |  |  |  |  | Will remain in delivery until all requirements fulfilled through DDP drops
4980: Change Supply Point Enquiry API to add in extra field and make certain other fields visible. |  |  |  |  |  |  | BER Approval requested in October ChMC
4713: Actual read following estimated transfer read calculating AQ of |  |  |  |  |  |  | 

## Slide 27: 7.9.2 Shipper - Data Discovery Platform Drop 2 Update 7.9.3 Networks - Data Discovery Platform Drop 1 Update
Both of these agenda items will be verbal updates.

## Slide 28: 7.9.4 Automation and Optimisation
Change Management Committee – 10/10/19

## Slide 29: Purpose and Contents
Purpose
Provide a detailed view of options/next steps following completion of the Report Review
Seek approval from CHMC for recommended option
Contents
High Level Options – Decision Required
KPMG Recommendation Summary
Recommended Options
Additional Options

## Slide 30: High Level Options – Decision Required
Below is a high level breakdown of the options for consideration by the Change Management Committee. The options are split by recommended, additional and not technically feasible. Further detail is provided on the following slides.
 | Option | Description | Timeline | Cost | Comments
Recommendation |  |  |  |  | 
Must Do | Continue DDP Delivery | Add KPMG recommendations which carry potential efficiency savings to the DDP product backlog and deliver DDP product backlog topics based on current priority | 2020/21 | Funded as part of BP20/21 | Recommendations added to backlog DDP in progress
Must Do | Consolidation of Reporting | Two internal changes will be raised to deliver the ‘Consolidation’ recommendations from KPMG | Completed | BAU Activity | XRNs will follow the normal process
1 | Analysis | Carry out detailed analysis with customers on reports identified, to reduce the number of reports delivered to Shippers via email. | 4 months | 96k | 8 week mobilisation period
Additional Available Option |  |  |  |  | 
2 | Expedite DDP Drops | Expedite DDP Drops but adding additional resources. | 4 months | 152k | 8 week mobilisation period
Not Technically Feasible |  |  |  |  | 
Unfeasible | KPMG Recommendations | KPMG recommendations delivered as a separate delivery from DDP is not technically feasible. Baseline data model needs to be completed before we produce any bespoke reporting | N/A | N/A | 

## Slide 31: KPMG Recommendation Summary
The table to the right summarises the recommendations from KPMG which carry potential efficiency savings; meaning if implemented, would mitigate the requirement for some manual reports delivered via email to customers.
The ‘automation’ themed recommendations detailed in the table, will be aligned to the Data Discovery Platform (DDP) product backlog. Therefore they will all feed into the DDP delivery process, releases are currently being planned for 2020/21, subject to priority.
The ‘consolidation’ themed recommendations will be raised as XRNs for delivery.
A detailed view of the recommendations can be found in appendix 1.
Recommendation | Theme | Potential Report Reduction
GSR Automation | Automation | 5
Consolidation of five 'Shipperless and Unregistered' reports | Consolidation | 4
SHQ Automation | Automation | 10
Allocations Automation | Automation | 9
Demand Automation (including weather data) | Automation | 2
Credit and Risk Automation | Automation | 2
Asset portfolio Automation | Automation | 48
Shipper pack Automation | Automation | 22
AQ/SOQ Automation | Automation | 20
Invoicing Automation | Automation | 20
Consolidate 'must read' reporting | Consolidation | 10
UIG Automation | Automation | 11
PACC and PARR Automation | Automation | 12

## Slide 32: Must Do - Continue DDP Delivery and Consolidation of Reporting
Description: | Recommendations provided by KPMG have been built in to the DDP product backlog. This option is to continue progressing with the DDP drops which are being released to Shippers this year, and will continue to be released next year. Also two internal changes have been raised to deliver the ‘Consolidation’ recommendations from KPMG.
Benefits: | There will be no additional investment required to deliver this option KPMG recommendations will be aligned with the DDP drops, ensuring consistency across the delivery Shippers will experience all benefits of DDP utilisation
Outputs: | More data being exposed via DDP KPMG recommendations have been included in the DDP delivery process
Total Cost: | Funding in place as part of BP20/21
Timescale: | Funding is in place until April 2021
Risks: | Risk that funding for DDP in BP20/21 will not cover all product backlog items Risk that priority of industry deliverables will change
Dependencies: | Delivery of backlog items is dependant on priority

## Slide 33: Option 1 - Analysis
Description: | The team will perform detailed analysis on reporting provisioned to customers, and identify reports which could be candidates for decommissioning based on the same data being provisioned via DDP or API. They will also work with customers to understand why the reports are required, and what they’re being used for.
Benefits: | Working with customers identifies which reports contain data which could be obtained via DDP/API, enabling us to start having conversations with Shippers on decommissioning reports/training Helps identify where we could add value to our existing reporting services Helps ensure future developments are aligned to the report purpose Customer insight for Xoserve on to the purposes of the reporting and how we potentially improve the experience for our customers Potential identified opportunities to remove manual effort at the customer end Identifies a clear roadmap of opportunities in improving and removing duplication
Outputs: | Complete list of reports which are candidates for decommissioning or potential improvements Customer Improvement and Decommissioning Roadmaps Documented view on why/how Shippers use their reports, building on the report review output
Total Cost: | £96k
Timescale: | 4 month delivery, following an 8 week mobilisation period planned to start post new year
Risks: | Risk that no decommissioning opportunities will be identified Recruitment is around 8 weeks, delay will effect timelines. To mitigate this risk, we’re intending to begin mobilisation post new year Risk that Shippers will be unable to support due to industry priorities changing, which will put the analysis timelines at risk
Dependencies: | Dependency on Shippers to provide the relevant information on their reports, i.e. why the reports are needed, and how are they used
 | Resource | Day rate | Duration | Total Cost
1 | Platform Delivery Specialist | N/A | 4 months | BAU
2 | Business Analyst | £600 | 4 months | £48k
3 | Data Analyst | £600 | 4 months | £48k
4 | Total Cost for Analysis Team |  |  | £96k

## Slide 34: Option 2 - Expedited DDP Drops
Description: | Energy (AQ/SOQ/SHQ) data will be exposed to Shippers faster. Currently, energy data is planned for drops post April 2020. If this option is approved, Shippers will have access to energy data via DDP faster.
Benefits: | Expedited delivery will result in data being exposed to Shippers via DDP faster Reduces requirement for manual email reporting Potential reduction in future XRNs
Outputs: | Additional development resource will result in more product backlog items being delivered via DDP. The following data topics will be exposed to Shippers faster; Energy data i.e. AQ, SHQ, SOQ
Total Cost: | £152k
Timeline: | 4 month delivery, following an 8 week mobilisation period planned to start post new year
Risks: | No focus on decommissioning (natural decommissioning) - Risk that we are unclear on how Shippers are using their reports and therefore we may not know the best solution to deliver them, option 1 (analysis) will mitigate this risk Shippers may use reports for different purposes Priority of product backlog items are subject to change based on industry requirements Recruitment is around 8 weeks, delay will effect timelines
Dependencies: | N/A
 | Resource | Estimated Contractor Day Rate | Duration | Total Cost
1 | Platform Delivery Specialist | N/A | 4 months | Funded by BAU
2 | Business Analyst | N/A | 4 months | Funded by BAU
3 | Developer | £650 | 4 months | £52k
4 | Data Modeller | £650 | 4 months | £52k
5 | Test Specialist | £600 | 4 months | £48k
 | Total Cost for Development Team |  |  | £152k