## Slide 1: KPI and KVI Review Progress Report
18th December 2019

## Slide 2: KPI Progress Review
Reviewed 100% of DSC Service Lines
A number of service lines will require updates
  Cosmetic change
  Measurement
  Service area
Identified potential processes where we could measure completeness & quality as well as timescales
Reviewing performance measures for each service line (are they appropriate)

## Slide 3: DSC Service Line & KPI Review Plan
Activity | Owner | Start Date | End Date | Status
Review all DSC service lines against UNC & other relevant non UNC docs. | Xoserve | 01/10/2019 | 29/11/2019 | Complete
Review all KPIs and any DSC services line that should be considered as a KPI | Xoserve | 15/10/2019 | 15/01/2020 | Delayed
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | Complete
Review performance measures for all service lines and supporting MI requirements | Xoserve | 21/10/2109 | 31/01/2020 | Delayed
Update Service Description Table (track changes) | Xoserve | 04/11/2019 | 31/01/2020 | On target
Develop performance measures & reporting | Xoserve | 04/11/2019 | 15/02/2020 | Delayed
Provide progress update to November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | Complete
Provide progress update to December CoMC | Xoserve | 18/12/2019 | 18/12/2019 | On target
First review of the draft DSC service lines & KPIs at January CoMC | CoMC | 15/01/2020 | 15/01/2020 | On target
Provide any comments to Xoserve of the draft service lines & KPIs | CMs | 15/01/2020 | 07/02/2020 | On target
Exec review of proposed KPIs & measures | Xoserve | 11/02/2020 | 11/02/2020 | On target
Second review of the updated DSC service lines & KPIs at February CoMC | CoMC | 19/02/2020 | 19/02/2020 | On target
Final review & approval of DSC Service Line and KPIs to March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
New service lines and KPIs effective & published | Xoserve | 01/04/2020 | 01/04/2020 | On target

## Slide 4: KVI Review Plan
Activity | Owner | Start Date | End Date | Status
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | Complete
Review KVIs and measures | Xoserve | 17/10/2109 | 31/01/2020 | Delayed
Carry out sessions to discuss KVIs with customers (via constituent groups) | Xoserve | 17/10/2019 | 28/02/2020 | On target
Develop strawman KVIs and measures | Xoserve | 04/11/2019 | 15/01/2020 | On target
Provide progress update & share view of proposed KVIs November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | Complete
Review strawman KVIs at December CoMC | CoMC | 18/12/2019 | 18/12/2019 | On target
Provide feedback on strawman KVIs | CMs | 19/12/2019 | 03/01/2020 | On target
First formal review of the draft KVIs and measures at January CoMC | CoMC | 15/01/2020 | 15/01/2020 | On target
Provide any comments to Xoserve on the draft KVIs | CMs | 16/01/2020 | 07/02/2020 | On target
Second review of the KVIs and measures at February CoMC | CoMC | 19/02/2020 | 19/02/2020 | On target
Provide any comments to Xoserve on the draft KVIs | CMs | 20/02/2020 | 06/03/2020 | On target
Final review & approval of KVIs at March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
New KVIs effective & published | Xoserve | 01/04/2020 | 01/04/2020 | On target

## Slide 5: KVI Topics
Following discussions with all customer groups, the following have been suggested as key customer focus areas;
  System availability / performance
  Defect Resolution
    Customer Issues – consistent approach to resolution
  Reporting – timeliness/quality
    Data quality around portfolio reports customers depend on for their business
  Incident Resolution/Service Desk
  Compliance
  Effective communication
  Continuous improvement
  Innovation
  Data Security
  Financial Reports

## Slide 6: Next Steps
A workshop will be arranged for January 2020 to draft the proposed KVIs for CoMC review at January meeting
Further review at February CoMC with aim to approve at March meeting.