## Slide 1: DSC Service Line & KPI Review Progress Report
15th January 2020

## Slide 2: KPI Progress Review
Reviewed all DSC Service Lines
A number of service lines will require updates
  Cosmetic change
  Measurement is unclear
  Service area is incorrect
  Potential new service lines
Identified potential processes where we could measure completeness & quality as well as timescales
Reviewing performance measures for each service line (are they appropriate)

## Slide 3: DSC Service Line Review
Activity | Owner | Start Date | End Date | Status
Review all DSC service lines against UNC & other relevant non UNC docs. | Xoserve | 01/10/2019 | 29/11/2019 | Complete
Review any DSC services line that should be considered as a KPI | Xoserve | 15/10/2019 | 13/12/2019 | Complete
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | Complete
Review performance measures for all service lines and supporting MI requirements | Xoserve | 21/10/2109 | 10/01/2020 | In progress
Update Service Description Table (track changes) | Xoserve | 04/11/2019 | 10/01/2020 | Present at Feb CoMC
Provide progress update to November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | Complete
Provide progress update to December CoMC | Xoserve | 18/12/2019 | 18/12/2019 | Complete
First review of the draft DSC service lines at January CoMC | CoMC | 15/01/2020 | 15/01/2020 | Delayed until Feb CoMC
First review of the updated DSC service lines at February CoMC | CoMC | 19/02/2020 | 19/02/2020 | On target
Provide any comments to Xoserve of the draft service lines | CMs | 20/02/2020 | 06/03/2020 | On target
Final review & approval of DSC Service Line to March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
New service lines effective & published | Xoserve | 01/04/2020 | 01/04/2020 | On target

## Slide 4: KPI Review Plan
Activity | Owner | Start Date | End Date | Status
Review all KPIs and any DSC services line that should be considered as a KPI | Xoserve | 15/10/2019 | 13/12/2019 | Complete
Present approach & plan to CoMC | Xoserve | 16/10/2019 | 16/10/2019 | Complete
Develop performance measures & reporting | Xoserve | 04/11/2019 | 15/05/2020 | In progress
Provide progress update to November CoMC | Xoserve | 20/11/2019 | 20/11/2019 | Complete
Provide progress update to December CoMC | Xoserve | 18/12/2019 | 18/12/2019 | Complete
First review of the draft KPIs at March CoMC | CoMC | 18/03/2020 | 18/03/2020 | On target
Provide any comments to Xoserve of the draft KPIs | CMs | 19/03/2020 | 02/04/2020 | On target
Second review of the updated KPIs at April CoMC | CoMC | 15/04/2020 | 15/04/2020 | On target
Final review & approval KPIs to May CoMC | CoMC | 20/05/2020 | 20/05/2020 | On target
New and KPIs effective & published | Xoserve | 01/06/2020 | 01/06/2020 | On target