## Project Plan 2019-20
|  |  |  | 2019 |  |  | 2020 | [11 empty] | 2021
Quarters are categorised using the calendar year i.e. Q1 is Jan-Mar | Status | Date | Date Complete | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January
Steering and Control
PAC member elections |  | Q3 2020
End of PAF year review |  | 2020-07-01
Industry consultation: PAFA/PAC Annual review |  | Q3 2020
industry engagement day/PAC review of the year
Performance Reports
Review Performance Reports and whether they are still fit for purpose, investigating what additional reporting elements are required |  | ongoing
Present changes to the PARR reports to the PAC for agreement |  | 2020-02-01
PARR report amendments presented to UNCC |  | 2020-03-01
Annual Huddle data cleanse and user review |  | 2021-01-01
Risk Register
Current version register agreed December 2019 |  | Q4 | 2019-12-01
Industry review |  | 2020-01-01
Quarterly Risk updates |  | quarterly
Risk Topic investigation |  | quarterly
Risk Model
Risk Model data update completed |  |  | 2019-09-01
Risk model redevelopment kick off (PAC approval on approach) |  | Q2-Q4
Finalisation of the risk model by PAC |  | 2021-01-01
Industry consultation on updated Risk Model |  | 2021-01-01
PAC Development
Further define and develop incentive regime |  | Q2 and Q3 2020
Continue with current performance targetting |  | ongoing
Begin implementation of defined incentives regime |  | Q4 2020
PAC/PAFA Development
Revised PAC election process to UNCC
Provision of Shipper specific bench marker to shippers on request