## Slide 1: Xoserve IX Refresh
Customer Update
18/03/2020

## Slide 2: IX Refresh Customer Update
Although the baselined project plan is targeting a 31st August completion we have structured our milestones to aim for a completion date of 8th July. This allows us to introduce tolerance within the plan and mitigate the risk of moving into September and needing to extend Xoserve’s support arrangement with the legacy network provider.
Our roadmap is therefore tracked against an 8th July completion. Progress:
Milestone 1 – Network Lines
The first two targets (40% and 60%) completion have been met and we are on track to meet our next target of 80%.
Milestone 2 – Routers
The installation of routers is ahead of schedule. Our next target is to reach 40% of router installations by 7th April. This target is forecasted to
be met by 13th March.
Milestone 3 – Servers
The rollout of the servers was delayed by two weeks due to a dependency on a commercial agreement being in place between of new
network provider and their third party server supplier. The commercial agreement has now been finalised. This resulted in the first target
(20%) being missed and the next target (40%) being at risk.
The server supplier have now on-boarded additional staff to support the rollout with an aim to meet the original 5th May completion date.
Milestone 4 – Migration
The migrations have been impacted by the delay in the server installations. To meet an early July completion date, we need to be migrating
8 sites per week starting w/c 9th March. We are currently tracking at 4 migrations a week.
Once the server installations increase, the project have the resources to increase the number of migrations per week and to bring our
original targets back on track.
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com