## Slide 1: Change Assurance XEC Report Health Check - 2
UK Link Release – June 20
February 2020

## Slide 2
Topic | RAYG | Summary
Business Case |  | This is the second Change Assurance activity conducted on the June 20 Release. Currently the project has completed Design and looking to commence UAT on 9th of March. Although there were delays in the Design and Build phase due to both resource and environment constraints this has not had any financial impact for the project. These delays have not impacted the implementation milestone as they have managed to run the phases in parallel due to breaking up the Release into 3 drops. All 36 findings reported in the last assurance that were actionable by the project team were closed. The open findings from the previous report are on the Scope and Capture process and are being addressed more widely than by the project team. A number of the findings raised from this Health Check, relate to areas of concern from the first assurance, indicating that the findings reported previously have been resolved symptomatically, but underlying concerns have not been fully addressed. Themes such as incomplete planning, inadequate project control, incomplete RAID management, and lack of effective service transition planning remain a concern as they are being managed reactively rather than proactively. Although the Test Approach document was approved, it was identified that key sections were missing such as the pre-requisites for testing, penetration testing, out of scope section, and a defect management process, giving a concern on completeness and on the approval process. The project team faced several challenges, the majority have been with respect to XRN4850. This change has been problematic from the start, especially having to procure a new service for Xoserve mid-way through the release which has made it more complex. The Project team have continued with their delivery, without too much impact on the L1 milestones by managing these unexpected challenges. Costs for this change have been significantly modified from HLSO due to the clarity being achieved on the various uncertainties. There are substantial (medium to high) security risks associated with this change that is yet to reviewed and mitigations accepted by the Supplier delivering the new service.
Sponsorship |  | 
Governance |  | 
Scope & Solution |  | 
Team & Skills |  | 
Plan |  | 
Customer |  | 
Other - Information Security |  | 
Other – Service Transition |  | 
Other - Testing |  | 
Other – Environments |  | 
Project | Date | Change Assurance Type | Overall RAYG
UK Link Release – June 20 | 02/03/2019 | General Health Check | 
CA1 | 0 | CA2 | Open 4 | Closed 1 | CA3 | Open 7 | Closed 2 | CA4 | Open 1 | Closed

## Slide 3: Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme

## Slide 4: Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects