## Slide 1: Change Management Committee
13th May 2020

## Slide 2: 2. New Change Proposals – Initial Review

## Slide 3: 2. New Change Proposals – Initial Review
Agenda Item | XRN / Title | Voting |  |  |  | Funding | DSC Service Area
 |  | Shipper Y/N | DNO Y/N | IGT Y/N | NTS Y/N |  | 
2.1 | XRN5164 CSEP Data Assurance – Performance Monitoring Capability |  | Y | Y |  | Funding breakdown to be determined between IGT and GT Customer Classes | DSC Service Area 10: Connected System Exit Points ASGT-CS SA10-01
2.2 | XRN5167 Report Product Class 4 Read Performance (MOD 672) | X |  |  |  | 100% Shipper | DSC Service Area 11: Performance Assurance - provision of information to the Performance Assurance Framework Administrator DS-CS SA3
2.3 | XRN5168 – MOD0721 – Shipper submitted AQ Corrections during COVID-19 | Y | Y | Y |  | 100% Shipper | Service Area 6: Annual quantity, DM supply point capacity and offtake rate reviews
2.4 | XRN5169 – MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19 | Y |  |  |  | 33% Shipper 67% DNO | Service Area 5: Metered volume and quantity
2.5 | XRN5170 – MOD0723 – User of the Isolation Flag to identify site with abnormal load reduction during COVID-19 period | Y | Y | Y |  | 100% Shipper | Service Area 1: Manage supply point registration
2.6 | XRN5171 – MOD0724 – Amendment to Ratchet charges during COVID-19 period |  |  |  |  | 33% Shipper 67% DNO | Service Area 5: Metered volume and quantity
2.7 | XRN5172 MOD0725 – Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19 | Y | Y | Y |  | TBC | TBC

## Slide 4: 2.1.1 XRN5164 CSEP Data Assurance – Performance Monitoring Capability
Customer Class | Voting Party? | Funding Split (%)
Shipper |  | 
Distribution Network Operators (DNOs) | Y | TBC
National Grid Transmission |  | 
IGT’s | Y | TBC
Impacted Parties:- DNO and IGT Funding breakdown to be determined between IGT and GT Customer Classes. |  | 
Voting Parties and Funding Split
DSC Service Area: | DSC Service Area 10; Connected System Exit Points ASGT-CS SA10-01
Service Line Impacts (new, amended, existing, deleted), etc. | Existing
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Problem Statement 1 GTs and IGTs are currently notified of breaches in CSEP MAX AQ through a UK Link file format – (.CGI) – the .CGI file was designed prior to Project Nexus implementation, with a set of pre-agreed triggers being used to generate it based on the CSEP details reaching 85% of the CSEP MAX AQ. The .CGI file did not take into consideration related CSEP data that is needed to help IGTs and GTs to better understand, review and monitor the characteristics of each CSEP Problem Statement 2 The CSEP Inconsistency Notification file (.CIN) was developed to alert IGTs and GTs to differences in the CSEP data that have been provided by the respective parties as part of the CSEP Creation and CSEP Amendment processes. Problem Statement 3 It is currently difficult to obtain clear visibility of the validity and behaviour of CSEP AQ and SHQ data due to the information being provided through multiple files – in addition, there is no alert or warning where AQ data being provided by the IGT is inconsistent across a CSEP. Problem Statement 4 There is a need to be able to easily identify and alert parties where default or invalid values have been populated in CSEP data items. Examples such as GT Reference Number being provided as ‘Default’ or ‘TBC’.
Sponsor Representative | Wales & West
Change Description
Data visualisation, monitoring trends and capability to track and report upon differences between sources of data provided by both GT and IGT customers.

## Slide 5: 2.1.2 Action 0208 - Xoserve (PO) will create consolidated change proposal concentrating on problem statements for DDP issues.
Approval needed from DNO & IGT’s
We would like approval for the following Change Proposals to be withdrawn.
XRN4691 CSEPs: IGT and GT File Formats (CGI Files)
XRN4692 CSEPs: IGT and GT File Formats (CIN Files)
XRN4693 CSEPs: IGT and GT File FormatsFiles Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN.
XRN4694 CSEPs: IGT and GT File Formats (Create new data validations)

## Slide 6: 2.2 XRN5167 Report Product Class 4 Read Performance (MOD 672)
Customer Class | Voting Party? | Funding Split (%)
Shipper | X | 
Distribution Network Operators (DNOs) |  | 
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- Shippers |  | 
Voting Parties and Funding Split
DSC Service Area: | DSC Service Area 11: Performance Assurance - provision of information to the Performance Assurance Framework Administrator
Service Line Impacts (new, amended, existing, deleted), etc. | Existing: DS-CS SA3
Link to Change Proposal | Link to CP
Change Details
Problem Statement
At present there are read submission performance targets set out in the UNC TPD Section M and these target a percentage of sites for which a read should be submitted. The risk is that if there are larger sites where a read is not received, those will be contributing more to Unidentified Gas (UIG) even though the Shipper may be achieving the read submission target. There is currently insufficient reporting detail to show performance against overall portfolio and no target proportion of AQ within UNC TPD Section M that shippers should achieve.
Change Description
UNC Modification 0672 seeks to reduce Unidentified Gas (UIG) volume by providing a target for read submission performance for Product Class 4 sites against overall portfolio. The modification proposes to target and measure performance against an agreed percentage for energy reconciled after a defined period. This change seeks to provide PAC with an un-anonymised report which will enable them to target shippers whose performance is below the target threshold. To fulfil the reporting requirements that may be required upon implementation of MOD 0672, the following reports should be added to the Performance Assurance Report Register. Two new reports will be included in the Performance Assurance Report Register (PARR) document: a Schedule 2.A Anonymised Report and a Schedule 2.B Unanonymised Report. (Note: whilst the Draft Modification Report only describes an Anonymised Report, the DMR also states “This reporting will be shared with PAC on a monthly basis at an un-anonymised level.” (Section 5: Solution). Hence a Schedule 2.B Unanonymised Report must also be developed and published.) See CP for the full description and schedule reports
Sponsor Representative | Scottish Power

## Slide 7: 2.3 XRN5168 MOD0721 – Shipper submitted AQ Corrections during COVID-19
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 100%
Distribution Network Operators (DNOs) | Y | 
National Grid Transmission |  | 
IGT’s | Y | 
Impacted Parties:- Shippers, DNO & IGT |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 6: Annual quantity, DM supply point capacity and offtake rate reviews
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Currently within the UNC Users are able to submit Annual Quantity (AQ) Corrections for premises where they consider that the AQ does not reflect the expected seasonally adjusted consumption of gas over the subsequent 12 months. The UNC sets out the eligible reasons for AQ Correction. These being: • The confirmed theft of gas (UNC TPD G1.6.21(a)) • The installation, replacement or removal of Consumer's Plant which results in a material change in the basis on which gas is consumed (UNC TPD G1.6.21(b)) • The commencement of a new business activity or discontinuance of an existing business activity at the consumer's premises (UNC TPD G1.6.21(c)). A User may also submit an AQ Correction where the User submits a Meter Reading which is rejected because it falls outside the wider tolerance band, but for which the User is satisfied that the Meter Reading is valid (and would not fail validation if the Annual Quantity were so changed). The COVID-19 Pandemic has led to businesses varying their activity or patterns of activity, for example: • Discontinuing activity (i.e. not being classed as essential, therefore being subject to Lockdown); • Establishing others (e.g. repurposing factories to make essential equipment (e.g. ventilators)); or, • Increasing existing activity having been classed as essential or meeting shortages (e.g. toilet roll factories). The current criteria for AQ corrections do not cater for changes in consumption for the above reasons, meaning that many sites have AQs that are unrepresentative of the actual consumption, with no mechanism in place to amend the AQ quickly enable increased volumes of AQ Corrections to be processed, measure and monitor AQ Corrections to ensure compliance with UNC. Create means to cancel AQ corrections that are non-compliant
Sponsor Representative | Gazprom

## Slide 8: 2.4 XRN5169 MOD0722 – Allow Users to submit Estimated Meter Readings during COVID-19
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 33%
Distribution Network Operators (DNOs) |  | 67%
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- Shippers |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 5: Metered volume and quantity
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Currently Users are unable to submit Estimated Meter Readings other than estimated Proposing User Estimate Opening Meter Readings (M 1.5.2 (c) (iv) refers), on the assumption that Shippers will either be able to obtain meter readings through site visits, or from customers. Where such readings are not available, then the UNC requires that meter reads are obtained by the transporters under the must-read process. As a result of the COVID-19 pandemic, routine site visit activity has ceased. In addition, many sites are unoccupied as the premises are closed, and their customers are unable to obtain meter readings. Indeed, they may be potentially breaking the law if they attempt to do so. Though many sites are known to be not consuming gas, it is not possible under the terms of the UNC to provide Estimated Meter Readings. These means that these sites are not being reconciled to their true consumption.
Change Description
Users may submit an Estimated Meter Reading as an Actual Meter Reading where in the User’s reasonable estimate, no Actual Meter Reading can be obtained as a result of coronavirus (as defined in the Coronavirus Act 2020). 2. An Estimated Meter Reading must reflect as closely as possible the site’s estimated consumption for the period covered by the meter reading, in the User’s reasonable opinion. 3. User must keep records of how any Estimated Meter Readings were derived for a period of 2 years
Sponsor Representative | Gazprom

## Slide 9: 2.5 XRN5170 MOD0723 – Use of the Isolation Flag to identify site with abnormal load reduction during COVID-19 period
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 100%
Distribution Network Operators (DNOs) | Y | 
National Grid Transmission |  | 
IGT’s | Y | 
Impacted Parties:- Shippers, DNO & IGT |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 1: Manage supply point registration
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP 5970 Link to CP 4645 (see next slide)
Change Details
Problem Statement
Live Supply Meter Points are subject to energy allocation and are also subject to being allocated the relevant share of Unidentified Gas (UIG) against each site. UNC Transportation Principle Document (TPD) Section G 3.5 states that a site that is Isolated by a Shipper User is deemed to warrant that the site is no longer being able to consume gas and is therefore removed from energy allocation and receiving allocation of UIG during the period of Isolation. Restrictions on businesses and people under the COVID-19 response, which includes measures as stated in Coronavirus Act 2020, has resulted in some sites not consuming gas, but as they are still capable of consuming and not discontinued, they cannot currently be deemed as Isolated for purposes of UNC TPD Section G. Currently Shipper Users can send a notice to Isolate a site by providing a notification to CDSP to advise that they have carried out specific activities with relation to cessation of the supply of gas at a Supply Meter Point under the following conditions as stipulated in UNC TPD Section G 3.5.5 ‘Where a User provides a notification in accordance with paragraph 3.5.2 such User shall have taken all reasonable steps to ensure that all work to cease the flow of gas has been carried out by suitably competent personnel using that degree of skill, diligence, prudence and foresight which would reasonably and ordinarily be expected from a skilled and experienced person complying with applicable law, recognised industry standards and GDN/PM/GT4, engaged in the same type of undertaking and the Transporter will be entitled to assume that the User has complied with such obligation’ This Modification seeks to temporarily allow these sites to be marked, and treated as, ‘Isolated’ for the purposes of Annual Quantity (AQ) calculations, energy allocation and UIG, without meeting the conditions for physical discontinuance as stated in UNC TPD Section G 3.5.5, whilst affected by measures in the Coronavirus Act 2020
Change Description
See the CP for full description
Sponsor Representative | NGN

## Slide 10: Change Required to Support Modification
Due to Mod 0723 where physical isolation need not have taken place the risk of incrementing reads on RGMA transactions will increase exponentially
XRN4645 is in place to prevent incrementing reads from being submitted within RGMA flows on an isolated meter point
  The solution to this, a new RGMA rejection code, has been previously ratified by DSG
0723 is expected to be utilised by many thousands of Supply Meter Points, that will be capable of physically flowing gas, so the new rejection code is now needed in order to support its implementation and prevent system exceptions and any resultant adverse impact to reconciliation release (and to UiG)
The urgency to implement a new rejection code was presented to DSG on 27/04/20 and no comments were made
We are seeking an approval in principle to implement the rejection code with a reduced lead time and in lieu of change packs being issued. We will propose the use of either:
  A new RGMA rejection code – essentially bringing forward the rejection element of the existing XRN 4645, or
  Re-use of an existing RGMA rejection code – which would mean that remedial work would need to be undertaken in 4645 to provide the new rejection code
    Our preference is the former, from efficiency of change perspective, but will solicit views in the Change Pack to ensure that DSC Customer and industry systems are not adversely impacted

## Slide 11: 2.6 XRN5171 MOD0724 – Amendment to Ratchet charges during COVID-19 period
Customer Class | Voting Party? | Funding Split (%)
Shipper | X | 33%
Distribution Network Operators (DNOs) | X | 67%
National Grid Transmission |  | 
IGT’s |  | 
Impacted Parties:- Shippers & DNO |  | 
Voting Parties and Funding Split
DSC Service Area: | Service Area 5: Metered volume and quantity
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Under UNC Transporters Principle Document (TPD) Section B Transporters are obliged to calculate Ratchet Charges where a Class 1 or 2 site exceeds their booked capacity. As a result of the COVID-19 pandemic a number of sites are having to increase their production etc in order to support the local/national needs caused by the crisis. This includes, but is not limited to, medical facilities, food producers, manufacturers of medical supplies or other relevant equipment. Also, a number of sites have changed their production purpose during this time to meet the needs of the NHS and other emergency services, eg exhibition spaces being utilised as temporary hospitals, breweries creating sanitiser sprays. Usage over the booked capacity for these sites will not only see them incur ratchet charges for the period, they will also have an increased System Offtake Quantity (SOQ) after the COVID-19 period, without the need for the increased capacity after the crisis. This would result in additional capacity charges being incurred until they can request a decrease at the start of the SOQ reduction window in October 2020 or later should the crisis continue.
Change Description
Where a Shipper User identifies a site as having increased consumption as a direct result of it assisting in the COVID-19 response, Shipper Users will be able to apply for the following Transitional rules to be applied. Applications, with supporting information, are to be made via Xoserve. Transporters decisions on the validity will be final. The periods during which the a relevant Supply Point is deemed to be in a COVID-19 period for the purposes as outlined in COVID-19 specific Modifications are: Where any of the powers as laid out in the Coronavirus Act 2020 Schedule 22, (Powers to Issue Directions Relating to Events, Gatherings and Premises) are enacted for all or any of England, Scotland, Wales, then this will be deemed to be a COVID19 Period for UNC purposes for the relevant Supply Point, when the Supply Point is situated in the a part of the UK for the period during which any of the powers enacted relevant to that part of the UK are in force. See CP for full description
Sponsor Representative | NGN

## Slide 12: 2.7 XRN5172 MOD0725 – Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19
Customer Class | Voting Party? | Funding Split (%)
Shipper | X | 
Distribution Network Operators (DNOs) | X | 
National Grid Transmission |  | 
IGT’s | X | 
Impacted Parties:- Shippers & DNO |  | 
Voting Parties and Funding Split
DSC Service Area: | 
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Since the COVID-19 pandemic many sites are in lockdown and business as usual has been disrupted. This has resulted in large changes in network use, especially for Class 1 and Class 2 Supply Meter Point sites, with many either ceasing production or seeing substantial reductions in daily demand. As a result, the site’s Transportation charges are no longer reflective of their actual use.
Change Description
This Modification proposes to create a defined period (implementation date to 30 September 2020) in which Class 1 and Class 2 Supply Meter Points (excluding Seasonal Large Supply Meter Points) can submit revisions to SOQ values to the CDSP to better reflect their gas network use during this summer. For the avoidance of doubt the process would not be retrospective.
Sponsor Representative | Gazprom

## Slide 13: 3. New Change Proposals – Post Initial Review

## Slide 14: 3.1 XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions
Customer Class | Voting Party? | Funding Split (%)
Shipper | Y | 
Distribution Network Operators (DNOs) | Y | 
National Grid Transmission | Y | 
IGT’s | Y | 
Impacted Parties:- All |  | 
Voting Parties and Funding Split
DSC Service Area: | CSSC Change
Service Line Impacts (new, amended, existing, deleted), etc. | 
Link to Change Proposal | Link to CP
Change Details
Problem Statement
The Ofgem Switching Programme Design Baseline 4 published in June 2018 indicated that following the implementation of the Central Switching Service (CSS), the preferred implementation of SoLR directions would be given effect using a Market Participant Identifier (MPID) transfer e.g. re-assignment of the failing supplier’s short code to the appointed SoLR. This would effectively transfer responsibility for all supply meter points registered against the failing supplier’s short code to the SoLR. Please see the change Proposal for the full statement.
Change Description
The Change Proposal will require changes to the MDD Market Participant Identity Verification Approach Document. This includes changes to the business rules in section 4 to clarify that supplier short codes can be re-assigned as part of a SoLR event and that a single Market Participant Identity could be assigned to different legal entities where the associated supplier and shipper are different.
Approvals | Deferrals | Rejections
2 | 1 | 4
Consultation Summary

## Slide 15
XRN and Title Voting Party Change Pack Ref | Organisation |  | Change Proposal in Principle : Approve Reject Defer
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions Voting Party: All Change Pack Ref: 2566.3 - MT - JR | EDF | Q1 - No. Q2 - Yes. We do however believe this is the correct time and opportunity to explore the shipper ID side. 1 - what would happen in the even of a shipper of last resort situation, is there a way a bulk shipper change could happen without the need for SPA CoS processes? Or could a transfer of shipper ID be facilitated if SoLR chose this option? 2 - what would happen if supplier was also their own shipper. How could this be managed? Q3 - We would support a minor release if changes only relate to supplier ID. If any changes are to be made to shipper ID as per my answer to Q2, we would need 6 months notice. Q4 - Yes. | Approve
 | NGN | Q1 - Yes – As Transporters may not have a Post Emergency Metering Services (PEMS) contract in place with the new Supplier, there is the risk that works will be carried out without the appropriate contractual arrangements and protections in place. Q2- Yes – As Transporters may not have a Post Emergency Metering Services (PEMS) contract in place with the new Supplier, there is the risk that works will be carried out without the appropriate contractual arrangements and protections in place. Q3 - If this proposal were to be implemented, we believe it would require a Major Release with at least 6 months’ notice for parties as we may need to make system as well as operational changes to enable us to endeavour to mitigate the traceability of contractual arrangements Q4 - Unable to comment as Section A6 contains no information | Reject
Initial review questions
1. Do you think the change proposed poses a material risk/cost to your organisation and / or the market?
2. Do you think the change proposed will benefit your organisation and / or the market? Please provide any quantifiable outputs as well as any assumptions.
3. As a result of this change, would your organisation support this to be implemented within a minor/major release. What Lead time is needed
4. Do you agree with the principles of this funding as indicated in section A6 (Service Lines and Funding)?

## Slide 16
XRN and Title Voting Party Change Pack Ref | Organisation |  | Change Proposal in Principle
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions Voting Party: All Change Pack Ref: 2566.3 - MT - JR | National Grid | Q1 - We do not believe that this changes poses a material risk to National Grid Gas as we believe the impacts (at first sight) look minimal. However we await the results of a full impact assessment to further quantify our response regarding risk and costs. Q2 - We await the results of an full impact assessment to further quantify our response. Q3 - National Grid believe the impacts (at first sight) look minimal, however we await the results of a full impact assessment to further quantify our response - only then would we be able to provide a accurate lead time for change - taking into account the complexity of change and when this change could be implemented considering the other changes either in flight or planned. Q4 - No details of funding arrangements have been provided in order to provide a view - we await the results of a full impact assessment to further quantify our response. | Approve
 | SSE | Q1 - There will be costs to amend our systems and processes, however it is not possible to impact assess and quantify these costs without further detail of the proposed new process - what are the redlined changes to be applied to the MDD Market Participation Identity Verification Document? How will the reassigned supplier short codes and break with the associated shipper link be communicated/ via what changes to which flows? Until such detail is provided, it is not appropriate to assume the level of materiality. Q2 - This change may have a relatively high impact on supplier/ shipper systems and processes for what seems low overall benefit to the market. Other than the need to facilitate delivery of the new faster switching arrangements, the benefits to the market described in section A4 require more explanation as at present they do not provide specifics or clear justification for implementing this change ahead of CSS go-live. Q3 - The change is proposed to be implemented ahead of CSS go-live, but it is not explained how far ahead this could be or why implementation before CSS go-live is of benefit. As such, it would seem more appropriate that the change should be a major release to align with CSS go-live date, with a minimum of 6 months for implementation. Q4 - The funding allocation is not yet indicated in the document section A6 so it's not possible to comment on this. | Reject
Initial review questions
1. Do you think the change proposed poses a material risk/cost to your organisation and / or the market?
2. Do you think the change proposed will benefit your organisation and / or the market? Please provide any quantifiable outputs as well as any assumptions.
3. As a result of this change, would your organisation support this to be implemented within a minor/major release. What Lead time is needed
4. Do you agree with the principles of this funding as indicated in section A6 (Service Lines and Funding)?

## Slide 17
XRN and Title Voting Party Change Pack Ref | Organisation |  | Change Proposal in Principle
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions Voting Party: All Change Pack Ref: 2566.3 - MT - JR | Wales and West | Q1 - We think that the change poses a material risk to WWU because we will use the link between Supplier short code and the legal entity. this will have a number of impacts on WWU. We think This proposal has been put forward to solve a small but urgent problem (speedy transfer in case a Supplier of Last Resort is appointed) but creates a much larger and enduring problem. If Supply short code ABC moves from X ltd to Y ltd then unless a clear record is kept of exactly when this happened we will not have a clear view of the company history. It also means that any reports based on Supplier Short Codes would need to be checked in case there was a change of owner and the reports would fail to give a true picture. Over time it would mean that these reports would become unusable particularly if they were done over a few years where there were a number of movements of Supplier Short Codes. There is no shortage of short codes there are 26 cubed or 17,576 available. A specific financial impact relates to Supplier related debt for example for Post Emergency Metering Services. If short codes move between legal entities then it will be difficult to identify the legal entity that is liable for the debt. This will almost certainly lead to increased bad debt resulting in prices being higher than they otherwise would be. When a Supplier fails and a SOLR is appointed one of 2 things can happen. 1. The SOLR becomes the holder of the failed Supplier's licence and the short-code moves across to the new supplier. Industry records do not need to be changed but we need an additional Supplier account to be set up for the Supplier taking on the failed Supplier's licence for the new extra short-code under their entity. 2. The licence is revoked and the supply points move under the SOLR’s existing licence/short-code. This requires prompt notification of the short-code to which the the supply points are being moved. The proposal is for a hybrid of these that would see the the failed Supplier's Short Code moved but without the licence being transferred to the new Supplier, thereby destroying any link between the legal entity and the short code. Q2 - The change will not benefit WWU. At the very least if will make reports based on Supplier short codes unreliable and will require someone to know that short code ABC transferred from legal entity X to Y on a certain date. At worst it will mean increased PEMS bad debt. We would expect it to lead to more substantial risks for Shippers that ship for third party Suppliers. Q3 - We do not support this progressing either as a major or minor release. Q4 - This seems to have come out of the faster switching project and should be funded as a Shipper funded consequential change. | Reject

## Slide 18
XRN and Title Voting Party Change Pack Ref | Organisation |  | Change Proposal in Principle : Approve Reject Defer
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions Voting Party: All Change Pack Ref: 2566.3 - MT - JR | Scottish Power | Q1 - More time is required to impact assess this change and identify what material risk/cost this could have on Scottish Power. Given the fact there is now a 6 months delay to the CSS Programme, we would be appreciative of an extension to fully understand the impacts to our business system and processes. Q2 - No, the vast majority of SoLRs take responsibility of the ID going forward. If this change is approved, it would only add to confusion. We would be looking for the change to include effective from AND to dates. Q3 - Major Release Q4 - Yes | Defer
 | SGN | Q1 - Yes – SGN as a Transporter believes the proposal to re-use the Supplier Sort Code may pose a material risk to our business. Re-use of the Supplier short code presents issues in relation to the current Post Emergency Metering Services (PEMS). Existing activity carried out under PEMS Contracts will impact the contractual relationships and billing due to the change in relationship which would be initiated by this proposal. Q2 - No - This will impact the ability to accurately identify a legal entity for contractual purposes. In addition, the wider implications to systems in breaking the relationship between the Supplier and Shipper have yet to be established. Q3 - In the event that this change were to be implemented, we would request a Major Release with a minimum of 6 months lead time. This would enable impacted parties to make operational and system changes to mitigate consequential contractual relationships. Q4 - No funding indication provided therefore no comment. | Reject
Initial review questions
1. Do you think the change proposed poses a material risk/cost to your organisation and / or the market?
2. Do you think the change proposed will benefit your organisation and / or the market? Please provide any quantifiable outputs as well as any assumptions.
3. As a result of this change, would your organisation support this to be implemented within a minor/major release. What Lead time is needed
4. Do you agree with the principles of this funding as indicated in section A6 (Service Lines and Funding)?

## Slide 19: 4. New Change Proposals – Post Solution Review

## Slide 20: 4.1 XRN4923 - AQ Calculation for RGMA (ONUPD) Estimate Reads
Follow up from DSG

## Slide 21: Background
XRN4923 was raised to look at the possibility of using Estimated RGMA readings within the Rolling AQ process
Scope includes UPD updates where no reads are provided, resulting in the CDSP having to estimate readings (JOB file are out of scope)
Currently CDSP estimated transfer readings feed AQ calculation processes
Aim is to align the approach and include estimated RGMA readings within the AQ calculation process
Solution Review Change Pack was issued out in November (2489.9 - RT - PO)
One solution was identified - Enable estimate reads created in UKL as a result of successful processing of RGMA ONUPD updates to trigger and be used in the Rolling AQ calculation process
HLSO cost was between 10,000 - 20,000 GBP
Reps received are as follows:
  2 Approval
  1 Reject
  1 Defer
Reps discussed in December-2020 ChMC and approval given to defer back to DSG for further development/ratify logic

## Slide 22: XRN4923 Reps
Customer | Org | Status | Representation | XOS Response
Eleanor Laurence | EDF | Reject Date & Solution | We do not support option 1 if UPD flows sent as part of a Change of Shipper/Supplier event are not treated differently (wait to estimate any read until after end of window for a Supplier to provide a customer or other opening read that could be validated and used in preference to a possible inaccurate estimate). We also do not see the benefits this will bring as estimated read will be generated using AQ and last read and so will not benefit the rolling AQ process | Thank you for your representation. Regarding your additional query, in the scenario where a UPD is provided as part of a Change of Shipper event, and the UPD is submitted before the CDSP estimates the Transfer Reading, the CDSP will firstly fulfil the Estimated Transfer Read early before estimating the UPD readings (if no actuals are provided), if actual readings are provided by the Shipper within the UPD file then these will either be used to assist the estimation of the Transfer Reading or the RGMA Read will be used as the Transfer Reading (depending when the UPD is submitted). Shipper Transfer Readings currently triggers a Rolling AQ calculation, so the fulfilment of the UPD estimates in these scenarios would not add additional AQ calcs. The main reason/benefits for the proposal was to align processes (as other CDSP estimates such as Shipper Transfer/Re-Confirmation reads feed the AQ process) and an attempt to trigger additional Rolling AQ calculations that could make the AQ more accurate if a number of months have passed since the last Rolling AQ.
Kirsty Dudley | Eon | Approve | We support the estimate read approach outlined. Should any suggestions be made by others during this representation we believe they should be reviewed for suitability without impacting the implementation date. | Thank you for your representation, we will feed this into ChMC for a final decision.
Helen Bevan | Scottish Power | Defer Date & Solution | Could you confirm how the read estimation is calculated ,my understanding is that it is currently calculated using the current AQ, meaning the new AQ will likely to be similar or the same. Can you please clarify what the benefit of the change is? | Thank you for your representation. Regarding your additional query, you are correct in that the CDSP non-daily metered read estimation process will utilise the AQ value in it's calculation. Therefore the AQ, in theory, could be similar/the same as the previous AQ value if no additional changes have been made to the Supply Meter Point. However, this may not always be the case as the Rolling AQ process uses readings within an 'optimum' rolling period, and some reads used in the last rolling AQ processes may not form part of the new calculation, they may have dropped off, leading to a revised AQ value. The main reason for the proposal was to align processes (as other CDSP estimates such as Shipper Transfer/Re-Confirmation reads feed the AQ process) and an attempt to trigger additional Rolling AQ calculations.
Alison Price | npower | Approve | Only 1 solution available | Thank you for your representation, we will feed this into ChMC for a final decision.

## Slide 23: DSG Outcome
DSG was asked to provide ChMC with a recommendation of either progressing with the change or to withdraw
Majority of DSG members did not support progressing this change further, as per the previous representations. Some reps did recommend a deferral with additional analysis being carried out before it is looked at again
ChMC Action
We ask that the Change Management Committee make a decision to
Defer the change for analysis
Withdraw the change for it to be raised again at a later date if still needed.
DSG and Xoserve recommends Option 2 to withdraw the change.

## Slide 24: 5. Implementation Plan
Please see the following slides for an overview of:
Detail Design Changes for approval
    XRN4850 - Notification of Customer Contact Details to Transporters
    XRN4922 CSSC Shipper BRD
    Settlement Data
Outages
    D & Boks, Control-M and Birst Connector Joined together under Shared Components
    DCC dates amended to be confirmed
    2 new outages – UK Link Portal and CMS
Attached is the full Implementation Plan document.

## Slide 25: Detailed Design Summary
The CSSC Settlement data change had 1 abstain response from Npower
“These proposals are still being evaluated as part of the detailed design phase, and therefore we have no views to put forward at the current time.”
Chart: 
| 01/06/2020 | CSSC | CSSC | 4850 | 4922 | Settlement Data
Abstain | 1
Approve | 3 | 1

## Slide 26
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
4970 | CMS | 09/05/2020 | 00:00 | 10/05/2020 | 19:00 | This is the cutover of the production environment for CMS, the outage will be on the weekend, the impact to the industry should be minor and that the Contact Management System will be unable to send or receive files, raise contacts and will not allow users to log on during the maintenance window as the application is switched from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 13/05/2020
4970 | CMS | 23/05/2020 | 00:00:00 | 24/05/2020 | 07:00:00 | This is the outage for CMS DR testing this will be on the weekend, the impact to the industry will be minor as this will be conducted through the scheduled maintenance window. During this window CMS will be unavailable as such users will be unable to log into the system and files that would normally be processed daily are unaffected as they are planned/scheduled for outside this window. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 13/05/2020
4970 | Shared Components | 15/05/2020 | TBC | 16/05/2020 | TBC | This is the cutover is for the collective aspects that make up Xoserve Shared Components (AD & Boks, Control-M and Birst Connector) the impact to the industry should be minor. Batch jobs that utilise Control-M during this window will use the contingency process will the migration from our Legacy DC into the TCS ECP takes place. Subject to change due to multiple inflight changes at the time, but only by a week. | 13/05/2020
 | Internet routing for UKLink | 23/05/2020 | TBC | 24/05/2020 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or receive files to corresponding systems during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | 13/11/2019
 | Gemini | 05/07/2020 | 03:00 | 05/07/2020 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 11/12/2019
4970 | DCC | TBC | TBC | TBC | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | Updated 13/05/2020
4970 | DCC | TBC | TBC | TBC | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 13/05/2020
10266 | UK Link Portal and CMS | 17/07/2020 | 23:00 UK BST | 18/07/2020 | 10:00 UK BST | UK Link Disaster Recovery Test 2020 (Failover to DR site) - the UK Link system will operate normally from the DR site in the period between Failover and Failback. | 13/05/2020
10266 | UK Link Portal | 18/07/2020 | 23:00 UK BST | 19/07/2020 | 07:00 UK BST | UK Link Disaster Recovery Test 2020 (Failback to primary site) - contingency dates for the test are Friday 14th to Sunday 16th August 2020 with the same timings as above. | 13/05/2020

## Slide 27: 6. Approval of Change documents
6.1 BER for XRN5092 iConversion Phase 2
  Voting: NTS
6.2 BER for XRN5152 Minor Release drop 7
  Voting: All
6.3 CCR for XRN5064 Meter Asset Enquiry Enhancements
  Voting: Shippers
6.4 CCR for XRN4779 Adding AQ to the PARR reports
  Voting: Shippers
6.5 CCR for XRN4857 Reporting review
  Voting: Shippers

## Slide 28: 7.1 XRN5110 November 2020 History and Scope
November 2020 Major Release was firstly earmarked for delivery of Retro, a project that subsequently required a detailed Proof Of Concept exercise
An alternative November-20 major release was scoped, based on priority (regulatory, customer benefits) and readiness (progress through the governance cycle) to make use of the delivery capacity
In Feb-20 ChMC approved a scope of 9 changes under parent XRN5110 including:
- 4780c MAP ID: CSSC
- 4801 Additional Info in DES
- 4871b Ratchet regime changes
- 4897 Contact Details
- 4899 Contact Details
- 4931 Space in SPA Files
- 4941 MOD 692 - Auto Updates to Meter Read Frequency
- 4992 Supplier of last resort charge type
- 5014 Hydeploy trial
Release Service Provider will be stood up in May (post-design phase) to begin development with associated costs being incurred from this point

## Slide 29: XRN5110 - Nov 20 Release - Status Update
13/05/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | An additional ChMC meeting was held on the 04/05/20 to discuss the possibility of deferring the implementation of XRN5110 from Nov 20 to Feb 21 due to the ongoing risk caused by COVID-19 and it’s impact on industry participants. The decision from the ChMC on the 04/05/20 was make a decision at the ChMC meeting on the 13th May once updated Government guidance is available. An Impact Assessment is currently being produced to identify the Code Object conflicts between Nov 20 and CSSC and will be completed once the Design activities are completed. Design activities are ongoing and due to finish on 15th April 2020. |  |  | 
Risks and Issues | Risk identified that Build may not start to plan because the CSSC project may still be using the environment. Risk identified that there may be code conflicts against the Nov 20 release and CSSC. The Nov 20 project team will identify all the impacted code objects once Design is completed. Risk identified that due to COVID-19 availability of required resources may be available during the project delivery |  |  | 
Cost | BER presented contains forecast costs and is based on all eight changes being delivered in Nov 20. Full delivery costs to be confirmed once contractual arrangements agreed with suppliers for full delivery of the release |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing. No current concerns |  |  | 

## Slide 30: XRN5110 - Nov 20 Delivery Timeline

## Slide 31: 7.2 BER for XRN5110 November 2020
This is still being worked on and will be a late paper

## Slide 32: 7.3 XRN5110 November 2020 release

## Slide 33
Reject – Reject the proposal to move Nov 2020 delivery schedule to Feb 2021
Approve – Approve to move the Nov 2020 release to Feb 2021
Chart: XRN5110 November 2020 Release
| Approve | Reject | Neutral | Abstained | Approve part delivery | Approve Tentatively
Total | 2 | 4 | 1 | 1 | 1 | 1

## Slide 34
Functional Changes |  |  |  |  | 
XRN / Title | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
XRN5110 - November 2020 Major Release Covid-19 Impacts - Capacity to Deliver in November Change Pack ref: 2566.9 - MT - JR November 2020 Release Voting: Shipper, Supplier, DNs and iGTs | EDF Energy |  |  | X | None
 | ESP |  |  | X | At this time ESP has adequate resources in place to manage the scope of the November release. As Xoserve has indicated they should have the resources to deliver the change then ESP is happy to continue with the delivery in November as scheduled.
 | EON | N/A | N/A | N/A | We recognise the pressures of the current releases, we are able to mobilise delivery either November 2020 or February 2021. We would support the consensus of the response. We accept that changing to February 2021 has different challenges as this is normally a document only release but we are keen to support a pragmatic delivery.
 | NGN |  |  | X | NGN would prefer for the November 2020 release to be delivered as currently planned and not delayed until February 2021. We believe it is important to keep everything running as close to normal where possible to minimise the impacts on industry.
 | Orstead | X |  |  | We support a delay to the implementation of the November 2020 as this will have no adverse effects on our business.

## Slide 35
Functional Changes |  |  |  |  | 
XRN / Title | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
XRN5110 - November 2020 Major Release Covid-19 Impacts - Capacity to Deliver in November Change Pack ref: 2566.9 - MT - JR November 2020 Release Voting: Shipper, Supplier, DNs and iGTs | SGN |  |  | X | SGN support the current scheduled implementation for the November 2020 Major Release to continue as BAU.
 | Npower |  |  |  | It is still too early to take a view on the impact that C-19 will have on our ability to manage the November release as planned. However, we think that a longer implementation period for some of the changes listed would be helpful.
 | SSE | X Part delivery |  |  | We consider that the majority of changes in scope for delivery in the November 2020 release should remain so if possible, to mitigate against change congestion next year. The exception to this would be XRN4941, which should be removed from November 2020 scope due to the appeal raised against/pending Ofgem decision on the related UNC modification that XRN4941 is dependent on for implementation.
 | Ovo Energy | X Tentatively |  |  | We tentatively support this mod. However, we believe that it should be noted that if there is a delay to the November release there could be a knock on effect to later modifications, and that due consideration should be given to understand workloads and capabilities further down the line.
 | Centrica | X |  |  | A delay to the industry release would allow industry participants to prioritise workstreams in alignment with Ofgem’s guidance: • ensuring customer needs are met, particularly the needs of people in vulnerable situations • maintaining secure, reliable and safe energy supplies; and • ensuring the safety and protection of consumers and employees. The earliest date we would accept the implementation of this release would be February 2021, however, we are willing to also consider later dates in 2021 where appropriate.

## Slide 36: 8.1.1 XRN4996 - June 20 Release - Status Update
13th May 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Plan: Issues with UAT and RT are being experienced by Xoserve which is having a cumulative impact on plan hence we have changed our RAG status to amber. Delivery: User Acceptance Testing (UAT) has been completed for 4 changes and Regression Testing (RT) completed for 2. Replan completed, UAT and RT is in progress for the remaining changes. Performance Testing: Has commenced for all changes Training: Training arranged for 11th May for 5 changes, xrn4850 training proposed for w/c 18th May Market Trials: MT approach approved at DSG and participants confirmed. Data prep in progress. Workshops with DN’s/iGT’s planned for 15th & 22nd May iDR: Preparation has commenced with a planned execution on 12th/13th June Implementation: Implementation date of Saturday 27th June confirmed. Implementation approach shared. |  |  | 
Risks and Issues | Risk – There is a risk that the progress of June 20 project phases and Market Trials for XRN4850 will be impacted from COVID-19 leading to a delay to implementation; we are closely monitoring impacts of WFH and any staff number reduction across Xoserve and Suppliers |  |  | 
Cost | Operating costs for xrn4850 shared with DN’s on 21st April. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 

## Slide 37: XRN4996 - June 20 Release Timelines
Key Milestone Dates:
Capture completion
- 19/09/19
Design completion
- 13/12/19
Build & Unit Test completion
- 31/01/20
System & UAT completion
- 15/05/20
Regression Test completion
- 29/05/20
Market Trials completion
- 19/06/20 (provisional)
Implementation
- 27/06/20
PIS Completion
- 25/09/20 (provisional)

## Slide 38: June 20 Release Summary
June 20 Release consists of 7 changes, Implementation is planned for June 2020:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 – Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining CRs. Descoped at ChMC on 08/01/20
** Descoped at eChMC on 22/11/19
*** Added to scope (revised scope from original)

## Slide 39: 7.1.2 High Level Implementation Timeline
The implementation for the 6 changes consists of code transports for BW, PO, AMT and ISU systems. Deployments for CMS and UKLink Portal and Integration for SMS/Email service.
We will need to close our EFT channels in order to implement the AMT and PO changes as part of XRN4850 and XRN4772
26
/
06
/
2020
27
/
06
/
2020
26
/
06
/
2020
23
:
59
:
59
Final Outbound files Sent
26
/
06
/
2020
-
26
/
06
/
2020
03
:
00
:
00
-
06
:
00
:
00
Code Transports/deployments
26
/
06
/
2020
-
27
/
06
/
2020
06
:
00
:
00
-
07
:
00
:
00
QA
27
/
06
/
2020
07
:
00
:
01
Open EFT channels
26
/
06
/
2020
23
:
00
:
00
Final Inbound Files processed
27
/
06
/
2020
00
:
00
:
01
Stop
EFT outbound channels
26
/
06
/
2020
23
:
00
:
01
Stop
inbound EFT channels

## Slide 40: File Format Transition plan (xrn4850)
To incorporate the changes in the file formats, the EFT channels will need to be closed in order to implement the changes in AMT and PO for XRN4850 for the below inbound files
  CNF, CNC, CFR, CNR, TRF, CSS, CRS, EMC and CTR – S66 segments will be enhanced to introduce new fields
We will follow the standard processing times of the files below and ensure that they are all processed before we close the channels
The new fields in S66 segment will be effective for files received after 07:00:01 on the 27/06/20. The change in rejections for the inbound files, will be applicable to any files received after this point.
All files in the old format are expected to be received by 22:59:59
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59 prior to closing the channels
Change ID | Last inbound in Old File Format (Time = File Processing) | Last Outbound in Old File Format (Time = File Processing) | First Inbound in New File Format * (Time = File Processing) | First outbound processed in New File format (Time = File Processing)
XRN4850 | 26/06/2020 CNC – 23:00:00 CNF – 23:00:00 EMC - 23:00:00 CSS - 23:00:00 | 26/06/2020 TRF – 08:00:00 CTR, CNR and CFR will be processed after CNC and CNF execution at 23:00:00 | 29/06/2020 CNF – 11:00:00 CNC – 18:00:00 EMC – 00:00:01 onwards CSS – Adhoc file | 29/06/2020 TRF - 09:00:00 CFR – 11:15:00 CNR – 18:00:00 CTR – 00:00:01 onwards (Post EMC)
*As CNF, EMC and CNC are only business day files, we are not expecting the next CNF, EMC and CNC until 29/06/20

## Slide 41: File Format Transition plan (xrn4772)
To incorporate the changes in the file formats the EFT channels will need to be closed in order to implement the file format changes in PO for XRN4772
  AWV and FWV– Solar and Precipitation parameters will be added along with Temperature and wind and the file format will be changed to capture all parameter values on an hourly basis
We will follow the standard processing times of the files below and ensure that they are all processed before we close the channels
The new fields in AWV and FWV will be effective for files received after 07:00:01 on the 27/06/20
All files in the old format are expected to be received by 26/06/20 22:59:59
Monitoring of all inbound files and confirmation of all response outbound files will be completed between 23:00:01 and 23:59:59 prior to closing the channels
Change ID | Last inbound in Old File Format (Time = File Processing) | Last Outbound in Old File Format (Time = File Processing) | First Inbound in New File Format (Time = File Processing) | First outbound processed in New File format (Time = File Processing)
XRN4772 | 26/06/2020 AWV – 23:00:00 FWV – 23:00:00 | 26/06/2020 AIA (to NG/GEMINI)- 07:30:00 CWF (to NG/GEMINI)- 23:00:00 | 27/06/2020 AWV– 07:00:00 FWV– 07:00:00 | 27/06/2020 AIA (to NG/GEMINI)- 07:30:00 CWF (to NG/GEMINI)- 08:00:00

## Slide 42: Deployment timeline
Deployment window to be followed according to the below table
Sl No | System | Available window | Code deployment Date / time
01 | CMS | 12 midnight-7 am | 27-Jun-2020 / 3 am – 4 am
02 | Portal | 5 am – 7 am | 5 am – 7 am
03 | ISU | 5 am-7 am | 27-Jun-2020 / 5 am-7 am
04 | BW/BO | 5 am-7 am | 27-Jun-2020 / 5 am-7 am (After IS-U transport)
05 | PO | 5 am-7 am | 27-Jun-2020 / 5 am-7 am
06 | AMT | 5 am-7 am | 27-Jun-2020 / 5 am-7 am
07 | Control-M | 5 am-7 am | 27-Jun-2020 / 5 am-7 am
Please note: all timings are subject to minor amendments following execution of the Implementation Dress Rehearsal where the detailed low level implementation plan will be updated.

## Slide 43: Additional points-Data Cleansing
XRN4932 cleansing plan:
Maximum volume of CF cleansing is considered around 12K MPRNs in SAP IS-U
This will be phased out in 4 days to accommodate batch window
Daily volume to be considered for cleansing will be around 3K
This approach will de-risk any impact on the daily batch schedule
BW will automatically extract the CF data on D+1 where D is the CF change date in IS-U
Part1-2 Hour window
29/06/2020
Part2-2 Hour window
30/06/2020
Part3- 2 Hour window
01/07/2020
Part4- 2 Hour window
02/07/2020

## Slide 44: 8.2 XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Progress update
13th May 2020 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Step 1 Results published to all participating shippers and market level view presented to ChMC. Generation of results for Step 2 and initial sanity checks and data assurance completed Execution of Deep Dive analysis for Step 2 has been impacted by SAS Analytic tool not being available remotely to complete required activities. Access made available in late April, impacting progress of POC execution for 4 weeks. Deep Dive steps now in progress working towards completing exercise by the end of May (though timescales are challenging) The project team is working towards publishing Industry Packs and Retro recommendations in June (dependent on resource being available to support and not being called on to support any urgent Covid 19 MOD work) Based on the ongoing worldwide Covid-19 situation a risk has been raised on the project regarding the timing of POC outputs and the potential for them not to be fully absorbed or noted at the point of communication as the industry’s focus is on maintaining critical BAU activity. It has been discussed at Change Management Committee and with participating shippers and agreement reached to proceed as planned ensuring the communications are pitched at the right level. Customer Engagement and Communications: Ongoing communication with POC participating members on progress of Step 2 deep dive External Communication approach for Step 2 to be agreed and finalised |  |  | 
Risks and Issues | SAS Analytics Tool is only available when working from the office and this is essential to undertake Deep Dive Analysis, no access is impacting the progress of Retro POC Mitigation: Now resolved following access being made available in late April |  |  | 
Cost | Approval received from DN’s for BER of £270k for proof of concept. Costs within approved budget. |  |  | 
Resources | Xoserve Customer Change team leading execution of POC Step 2 with input from SMEs where required |  |  | 
XRN4914 MOD 0651 - Retrospective Data Update Provision - ChMC Update 13th May

## Slide 45: XRN4914 – Retro proof of concept – Timeline
2019 / 2020
Customer Engagement
Key:
Completed
Slipped / High risk
Medium risk
On-target
Support
Analysis
Customer / Advocates encouraging participation
Checkpoint 1 29th Nov
Design (Step 1)
Test files can be accepted
Initial Customer engagement
kick-off 4th Nov
Planning
Develop (Step 2)
Testing (Step 2)
Kick-off prep
Actual data
files in
Step 1 Compare / Outcome / Aggregate
Initial Customer engagement of File receipt and triage
Actual data files can be accepted
Test data
files in
8th Dec data sliced
Output from Step 1 (Volunteer Shippers > ChMC > PAFA > Website)
Recommendations
Develop (Step 1)
Testing (Step 1)
Checkpoint 2 4th Feb
Design (Step 2)
Dates need to be confirmed post Step 2
results as volumes will inform task size
File Triage
Core Retro Shipper Pack
XRN4914 MOD 0651 - Retrospective Data Update Provision – 13th May 2020
Checkpoint 3 May 1st
Bi - Weekly project update via external communication methods
Technical Support (Innova & Data Strategy) – Excluding Environment maintenance which continues
Industry Pack
RGMA & MAM
Raw Data
Notes: Tony

## Slide 46: 8.3 XRN5152 – Minor Release Drop 7 - Status Update
01/05/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Three changes in XRN5152 Minor Release Drop 7 to be implemented on 04/07/2020: XRN5036 – Updates to Must Read Process (removes AMR and SMART from Must Read contacts - precursor to Nov 2020) XRN4989 – Online Solution for Credit Interest Process (to automatically issue the supporting info through IX) XRN5065 – Addition of Email Address to DES Last Accessed Report (security enhancement) Scope / Implementation Date Approval received from ChMC – 08/04/20 Capture Phase Completed / Impacts Assessments produced / signed-off – 03/04/20 Design Phase Completed / Signed off – 24/04/20 Detailed planning to commence – w/c 01/05/20 Build Phase started – w/c 20/04/20 Change Pack due to be drafted for Internal review by 04/05/20 |  |  | 
Risks and Issues | XRN4989 - There is a risk that DSG (planned for 27/04/2020) will not support the change to the IX route and decide for this change to be scoped into the next UK Link Release. |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21. BER for ChMC approval – 13/05/20 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase |  |  | 

## Slide 47: XRN5152 – Minor Release Drop 7 Timelines
Key Dates:
Impact Assessment Completed / signed off – 03/04/20
Design Complete / signed off – 20/04/20
Build Complete MiRD7– 01/05/20
Testing Complete – 19/06/20
Implementation Complete – 04/07/20
PIS Complete – 17/07/20
Dates now baselined following completion of detailed design

## Slide 48: 8.4 UK Link Releases Update – For Information
May 2020 CHMC

## Slide 49: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Please note that this slide includes potential activity within UK Link over the next 24 months
Assumes 3x Minor Releases required prior to April 2021
BER Approval
10/04/18
Potential Activity
Governance Approval dates tbc…
On track
At risk
Key:
Complete
BER Approval
May-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
Scope Approved – April ChMC
Potential Activity
MiR 9
MiR 8
Retro
Nov 20
June 20
MiR 7
Potential Activity
Potential Activity
Scope Approval – October ChMC
Scope Approval – Jan ChMC
MiR 10
Potential Activity
BER Approval – May ChMC
Scope Approval – July ChMC
June 21
Nov 21
Potential Activity
Potential Activity
Scope Approval – July 20 ChMC
Scope Approval – December 20 ChMC

## Slide 50: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 5036 | Updates to must read process | In Delivery | Nov 2020 | Small | DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4992 | Supplier of last resort charge type | In Delivery | Nov 2020 | Medium | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4780c | MAP ID part C (CSSC) | In Delivery | Nov 2020 | Large | CSS
 | 4941 | Auto updates to meter read frequency | In Delivery | Nov 2020 | Large | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO
MiR D7 Jul-20 | 5036 | Updates to Must Read Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 4989 | Online Solution for Credit Interest Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 5065 | Addition of E-mail Address to DES Last Accessed Report | In Delivery | MiR Drop 7 | Medium | Minor Release

## Slide 51: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)

## Slide 52: 8.5 Change Proposals in Capture

## Slide 53: Context
The Xoserve Customer Change Team (CCT) is currently performing ‘capture’ on 193 changes (not inclusive of changes already in delivery). This includes 23 Change Proposals (CPs) raised by various parties:
- 96 ‘Early Engagements’ (e.g. as yet to be realised UNC / SPAA / REC changes)
- 74 Additional Service Requests (ASRs) or Third Party Requests (TPRs)
We are also working on a further 29 internal Change Requests (CRs)
The order that we work on any given change is dictated by the prioritisation score each change was originally given (ratified in DSG). Some customer changes are regulatory and ‘need by’ dates are driven appropriately
With BAU release schedules being squeezed by CSSC in 2021 / 2022 this is a reminder of the customer changes we are working on and a chance to frame further discussion on whether ChMC would like us to review the order of priority to speed up or pause capture as appropriate for non-regulatory changes

## Slide 54: What’s new with this list?
We usually present a view of everything that is ‘assigned’ to a release and another list of changes that are almost through the governance process and could be contenders for your next scoping exercise. We call these ‘unassigned’ (to a major or minor release)
The view of changes in these slides is more comprehensive and includes XRNs that might eventually draw down on the DSC change budget (should this committee wish it to be delivered) but might not require a release, so would fall outside of our usual discourse / decision points
The priority order is interchangeable and this committee provides steer
We propose a quarterly (at a minimum) review of this list to ensure we are working on the changes you deem priority first to drive future release scoping decisions and focus attention in DSG / ChMC on the changes that matter most to you

## Slide 55: Current Capture List

## Slide 56: Summary / Next Steps
Xoserve deliver customer changes as a priority
23 Change Proposals are currently being progressed through capture
Some customer changes are regulatory and have associated ‘need by’ dates that drive capture and delivery order
We will add an agenda item to the June ChMC to enable you to feedback views on priority order for non-regulatory CPs

## Slide 57: 8.6 UK Link POAP

## Slide 58: 9. CSSC Programme Dashboard
27th April 2020

## Slide 59
Executive Summary
Programme currently tracking Amber, primarily due to the uncertainties around the Switching Programme re-plan, dependencies on CSSP & DES NFR delivery. Key Programme Updates The Programme has successfully exited the "PIT" phase. External "SIT" phase has been delayed by a day to 29th April due to a message signing defect. This was worked through between Xoserve & Landmark and closed on 29/04 Internal Non-Functional Testing continues, with a completion of early June. External Non-Functional Testing continues as per the Work Off Plan to meet the DES 1 hr RTO NFR (agreed with the SI). Internal SIT phases 2&3 continues to track to plan. Preparation continues for UAT and other internal phases continue with replanning in line with the revised Ofgem timelines. Options re being explored with regards to Market Trials. These will be agreed with the Market Trials workgroups and Ofgem Data Migration activities in preparation for external DMT continues to plan and Xoserve is on track to hit programme milestones. General Programme Update Re-plan: Ofgem have advised a 6-month delay to the Switching programme with UEPT moved out up to 6m, due to COVID-19 impacts on suppliers. Xoserve activities are expected to continue to current plan Quality: Internal Gate C++ has been achieved and passed. KPMG continue to assure our programme, on an independent with their draft report issued in support of Stage Gate C++. Findings are being addressed within the programme team. have issued their draft report. Switching Programme Assurance by Expleo has been conducted with a report received with queries. These have since been answered and evidence provided where required Programme Costs: Activity underway to reflect the impacts on CSSC Budget as a result of the re-plan. This activity has a lot of dependencies on clarity from the Switching programme. External Change Request: A number of change requests have been going through programme governance, Xoserve have been assessing them against Functional aspects and high level ROMs have been provided. Costs are being in our budget and will be shared with the Board. These will be shared in conjunction with the budget re-assessment following the re-plan.
Programme Health – RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Return To Green Plan |  | 
Awaiting Switching Programme re-plan (baselined in September 2020) Completion of development for DES NFR to meet the SI "Work Off Plan“ |  | 
KEY Progress (Last Month) |  | 
DMT PIT completed, 1m ahead of plan All data extract changes requested by SI to support Switching Programme completed Team continue working well from home location with no impacts on delivery External audits completed and successfully passed Primary API solution delivered including Smoke testing NFR testing (Phase 1) started Gemini SUPT successfully completed Achieved PIT EXIT and entered external SIT RA020 Readiness Assessment Complete (Business Change Milestone) Internal SIT (Phase 1), focussed on Switching Programme requirements completed, Phase 2 started which will concentrate on Consequential requirements |  | 
Programme Update

## Slide 60: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Provision & Migration | All external & internal data provision to date, have been completed to plan. Internal data migration testing is on track to complete. Preparatory activities are on track to complete ahead of external Data Migration activities. Amber RAG is reflective of the dependency on Landmark to provide REL Data for migration into the external SIT environment. This date has moved a few times; the uncertainty is reflected in the RAG.
 |  | DES & API | Overall RAG Amber. Work continues for DES to meet the 1hr RTO NF and is being actively managed. Agreed "Work Off Plan" in place with SI, in order to meet external NFR testing API: All primary APIs have been delivered and successfully tested. Secondary API delivery is underway and on track to be delivered.
 |  | UK Link | Overall RAG Amber only due to dependency on internal re-planning to align with external programme delay as well as external change requests that are underway. RTG actions: Completion of re-planning and incorporation of Change Requests
 |  | Networks | Overall RAG Amber: Awaiting confirmation from Ofgem on the use of IX by market participants. If IX is descoped, Ofgem will need to raise a CR
 |  | Testing | PIT exit has been successfully met by the programme, caveated by the work-off plan for DES Non-Functional Requirements. Overall RAG Amber due to dependency on completing internal re-planning to align with external programme delay
 |  | Market Trials | Overall RAG Amber. The programme continues engagement with industry, in relation to consequential market trials. Due to the deferral of UEPT, the programme is reviewing the CCMT date and have withdrawn the Switching Programme change (CRD015) submitted to Ofgem, whilst planning reviews and discussions are taking place with market participants and Ofge,
 |  | Service Management | Overall RAG Green. Decision required around the option to integrate Incident Management and Service Request processes once IA has been completed. Placeholders for 4 workshops agreed with DCC to validate the core processes starting 23/04.
 |  | Gemini | Overall RAG Green. Schedule is amber until details of the Programme re-plan are available. NGIT Test Cases for SIT have been received and sent for RQM upload.
 |  | Business Change | Overall RAG Green. The business change assessment pack to support BC020 has been completed and sent to Ofgem and the SI on 09/04​. A re-plan will be conducted once the SI issue a revised CSS IP which incorporates the 6-month extension announced by Ofgem.
 |  | Environments & Release Mgt. | Overall RAG Green: Work continues to assess future requirements and synergise the use of environments in order to reduce spend. Additional environment requirements have also surfaced from the SI.

## Slide 61: Key Programme Risks (1/2)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | Description and probability updated to reflect the re-planning if UEPT. No update received on the mechanism to provide IP addresses to Xoserve or whether any MPs have signed up to use IX to connect to CSS. | 30/06/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 29/05/20
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | This continues to be actively monitored and managed - no changes to the status has been identified that could alter the probability or impact. | 30/09/20

## Slide 62: Status at PIT exit and Current test phase(s)
Current Status
PIT Exit
Lost 54 days due to:
  late delivery of code (Mainly API/DES)
  Issues relating to environments
  System test defects appearing in SIT
Successfully met PIT exit milestone for functional test
Completed 153 Test scripts and all defects were fixed and retested
NFR PIT exit is currently ongoing to be completed on the 9th June. Performance test to commence on the 15th May when DES solution is delivered and deployed to the test environment – Project on track
Total no of scripts = 132
Total no of defects to date = 25, 15 fixed and retested
Total no of scripts executed to date = 44
Project on Track
SIT Phase 2
Test Automation
Total no of scripts = 135
Total no of scripts completed to date 80
Project on track
CSSC UAT (Currently in test prep)
Total no of scripts = 200 (Completed)
SME assurance 80% complete (Remaining 20% Scripts have reviewed and the test team are in the process of updating)
On Track
June release UAT
Bottleneck with test execution support. Go live is at risk

## Slide 64: CSCC File Formats

## Slide 65: CSSC File Formats
CSSC File Formats have been baselined as part of Project Delivery.
The programme recognises that prior to CSSC go-live releases will continue in the interim and there will be a need to merge changes into the CSSC code base which may include changes to file formats. e.g. June 2020.
The programme will aim to merge releases into the CSSC code-set as soon as possible following the go-live date for the particular release.
As soon as stability is reached within a release design Xoserve will analyse any file format changes and produce an updated set of CSSC file format changes where necessary. This will be issued via an Informational Change Pack.
Where there is a risk of contention with a merge process and a CSSC external test phase Xoserve will engage with participants to agree delivery dates for merged code-sets into test environments.

## Slide 66: 10.1 Bubbling Under Report

## Slide 67: 10.2 Gemini Horizon Planning

## Slide 68: 11 Finance and General Change Budget Update

## Slide 69: 12. AOB

## Slide 70: 12.1 Xoserve IX Refresh
Customer Update
15/04/2020

## Slide 71: 12.2 IX Refresh Customer Update
There continues to be a significate impact on the project regarding COVID-19. This is due to customer site access restrictions being in place following government recommendations
  90% of all remaining customers are on hold due to business continuity arrangements or restrictions in place with BT Openreach
  Project continuing where possible with remaining customers
Overall project RAG status remains at Red
  Network Lines, Server and Router installations all require site access which has been limited
  Customer migrations dependent on all physical infrastructure being in place
Project team have engaged with legacy service provider to ensure all customers remain on a fully supported solution
  Agreement in place to extend support past August 2020, if needed
  Minimum 3 month extension
  Extension can be triggered at the end of June 2020
Once lockdown restrictions begin to ease, following government guidance, the project will re-plan and confirm new project milestone dates.
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 73: 11.2 Unresolved Exceptions
What happened? | An ‘Exception’ is raised by UKLink SAP system where the system is unable to complete an activity for an MPRN(s). These system exceptions then require to be investigated and resolved. The majority of exceptions are resolved via a technical or business solution and have no impact to customers as they are resolved before they are needed in the next step of the process. However, there are three outstanding exceptions which we are unable to resolve. Details surrounding these can be found in the attached spreadsheet.
Customers Impacted | Shippers Distribution Networks
Who has this communication been issued to | All Contract Managers Invoicing contacts distribution list
What does this mean? | Reconciliation charges for the affected MPRNs will be held and have not been invoiced. This will also impact Unidentified Gas (UIG) reconciliation as the equal and opposite of the meter point reconciliation charge is not being invoiced in UIG reconciliation. Please see attachment for details by exception code
What have we done to resolve the situation? | Change requests have been raised to prevent re-occurrence of these issues in the future Although the change, once implemented, will resolve the exceptions going forward, in some cases, as detailed in the attachment, the withheld charges will still require further action to be resolved. The actions for this are detailed in the attachment.
Resolution Date | Please see attached spreadsheet for target resolution date for each exception code.
Next Update | Updates will be provided monthly in the Amendment Invoice update pack, published on the Joint Office website for Contract Management Committee Impacted MPRNs are issued in the monthly reports, as part of the Amendment invoice.
Financial / Materiality Impact to Customers | Please see attachment for details by exception code
What action is required by the customer? | No action is required from customers at this time. This communication is for information only. If customer action or support is required, a further communication will be issued.
Additional information: | The MPRNs impacted by these exceptions are detailed in the monthly MI reports that are issued to all impacted customers 2 business days after the Amendment invoice is issued.