## IP - For Approval - Design
UK Link Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4989 |  | Online End to End Credit Interest Process | 2587.2 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X | [5 empty] | 2020-06-10 | 04/07/2020 MiR7
5036 |  | Updates to must read process | 2587.3 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 |  | X |  |  |  |  | 2020-06-10 | 04/07/2020 MiR7
5065 |  | Addition of Email Address to DES Last Accessed Report | 2587.4 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X | X |  |  |  |  | 2020-06-10 | 04/07/2020 MiR7
N/A |  | UK Link File Formats CSS Consequential Change | 2588.1 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X | [5 empty] | 2020-06-10 | CSSC
N/A |  | UK Link Settlement Data API Design Specification | 2588.2 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X | [5 empty] | 2020-06-10 | CSSC
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Implementation Plan - Approved last meeting
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4922 |  | CSSC Shipper BRD | 2567.1 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | [5 empty] | 2580 – JLR - ES | 2020-05-13 | CSSC | Responses - 1 approval
N/A |  | Settlement Data | 2567.2 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | [5 empty] | 2580 – JLR - ES | 2020-05-13 | CSSC | Responses -1 abstain
XRN4897 & 4899 |  | XRN4897 - Resolution of deleted Contact Details at a Change of Shipper event & XRN4899 - Treatment of Priority Service Register Data and Contact Details on a Change of Supplier Event – Change Pack | 2566.1 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X |  |  |  |  | 2579 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 4 approvals
XRN5014 |  | Facilitating HyDeploy2 Live Pilot | 2566.2 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X | X |  |  |  | 2580 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 3 approvals & 1 neutral
XRN4871B | 665 | Modification 0665-Changes to Ratchet Regime - Detailed Design | 2566.4 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X | X |  | X |  | 2581 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 3 approval
XRN4801 |  | Additional Information to be made available on DES | 2566.5 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X |  |  |  |  | 2582 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 4 approval responses, however one of these rejected the implementation date
XRN4850 |  | Notification of Customer Contact Details to Transporters - Revised Change Pack | 2566.6 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X | X |  | X |  | 2583 – JLR - ES | 2020-05-13 | Jun 20 | Responses - 3 approval
XRN4931 |  | Submission of space in mandatory data on multiple SPA files | 2566.7 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X |  |  |  |  | 2584 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 2 approval
XRN4941 | 692S | Auto Updates to Meter Read Frequency | 2566.8 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X |  |  |  |  | 2585 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 1 approval and 2 reject responses. After being approved at the eChMC meeting, this Change was pulled from Nov 20 at the May ChMC meeting due to the Mod not being approved by Ofgem
XRN4992 | 687 | Modification 0687 - Creation of new charge to recover Last Resort Supply Payments | 2566.10 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X | X |  |  |  | 2587 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 3 approval After being approved at the eChMC meeting, this Change was pulled from Nov 20 at the May ChMC meeting due to the Mod not being approved by Ofgem
XRN4780C |  | Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) | 2566.11 - MT - JR | 2020-04-14 | 2020-04-28 | 2020-05-05 | X |  |  |  |  | 2588 – JLR - ES | 2020-05-04 | Nov 20 | Responses - 1 approval response and 1 response to clarify a number of things within the proposed design
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
4970 | CMS | 2020-05-09 | 0:00 | 2020-05-10 | 19:00 | This is the cutover of the production environment for CMS, the outage will be on the weekend, the impact to the industry should be minor and that the Contact Management System will be unable to send or receive files, raise contacts and will not allow users to log on during the maintenance window as the application is switched from PET/KET to Chess/Cress. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-05-13
4970 | CMS | 2020-05-29 | 0:00 | 2020-05-30 | 7:00 | This is the outage for CMS DR testing this will be on the weekend, the impact to the industry will be minor as this will be conducted through the scheduled maintenance window. During this window CMS will be unavailable as such users will be unable to log into the system and files that would normally be processed daily are unaffected as they are planned/scheduled for outside this window. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 10/06/2020 Dates moved forward a week
4970 | Shared Components | 2020-06-12 | TBC | 2020-06-13 | TBC | This is the cutover is for the collective aspects that make up Xoserve Shared Components (AD & Boks, Control-M and Birst Connector) the impact to the industry should be minor. Batch jobs that utilise Control-M during this window will use the contingency process will the migration from our Legacy DC into the TCS ECP takes place. Subject to change due to multiple inflight changes at the time, but only by a week. | Updated 10/06/2020 Dates moved forward a month
| Internet routing for UKLink | 2020-06-26 | TBC | 2020-06-27 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or receive files to corresponding systems during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | Updated 10/06/2020 Dates moved forward a month
4550 | Gemini | 2020-07-05 | 3:00 | 2020-07-05 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 2019-12-11
4970 | DCC | TBC | TBC | TBC | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | 2020-05-13
4970 | DCC | TBC | TBC | TBC | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-05-13