## Slide 1: History and Scope of November-2020 (XRN5110)
November 2020 Major Release was firstly earmarked for delivery of Retro, a project that subsequently required a detailed Proof Of Concept exercise
An alternative November-20 major release was scoped, based on priority (regulatory, customer benefits) and readiness (progress through the governance cycle) to make use of the delivery capacity
In May 20 ChMC approved a scope of 6 changes for delivery under parent XRN5110
In Scope
    4801 Additional Info in DES
    4871b Ratchet regime changes
    4897 Contact Details
    4899 Contact Details
    4931 Space in SPA Files
    5014 Hydeploy trial
Out of Scope
    4941 MOD 692 - Auto Updates to Meter Read Frequency
    4992 Supplier of last resort charge type
    4780c MAP ID: CSSC

## Slide 2: 7.5 XRN5110 - Nov 20 Release - Status Update
10/06//20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delay in completing Design due to SMEs priority of June 20 and rework of XRN4871b. Design activities re-planned to finish w/c 01/06/20. Build activities to start w/c 01/06/20 Build & ongoing phases to be delivered via two drops. Drop 1 – XRNs 4931, 4897, 4899 and Drop 2 – XRNs 4871b, 4801, 5014 Parties are asked to note XRN4780c MAP ID will not be implemented as part of November Release Discussions are ongoing with non-DSC parties Action on Xoserve to discuss with Change Management Committee target implementation dates |  |  | 
Risks and Issues | Risk identified that Build may not start to plan because the CSSC project are still using the environment. To mitigate any delay the project team are investigating the possibility of starting Build on one environment and moving to the original one once it becomes available. Once confirmed Build activities can start w/c 01/06/20. Risk identified that there may be code conflicts against the Nov 20 release and CSSC. The Nov 20 project team will identify all the impacted code objects once Design is completed. Risk identified that due to COVID-19 required resources may not be available during the project delivery |  |  | 
Cost | BER presented contains forecast costs for UAT. Discussions are ongoing to confirm UAT supplier. Once confirmed there is an expectation that UAT costs will reduce. Full delivery costs to be confirmed once contractual arrangements agreed with all suppliers for full delivery of the release. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing. Only concern is availability of SMEs to complete Design approval while June 20 is priority. |  |  | 

## Slide 3: XRN5110 - Nov 20 Delivery Timeline