## Slide 1: UK Link Future Releases Update – For Information
June 2020 CHMC

## Slide 2: UKLink Future Releases
Agenda:
Future Releases update – For Information
  Future Releases Governance Timeline 2020 – 2021
  Changes in delivery
2021 Major Releases – For Discussion
  Current status
  June 2021 Optionality
  November 2021 Optionality
Glossary

## Slide 3: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Please note that this slide includes potential activity within UK Link over the next 24 months
Assumes 3x Minor Releases required prior to May 2021
BER Approval
10/04/18
Potential Activity
On track
At risk
Key:
Complete
BER Approval Jun-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
Scope Approved – April ChMC
Potential Activity
MiR 9
MiR 8
Retro
Nov 20
June 20
MiR 7
Potential Activity
Potential Activity
Scope Approval – October ChMC
Scope Approval – Jan ChMC
MiR 10
Potential Activity
BER Approval – May ChMC
Scope Approval – July ChMC
June 21
Nov 21
Potential Activity
Potential Activity
Scope Approval – July 20 ChMC
Scope Approval – December 20 ChMC

## Slide 4: Change Index – UK Link Allocated Change
Proposed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 5036 | Updates to must read process | In Delivery | Nov 2020 | Small | DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4992 | Supplier of last resort charge type | In Delivery | Nov 2020 | Medium | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4780c | MAP ID part C (CSSC) | In Delivery | Nov 2020 | Large | CSS
 | 4941 | Auto updates to meter read frequency | In Delivery | Nov 2020 | Large | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO
MiR D7 Jul-20 | 5036 | Updates to Must Read Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 4989 | Online Solution for Credit Interest Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 5065 | Addition of E-mail Address to DES Last Accessed Report | In Delivery | MiR Drop 7 | Medium | Minor Release

## Slide 5: 2021 Major Releases - Status
CSSC re-planning for April 2022 underway
The June 21 major release slot was assumed to be the CSSC release
Xoserve limited in what non-CSS changes can be made without impacting CSSC Programme.
June 2021:
Capture in progress for candidate XRNs. DSG discussions on requirements and solution options ongoing
2 changes are ready for assignment to a major release (pending MOD approval)
Standard 12 month project under pressure as:
  Scope will not be confirmed today
  Start-up / Design will need to be condensed to facilitate hitting Change Pack dates (Nov 2020).
November 2021:
Scope constrained by impacts to CSSC
Scope targeted to be agreed at the November 2020 ChMC.

## Slide 6: June 2021 – Optionality for Discussion
No Major Release in June – defer changes to the November 2021 release
Full Major Release in June (Up to 120 points):
  Accept the risks of developing a full size release with Start-Up, Analysis and Design Phases condensed (esp. scope, cost and timeline volatility)
  Mitigate the risks around condensing activity up to the end of Design by flexing Detailed Design Change Pack submission dates
“Midi” Release in June (60 points max)– Reduced scope release - Implement MOD/Regulatory changes, required before November 2021, only
Minor Release(s) – Further reduced scope – only implement those changes that are regulatory, don’t impact CSS or Customer Systems – some changes may need to be split out and the more substantial (customer systems impacting) elements delivered in a subsequent Major Release..

## Slide 7: November 2021 – For Discussion
Currently assuming a full scale UK Link Major Release, the last prior to CSS implementation.
Key points:
Minimising impact on the CSS Programme will constrain scope (especially in the SPA processes)
Scope approval scheduled for November 2021 ChMC
MODs/Regulatory changes required prior to CSS implementation to be prioritised during Capture.

## Slide 8: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)