## Slide 1: Minor Release Drop 7 Update

## Slide 2: XRN5152 – Minor Release Drop 7 - Status Update
01/05/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Three changes in XRN5152 Minor Release Drop 7 to be implemented on 04/07/2020: XRN5036 – Updates to Must Read Process (removes AMR and SMART from Must Read contacts - precursor to Nov 2020) XRN4989 – Online Solution for Credit Interest Process (to automatically issue the supporting info through IX) XRN5065 – Addition of Email Address to DES Last Accessed Report (security enhancement) Scope / Implementation Date Approval received from ChMC – 08/04/20 Capture Phase Completed / Impacts Assessments produced / signed-off – 03/04/20 Design Phase Completed / Signed off – 24/04/20 Detailed Implementation planning to commence – w/c 01/06/20 Build Phase Completed – w/c 01/05/20 Change Packs Issued out for review – May 2020 AT Testing XRN5036 – complete / XRN4989 on track for completion 02/06 / XRN5065 on track for completion 02/06 Code Merge activities started – 29/05 |  |  | 
Risks and Issues | There is a risk that Minor Release 7 could have resources issues during Implementation due to Gemini Migration Project going live 5th July 2020 – Xoserve Implementation approach agreed internal |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21. BER approved at ChMC – 13/05/20 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 

## Slide 3: XRN5152 – Minor Release Drop 7 Timelines
Key Dates:
Impact Assessment Completed / signed off – 03/04/20
Design Complete / signed off – 20/04/20
Build Complete MiRD7– 01/05/20
Testing Complete – 19/06/20
Implementation Complete – 04/07/20
PIS Complete – 17/07/20
Dates now baselined following completion of detailed design