## Slide 1: UK Link Future Releases Update
July 2020 CHMC

## Slide 2: UKLink Future Releases Update
Agenda:
Future Releases update – For Information
  Future Releases Governance Timeline 2020 – 2021
  Changes in delivery
2021 Major Releases – For Information:
  June 2021 – proposed scope
  November 2021 – proposed scope
August ChMC content.
Glossary

## Slide 3: 2020/2021 UK Link Governance Timeline
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 
2020 | 2021
Please note that this slide includes potential activity within UK Link over the next 24 months
Assumes 3x Minor Releases required prior to May 2021
BER Approval
10/04/18
Potential Activity
On track
At risk
Key:
Complete
BER Approved Jun-20
CSSC activity
CSSC
Scope approved – Feb ChMC
EQR Approved – March ChMC
Scope Approved – April ChMC
Potential Activity
MiR 9
MiR 8
Retro
Nov 20
June 20
MiR 7
Potential Activity
Potential Activity
Scope Approval – October ChMC
Scope Approval – Jan ChMC
MiR 10
Potential Activity
BER Approval – May ChMC
Scope Approval – July ChMC
June 21
Nov 21
Potential Activity
Potential Activity
Scope Approval – Aug 20 ChMC
Scope Approval – December 20 ChMC
EQR Approval – Aug ChMC

## Slide 4: Change Index – UK Link Allocated Change
Confirmed Release | XRN | Change Title | Current Status | UK Link Release | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DNO
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DNO
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DNO
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DNO
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4627 | Consequential Central Switching Services | In Delivery | June 2021 | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DNO
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DNO
 | 5036 | Updates to must read process | In Delivery | Nov 2020 | Small | DNO
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4992 | Supplier of last resort charge type | In Delivery | Nov 2020 | Medium | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4780c | MAP ID part C (CSSC) | In Delivery | Nov 2020 | Large | CSS
 | 4941 | Auto updates to meter read frequency | In Delivery | Nov 2020 | Large | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DNO
MiR D7 Jul-20 | 5036 | Updates to Must Read Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 4989 | Online Solution for Credit Interest Process | In Delivery | MiR Drop 7 | Small | Minor Release
 | 5065 | Addition of E-mail Address to DES Last Accessed Report | In Delivery | MiR Drop 7 | Medium | Minor Release

## Slide 5: 2021 UK Link Future Releases
Proposed Release | XRN | Candidate Change Title | Comments | Current Status | Complexity | Points | Finance
Jun-21 | 4941 | MOD0692 - Auto updates to meter read frequency | Descoped from Nov 20. Dependent on Ofgem decision | Design | Large | 13 | Shipper
 | 4992 | MOD0687 – Creation of new charge to recover last resort supply payments | Descoped from Nov 20. Under appeal | Design | Large | 13 | Shipper
 | 5093 | MOD0711 – Update of AUG Table to reflect new EUC bands | HLSOs in review | In Capture | X-Large | 21 | Shipper
 | 5038 | MOD0691 – Class 2,3 or 4 meter points to Class 1 when G1.6.15 criteria are met | Depending on solution option chosen this change could be delivered via a Minor Release | In Capture | Tbd. | Tbd | Shipper
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Related to a SEC change | In Capture | Tbd | Tbd | DN
Nov 21 | 4990 | MOD0664 – Transfer of sites with low read submission performance |  | In Capture | Tbd. | Tbd | Shipper
 | 5063 | MOD0719R – Flow Weighted Average CV (FWACV) |  | In Capture | XXXL | Tbd | DN
 | 5186 | Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  | In Capture | Tbd. | Tbd | DN
 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes |  | In Capture | Tbd. | Tbd | Shipper
 | 5091 | Deferral of creation of Class change reads at transfer of ownership |  | In Capture | Tbd. | Tbd | Shipper
XRN5063 – Flow Weighted Average CV change is likely to be very complex and may not be delivered by a UK Link Major Release.
Service sustaining activity may be considered for inclusion in future releases.

## Slide 6: Available Points A
Year | 2020 |  |  |  |  |  |  | 2021 |  |  |  |  | 
Month | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 100 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 75 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 34 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 21 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 5 |  |  |  |  |  |  | 
Change Packs issued for review
Change Packs issued
Implementation
Scope Approval

## Slide 7: Available Points B
Year | 2020 |  |  |  |  |  |  | 2021 |  |  |  |  | 
Month | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Phase | Start-Up |  | Init | Design |  |  | Build / Test / Implement |  |  |  |  |  | 
Points Available | 120 |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 90 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 60 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 30 |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 15 |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 0 |  |  |  |  |  |  | 
Change Packs issued for review
Change Packs issued
Implementation
Scope Approval

## Slide 8: August ChMC
June 21 Major Release:
  Seek scope approval
  Present High Level Plan (up to the end of Design)
  Seek EQR approval for project costs up to end of Design Phase.
Minor Release Drop 8
  Present plan
  Confirm implementation date and PIS.
November 21 Major Release:
  Update on progress through Capture
  If applicable, discuss risks.
Service Sustaining Schedule:
  Activities to sustain UK Link service – overview.

## Slide 9: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal
HLSO(s) | High Level Solution Option(s)