## Slide 1: CSSC Programme Dashboard
July 2020

## Slide 2
Executive Summary
Key Programme Update (as of 23rd June 20) All key external milestones to date have been met for this reporting period. The programme continues to trend to Amber. Costs: Cost analysis review continues following the announcement of the Programme delay, Programme re-planning, new requirements and a back log of CR’s that currently sit within Programme governance. At this point as confirmed to CoMC we are still within our estimates for FY20/21 and FY 21/22 which will include the 5 million contingency which will be required due to the Programme delay. As the Programme is now extending in 2022 we are estimating our budget requirements in line with the 22/23 budget governance. Data: DM Smoke testing is progressing following previous delays caused by CSSP, however this is behind schedule as testing is taking longer than the Programme planned for. A document inconsistency (PHID v8.4 and DM Solution Design) review by the SI has identified approx. 22 out of 125 data item definitions that require addressing. Approximately 5 data items will impact the programme and the fix time will be approximately 2 weeks. A review of the DMT schedule is now required, in light of smoke test performance, as there are doubts over whether the overall DMT schedule is now achievable. This has been escalated to the SI. External SIT: SIT Integration Sequencing had been extended back in May due to a number of CSSC Defects Since then, there have been further delays to External SIT. SIT Functional Cycle 1 is yet to commence The SI continue to review this plan, and updated plan is expected w/c 06/07 Environments: We continue to raise concerns and challenge the number of environments required by the Switching Programme, a new CR has been raised by the Programme data workstream to for new environments for upcoming test phases. We have asked for an exercise to rationalise environment usage by re-planning to allow reuse where possible. This is an effort to reduce the environment costs that will be incurred by both Xoserve and other Industry parties based on the current plan. DES/API Agile delivery continues to plan in order to feed into SIT phase 4.
Programme Health – RAG |  | 
Overall Programme Status | Previous | Current
Programme Plan – On Track | Previous | Current
Risk Profile | Previous | Current
Resources | Previous | Current
Return To Green Plan |  | 
Resources (supplier resources), Risk and Plan are showing Amber due to uncertainties with the lack of an Ofgem plan. RTG will take place when a plan materialises. Based on this, the programme continues to trend at an amber status Cost and budget review completed with efficiencies agreed to ensure costs remain within approved budget |  | 
KEY Progress (Last Month) |  | 
DMT Smoke testing started NFR Smoke testing started External SIT continues Migration of UK Link on Prem (Project track 1) migration to cloud completed Internal SIT Phase 2 completed, Phase 3 commenced Programme Re-plan (including finances) continues to align to Switching Programme near term plan. Expleo audit review completed. Awaiting final report. No issues identified. Finance and budget review continues |  | 
Programme Update

## Slide 3: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Networks | Overall RAG is Amber. Status remains unchanged pending submission of the Ofgem CR as captured at the Switching Programme Implementation Group on 14/4/20 detailed as follows – “IG10-A03: Adaptor Services Recommendation 17 - It was confirmed that no party intends to use the IX network to connect to the CSS and that Ofgem, Xoserve and DCC were collaborating to identify the appropriate mechanism to descope IX delivery from the Switching Programme which will be implemented via a CR. ​”. Awaiting Ofgem/DCC confirmation of removal.
 |  | Data Migration | Overall RAG is Amber: DM Smoke testing is progressing following previous delays caused by CSSP, although overall, behind schedule as testing is taking longer than originally expected. Document inconsistencies (PHID v8.4 and DM Solution Design) review by the SI has identified approx. 22 out of 125 data item definitions that require addressing. Approximately 5 data items will impact the programme and the fix time will be approximately 2 weeks. The programme believe that a review of the DMT schedule is now required, in light of smoke test performance, as there are doubts over whether the overall DMT schedule is now achievable. This has been escalated to the SI
 |  | UK Link | Overall RAG is Amber. Following approval of internal and external CR’s a review of Technical Specs is in progress, all this will require additional time from SMEs and IS Ops. SME time may be available after 1st June. Additional Requirements and work has been identified to support Secondary APIs as a result of the above we are currently actively managing priorities.
 |  | Testing | Overall RAG is Amber: A high volume of defects sitting with the CSSP are impacting testing window phases and the ability to meet the phase timescales. Xoserve continue to make good progress for our internal UAT phase and have completed Phase 2 test execution and are currently undertaking test evidence assurance activities with internal SME’s. End to End Gemini Trigger Testing schedule has been agreed with National Grid. External SIT “Initial Integration Sequence” test execution phase is delayed due to CSS Landmark identifying a defect on their system. Planned testing of inbound UK-Link API re-commenced on 12/5 but we still have not received any inbound API’s from Landmark.​ This is an external SI milestone and it is marked as red in the CSSIP.
 |  | Testing – Market Trials | Overall RAG is green. Re-plan for Consequential Change Market Trials is now complete. This status is subject to any significant changes made to the overall Ofgem plan. Engagement continues following the Ofgem guidelines and is currently in the voluntary stage, however, it should be noted that industry engagement remains positive. Due to the engagement guidelines, a considerable amount of milestones will not be complete until October & November due to industry involvement. ​

## Slide 4: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Environments & Release Mgt. | Overall RAG Green. Environments plan being updated in line with latest test plan, however we are mindful that further Switching Programme external CR’s are being delivered and will need to understand these impacts. SIT non functional environment has been delivered.
 |  | Service Management | Overall RAG is Green. Internal workshops have been arranged to cover the outstanding questions for the core processes outlined by the Switching Programme. We are working through the CSS traceability matrix to align to the SPTL matrix which will provide a view of a) which system is impacted b) Is it a new service or a change to an existing service c) which document will be impacted and d) which stage gate the document will need to be completed by. Once analysis completed, transition lead will work with each workstream to ensure plans are updated accordingly.
 |  | Gemini | Overall RAG is Green. Continuing to work closely with the test stream to ensure that all Gemini triggers are tested successfully before testing with NGIT commences. ​ A three phased approach has been agreed for NGIT commencing on 15/06 and completing following the validation of the monthly files on 03/08. ​There are ongoing conversations around when Gemini UAT will take place, along with the transition to the Gemini ECP environments.
 |  | Batch | Overall RAG is Green.​ Good progress made on testing the Gemini triggers. A 3 phased approach has been agreed for NGIT commencing on 15/06 and completing following the validation of the monthly files on 03/08. ​Some updates to the Control-M baseline document have been identified.
 |  | Secondary APIs | Overall RAG is green following re-baselining. ​Inbound PO testing complete. Inbound and Outbound Azure testing complete and handed over to TCS Outbound PO build. Outbound BRR interface build on track to complete by 29/05​.
 |  | Reporting | Overall RAG is Green. Reporting activities are have been re-planned as the team is focused on completing outstanding report investigation work.​. The Data Team have investigated the remainder 3 reports which may be impacted under switch type/switch view/switch status. The findings on the Elected Shipper report shows it has no potential impact as per CSSC changes. Project Team to ascertain this position with the Business.​The Workstream may be closed down based on the output of the report findings currently being carried out.​
 |  | DES & API | Overall RAG is Green. DES NFR (DES3) solution has been completed on plan and passed over for SIT readiness and NFR testing. Architectural session completed and draft high-level plan and resource profile in progress​.

## Slide 5: Key Programme Risks (1/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62377 |  | Data Migration | There is a risk that Xoserve may not be ready for DM non functional testing on time because of lack of clarity of Overall programme plans for environments, testing and data leading to insufficient time allowed for preparation | Xoserve to engage with the SI on this risk | New proposed dates for non functional test start look quite tight against completion dates for SIT NF. This is to be investigated by the SI | 07/08/20
62444 |  | Programme | There is a risk that there are inconsistencies between and within certain design documentation from CSSP and SI, for example the CSS Inteface Specification and the Data Migration Solution design, because of failings in design solution, document creation, quality control, review and consistency checks leading to rework in one or multiple workstreams, most likely Data migration or API delivery in order to correct any mis-alignments once a consistent and coherent design has been properly defined. | SI to identify discrepancies and then agreement to be reached on which area will change to align to common data types. | Weekly meeting held with SI on 10/6, and this was discussed. Programme advised that a separate meeting held with SI Data PM where Xoserve advised that it still has concerns. Xoserve SPOCs looking to hold internal discussions and provide an update. | 30/06/20
62684 |  | Programme | There is a risk that SIT testing timelines will slip further (currently running with a 4 week slip) because of the significant number of defects that are currently open with Landmark leading to further slippages to subsequent phases and incurring additional costs for Xoserve (resources, supplier costs & environment run costs) along with the potential of invalidating environment re-use planned currently. | Escalate to the SI to ensure re-plan activities take into consideration delays to SIT so that upcoming phases are planned appropriately | Awaiting confirmation from SI on SIT and SIT NFR revised timelines | 31/07/20
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | This has been raised at the testing workgroups as well as discussions with the SI. Awaiting a response from the SI | 31/07/20

## Slide 6: Key Programme Risks (2/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62326 |  | Service Management | There is a risk that Service Design and Service Management processes are being tested before the E2E testing of CSS is complete (or even started) because Operational Testing is not being re-planned alongside the re-plan of the UEPT and E2E test phases leading to the possibility of additional test cycles being required at later stages of the programme to cover potential gaps that will be uncovered via market participant testing and as a result additional costs to be borne by Xoserve (and other existing service providers) | Raise with DCC & SI to understand mitigation strategy | DCC have taken away an action to look at the risk. Awaiting update from DCC. | 31/07/20
62448 |  | Data Migration | There is a risk that DMT cycle 1 will not expose potential differences in PUIs interpretation of the solution design because these differences will only be found through full low level industry testing, and DMT Cycle 1 is likely to be replanned to include only high risk elements of the solution, due to time constraints. leading to avoidable defects arising in SIT and the subsequent rework required by one or both parties. | Confirm with SI the correct version of this document and support them in improving the version control in future | Xoserve have been advised by the SI that the CSSP is standing up a “BLOG” to allow PUIs the ability to review any changes/updates that are made in the ‘Developer Portal’. Xoserve are still awaiting an update/communication when this will be “live”. | 26/06/20
62483 |  | Data Migration | There is a risk that DMT cycle 1 will not expose potential differences in PUIs interpretation of the solution design because these differences will only be found through full low level industry testing, and DMT Cycle 1 is likely to be replanned to include only high risk elements of the solution, due to time constraints. leading to late discovery of defects in cycle 2 and 3, with limited time to resolve and restest | Raise risk with SI for consideration | To be monitored through DMT | 26/06/20
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This RAID item will be kept open for monitoring during SIT | 30/06/20

## Slide 7: Key Programme Risks (3/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | This RAID item will be kept open for monitoring during SIT. | 30/06/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 30/06/20
62764 |  | Testing | There is a risk that the Ofgem Switching Volumetrics specified in the CSS NFRs may be outdated/inaccurate, because Ofgem has made a volumetric assumption based on historic numbers and this assumption may be incorrect. PERF060 specifies that the average number of daily switching requests (gas and elec) is 42300, and peak number of daily switches (gas and elec) is 281,600. From metrics collected in Xoserve, average daily gas switching requests are around 90,000 during the week, and this shows an increasing trend, leading to a situation where the solution being developed for CSS, is being built and tested for a lower set of volumes than will actually be encountered when the system goes live. Failure upon going live due to excessive switching loads will incur additional financial and time costs. | A design issue should be raised in JIRA, and reviewed by the Ofgem Design Review Board | Risk raised with SI, when reviewing the NCT-0017 SIT NF test document. SI suggested that a Design Issue be raised in Jira, Xoserve are progressing this. | 31/07/20
62747 |  | Programme | There is a risk that SI working groups such SI Transition Group & Technical Data working group are working in silo because of the way working groups are set up and co-ordinated leading to conflicting assumptions and decisions being made by different working groups. | Escalate to the SI & Ofgem via working group discussion to bring together related workgroups or ensure there are feed-ins between workrgoups | This was raised at the SI Transition Group on 10/06. Ofgem also acknowledged this concern. The SI have taken an action away to work this through | 31/07/20

## Slide 8: Key Programme Risks (4/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62748 |  | Programme | There is a risk that the later test phases such as DMT Live Rehearsals, Transition Testing and Operational Testing are not sufficiently defined or planned with clear understanding of the scope or the associated roles & responsibilities of participating industry parties because the SI have been working predominantly on the near term plan without taking into consideration the scope and objectives or the later phases | Escalate to the SI for addressing as part of the re-planning exercise | This was raised at the SI Transition Group on 10/06. Ofgem also acknowledged this concern. The SI have taken an action away to work this through | 30/06/20
62758 |  | Data Migration | There is a risk that DM Non-functional scenario and script population may not be completed in the allocated time because the timing clashes with DMT functional and the same resources are required for both leading to delayed completion of scripts for DM NF | Discuss with SI | To be escalated for consideration | 08/07/20
62682 |  | Data Migration | There is a risk that DMT will not complete on time because of extremely tight schedule | Risk raised with the SI prior to the start of DMT. The SI reported at SI-TDG that the schedule would be reviewed, but this has not happened, or the outcome has not been implemented. DMT is currently on day 2 and is significantly behind schedule | Cycle 1 to be extended by 1 week, reducing the reset window to 1 week. Confidence that cycle 2 will complete in the time allowed is low | 26/06/20
62685 |  | Data Migration | There is a risk that REL Cycle 3 data may not be provided in time, if the deadline date of the 16/09 is re-affirmed as part of the overall replan, because of the lead time required to extract data, and limited access to datacentre during lockdown leading to inability to extract data copy from production | Discuss with SI, review revised plan | Awaiting revised plan or confirmation from the SI that this milestone is to be removed | 16/09/20

## Slide 9: Key Programme Risks (5/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Discussions are ongoing with DCC as part of the monthly Stakeholder sessions as well as detailed sessions (dates to be agreed with DCC). Current assumption is that Xoserve's existing SLAs will continue to hold until notified otherwise by Ofgem (potentially via REC consultations) | 31/07/20
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | This continues to be actively monitored and managed - no changes to the status has been identified that could alter the probability or impact. Xoserve's activities continue to be on track to deliver to plan | 30/09/20
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | We have now received copies of the revised processes which we will review internally. Have requested overview/summary of changes from DCC. | 17/06/20
55572 |  | Network | There is a risk that Market Participants may not have sufficient time to procure and provision IX , if they choose the IX option for comms network connectivity, because of lead times for hardware, software and installation into data centres. Leading to lack of readiness on the part of Market Participants for UEPT in April 2020. Xoserve request that SI / DCC engage with Market participants as early as possible. | Raise with SI / DCC, to request early engagement with Market Participants and review additional MAD milestones as they become available. | Awaiting update on progress of Ofgem CR | 30/06/20

## Slide 10: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62485 |  | Data Migration | The PHID defines REL logical status and language as optional data items, however the DM validation catalogue shows them as mandatory. Xoserve have coded these as mandatory, and they are part of a composite key and so raised a Sev1 defect in smoke testing on receipt of a data file which did not contain the data expected. There is disagreement between parties over the correct definition of the data items which needs to be resolved in order for DMT to proceed. | TCS to develop and deploy a defect fix | 17/6 - Defect fix underway and on track | 29/06/2020

## Slide 11
High Level Plan