## IP - For Approval - Design
UK Link Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4989 | N/A | Online End to End Credit Interest Process - IIS File Format Change | 2605.1 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | [5 empty] | 2020-07-08 | 04/07/2020 MiR7
5116 | N/A | Domestic Report - Must Read Prenotification | 2605.2 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | [5 empty] | 2020-07-08 | Adhoc TBC
4922 | N/A | CSSC Shipper BRD | 2606.1 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | [5 empty] | 2020-07-08 | CSS Release
N/A | N/A | UK Link File Formats CSS Consequential Change | 2606.2 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | [5 empty] | 2020-07-08 | CSS Release
N/A | N/A | CSSC Code of Connections | 2606.3 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | X |  |  |  |  | 2020-07-08 | CSS Release | Information only
N/A | N/A | Query APIs Technical Specification Secondary API Error Handling Strategy | 2606.4 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | X |  | X |  |  | 2020-07-08 | CSS Release
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Implementation Plan - Approved last meeting
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4989 |  | Online End to End Credit Interest Process | 2587.2 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X |  |  |  |  | 2587.2 - MT - JR | 2020-06-10 | 04/07/2020 MiR7 | We received three approval responses
5036 |  | Updates to must read process | 2587.3 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 |  | X |  |  |  | 2587.3 - MT - JR | 2020-06-10 | 04/07/2020 MiR7 | We received three approval responses and one rejection response.
5065 |  | Addition of Email Address to DES Last Accessed Report | 2587.4 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X | X |  |  |  | 2587.4 - MT - JR | 2020-06-10 | 04/07/2020 MiR7 | We received five approval responses.
N/A |  | UK Link File Formats CSS Consequential Change | 2588.1 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X |  |  |  |  | 2588.1 - MT - JR | 2020-06-10 | CSSC | We received one approval responses
N/A |  | UK Link Settlement Data API Design Specification | 2588.2 - MT - JR | 2020-05-18 | 2020-06-02 | 2020-06-05 | X |  |  |  |  | 2588.2 - MT - JR | 2020-06-10 | CSSC | We received one responses for clarifiction
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
| Internet routing for UKLink | 2020-06-26 | TBC | 2020-06-27 | TBC | This is the cutover of the Internet routing for UKLink, the outage will be on the weekend and the impact will be minor, UKLink will be unable to be accessed and unable to send or receive files to corresponding systems during the maintenance window as the application is switched from our Legacy DC to TCS ECP. | 2020-06-10
4550 | Gemini | 2020-07-05 | 3:00 | 2020-07-05 | 17:00 | In order to complete the Gemini Re-Platforming (GRP) project implementation, an extended outage will be required on the Gemini system on 5th July 2020. Provisional timescales for the GRP implementation are as follows: Gemini Maintenance Window: 03.00 to 5.00 Extended outage: 05.00 to 13.00 In the event of a rollback an additional outage will be required from 13.00 to 17.00 If a change is identified to the above timings, a further notification will be issued. The GRP team will work with the National Grid and Xoserve business to ensure appropriate measures are in place to manage all impacts due to the extended outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 2019-12-11
4970 | DCC | TBC | TBC | TBC | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | 2020-05-13
4970 | DCC | TBC | TBC | TBC | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-05-13