## IP - For Approval - Design
UK Link Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4989 Part B | N/A | Online End to End Credit Interest Process - IIS File Format Change | 2634.2 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | TBC | 2020-08-12 | Minor Enhancement Potencial Oct 20 | We received three approval responses
5047 | N/A | Seasonal Normal Review Implementation in SAP ISU | 2634.3 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | TBC | 2020-08-12 | Adhoc TBC | We received three approval responses
N/A | N/A | UK Link File Formats CSS Consequential Change | 2635.1 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X |  |  |  |  | TBC | 2020-08-12 | CSSC | No reps received
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Change Management meeting, UK Link Release Dates and Non Business Days | 2634.1 - MT - JR | 2020-07-13 | 2020-07-27 | 2020-08-03 | X | X | X | X |  | TBC | 2020-08-12 | 2021 | We received three approval responses

## IP - Approved Last Meeting
UK Link Implementation Plan - Approved last meeting
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4376 | N/A | Gas Transmission Charging Regime | 2601.1 - MT - PO | 2020-06-05 | 2020-06-19 | 2020-07-26 | X |  | X |  |  | 2612 - MT - PO | 2020-07-08 | Adhoc 01/10/2020 | We received one approval responses
4989 | N/A | Online End to End Credit Interest Process - IIS File Format Change | 2605.1 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X |  |  |  |  | 2630 - KL - JR | 2020-07-08 | 04/07/2020 MiR7 | We received two approval responses for option 1
4922 | N/A | CSSC Shipper BRD | 2606.1 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X |  |  |  |  | 2630 - KL - JR | 2020-07-08 | CSS Release | We received two responses for clarifiction
N/A | N/A | UK Link File Formats CSS Consequential Change | 2606.2 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X |  |  |  |  | 2630 - KL - JR | 2020-07-08 | CSS Release | No responses received
N/A | N/A | CSSC Code of Connections | 2606.3 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | X |  |  |  | 2630 - KL - JR | 2020-07-08 | CSS Release | No responses received
N/A | N/A | Query APIs Technical Specification Secondary API Error Handling Strategy | 2606.4 - MT - JR | 2020-06-15 | 2020-06-29 | 06/072020 | X | X |  | X |  | 2630 - KL - JR | 2020-07-08 | CSS Release | No responses received
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
4550 | Gemini | 2020-08-08 | 3:00 | 2020-08-08 | 8:30 | Gemini Disaster Recovery Test 2020 There is a planned Disaster Recovery test on the Gemini system on 8th and 9th August. This is an annual activity in order to confirm the capability to rehost services to an alternative data centre location should there be a catastrophic failure within the primary data centre. There will be an outage on Gemini 8th August 4am-8.30am where the system will be unavailable whilst the test is in progress. During the initial activity we will be recreating the scenario whereby the Gemini system is unusable within the primary data centre and therefore brought up within the secondary data centre. Note that the system will operate normally during times where there is no outage. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 2020-07-08
4550 | Gemini | 2020-08-09 | 3:00 | 2020-08-09 | 8:30 | Gemini Disaster Recovery Test 2020 There is a planned Disaster Recovery test on the Gemini system on 8th and 9th August. (please see details above). During the second activity we will be recreating the scenario whereby the Gemini system is recovered to the primary data centre. There will also be an outage on Gemini 9th August 5am-8.30am where the system will be unavailable whilst the test is in progress. If you have any concerns or any questions, please contact the project team on box.xoserve.geminire-platform@xoserve.com | 2020-07-08
| EFT | 2020-10-09 | 5:00 | 2020-10-11 | 7:00 | As part of our Xoserve Annual Programme of Resilience and Disaster Recovery (DR) testing , Xoserve will be managing and conducting an end-to-end 2020 Enhanced File Transfer (EFT) DR test to prove and confirm the procedures, resilience and capability of the newly hosted EFT services at our new Data Centre’s. The activity will be carried out over three days from October 9th, 10th and 11th 2020 during the daily UK-LINK Maintenance window between 05:00 to 07:00 UK BST. Please be aware that the confirmed EFT DR Contingency Dates have been scheduled to be carried out on the following week over three days during the 05:00 to 07:00 UK BST UK-LINK Maintenance window on October 16th, 17th and 18th 2020. Any Customer IX files that would be processed by EFT during this window will remain safely in your respective IX Folders, once EFT is back online, all IX file transfers will be synced and issued. | 2020-08-12
| SD+ | 2020-09-26 | TBC | 2020-09-27 | TBC | This is the implementation Service Now (SNOW) , the replacement for SD+, the outage will be on the weekend to cause less impact to the industry. SD+ will be unavailable to raise tickets but users will be able to still raise these via the normal number. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-08-12
| SD+ | 2020-10-31 | TBC | 2020-10-01 | TBC | This outage is to allow for our instance of SNOW to be integrated with WIPRO SNOW. This will be on the weekend to cause less impact to the industry. SD+ will be unavailable to raise tickets but users will be able to still raise these via the normal number. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-08-12
| SD+ | 2020-12-14 | TBC | 2020-12-15 | TBC | This outage is to allow for our instance of SNOW to be integrated with TCS SNOW. This will be on the weekend to cause less impact to the industry. SD+ will be unavailable to raise tickets but users will be able to still raise these via the normal number. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-08-12
4970 | DCC | TBC | TBC | TBC | TBC | This is the cutover of the production environment for DCC the outage will be on the weekend, the impact to the industry will be minor and that any nominations/ confirmations that utilises the Data Communications Company (DCC) as a background application will be unable to send or receive files during the maintenance window as the application is switched from our Legacy DC to TCS ECP. Subject to change due to multiple inflight changes and dependencies on suppliers. | 2020-05-13
4970 | DCC | TBC | TBC | TBC | TBC | This is the outage for DCC DR testing this will be on the weekend, the impact to the industry will be minor and that any application that utilises DCC as a background application will be unable to send or receive files during the maintenance window will DR testing is conduct. Subject to change due to multiple inflight changes at the time, but only by a week. | 2020-05-13