## Slide 1: CSSC Programme Dashboard
August 2020

## Slide 2
Programme Update
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme is Amber due to Switching programme re-plan and the number of outstanding defects from SIT Integration sequence preventing Xoserve’s progression of SIT scenarios. RTG actions include active analysis and feedback of the CSSIP as and when the updated versions are received and continued feedback and interaction with the SI to understand when the defects are likely to be released into SIT. | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Key Progress & Milestones (Last Month)
Key Programme Updates: All key external milestones have been met Programme Planning: SI have issued a revised MAD log (v1.1), and the CSSC team have challenged the log from a number of areas, including planned milestone dates, environments and resource impacts. The programme is included in discussions on phases such as UEPT/E2E, Transition and Operational Testing. Revised Programme plan is due to be released to parties for a second round of review on 31/7. The revised plan is expected to be baselined in September. External Testing: SIT Integration sequence has completed, with 440 scripts passing and 41 failures. A number of defects across parties remain outstanding. External NFR: SI have commenced SIT NFR execution with Landmark undertaking mock testing to establish baselines. Xoserve will commence connected tests in early September based on current plans. Programme continues to be concerned that commencing NFR SIT in July, without having undertaken an adequate level of SIT Functional testing in potentially adding the risk of re-test down the line. External Data DMT: Cycle 1 completed and Cycle 2 of DM testing in progress and reporting ahead if schedule. Xoserve team continue to be ahead of plan.The SI are planning to include “Delta’s” into Cycle 2, if the schedule permits. External Data NFT: Detailed cycle planning (1st draft) completed. Detailed planning will continue alongside the overall programme plan review. Internal Activities: Internal Testing including SIT & UAT is ongoing for functionality tested in Market Trials. All activities continue to be progress to plan |  |  |  | DMT: Cycle 1 complete, Cycle 2 started External NFR: Smoke test complete, CSSP internal tests started External SIT: Integration Sequence testing finished with 0 Xoserve defects Internal SIT: Phase 3 completed Programme: 1st review of MAD log complete. Gemini & Batch: UAT Completed CRs: Delivery and IA’s continue Internal NFT: Complete Performance Testing Phase 2A (ETC 31/7)
 |  |  |  | Upcoming Activities & Milestones (Next Month)
 |  |  |  | DMT: Complete Cycle 2 External SIT: Continue External SIT Internal Test: Continue UAT Phase 1 Internal NFT: Commence Performance Testing Phase 2B Service Mgmt: Obtain approval on Xoserve integration with DCC Service Now and continue internal SM activities DES: Continue DES Re-write activities Secondary APIs: Progress design, build and test External Audit: Expleo Test audit

## Slide 3: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Market Trials | Overall the workstream is amber as Market Trials is being re-assessed in light of the Programme re-plan and the lengthening of the SIT phases, which potentially poses a risk to CSS code stability.
 |  | Performance Test and OAT | Overall status is amber until the last concern area is assessed and addressed. Performance Test has further progressed. Testing so far has yielded postiive results. We continue to test around the 5 pm Gate Closure constraint to ensure all possible performance bottlenecks are adequately addressed before sign off.
 |  | DES, API | DES Full Re-platform (DES4) Build in progress. Queries, data transformations and replication tasks underway. Scope is showing amber as original DES requirements are still being confirmed and reviewed. A resource has been allocated to assist with completing the gap analysis and expanding the requirements previously defined if required
 |  | UK Link | Overall status is Green. A number of CRs are emerging from the central programme. These are being impact assessed against baseline design and delivered as they progress through the governance
 |  | Data Provision | Replanned dates for the transfer of UEPT production data to the SI /Landmark is still targeted for December 2020 . Awaiting confirmation from SI on whether delivery plan for Reg ID and REL data for UEPT will align with the December date.
 |  | Reporting | The Reporting Team have completed investigation on the remaining 3 reports which may be impacted under switch type/switch view/switch status. Internal CR to be raised to include switching data into Data Delivery platform & SAP BW
 |  | Environments | RAG is green. Environment requirements have been re-aligned with latest plans from SI.

## Slide 4: Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Migration | Overall status is Green: Schedule is AMBER as a number of industry CRs have been raised . Initial attempts by the SI to fast track in time for DMT cycle 3 have not been successful and it is now unlikely that CR-D016 (Registration ID), CR-D024 (reconciliation ordering) and CR-D026 (PHID Alignment) will be approved in time.
 |  | Business Change | Internal activities to bring wider Xoserve stakeholders up to speed with impacts as a result of CSSC continue..
 |  | Gemini | The overall status is green. However schedule is amber until details of the Ofgem Programme re-plan are confirmed. NGIT SIT phase completed successfully on 03/07 and the Exit Report has been approved. UAT has commenced and the test cases have been signed off
 |  | Batch | The overall status is green however schedule is amber until details of the Ofgem Programme re-plan are confirmed. SIT Exit Report and the Batch jobs will be mentioned in the Internal SIT Exit Report produced by the Test workstream. UAT for both Control-M and EFT has started. The SIT Evidences for Control-M and EFT have been approved.
 |  | Testing - SIT | Completed Phase III testing and preparation has started for phases IV and V - Resource is amber due to the ongoing delays to External SIT - revised MAD log has been received and review comments provided to the SI. UAT testing has commenced and daily progress reports are being created.
 |  | Service Management | Draft re-plan produced based on revised MAD log and will be further reviewed through the iterations of the planning cycle. Plan in place to obtain approval on Xoserve integration with DCC Service Now with DCC. work continues to complete the latest DCC questionnaire to be submitted by the end of the month.
 |  | Secondary APIs | Overall status remains Green. Priority remains on authorization and authentication in API and business rules/validation mapping and wiring up to data service API. Customer user journey deliverable out for 1st review. This review is aligned to the agile sprint delivery governance. Walkthrough of the current User Management process planned to ensure clarity between new and current processes.

## Slide 5: Key Programme Risks (1/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62448 |  | Data Migration | There is a risk that Xoserve's solution delivery is incompatible with the CSS being delivered by Landmark because of poor version control and ambiguity as to which is the live version of the CSS Interface Design Specification that the CSSP have built to, leading to avoidable defects arising in SIT and the subsequent rework required by one or both parties. | Confirm with SI the correct version of this document and support them in improving the version control in future | SI have put a formal request into Landmark to start to provide a forward sprint schedule which will start to give more detail on what is contained in future development outputs. Although a step forward, this still does not mitigate the current risk for Xoserve. | 31/07/20
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | This risk is still very relevant, particularly since SIT NR is currently scheduled to complete in November (ahead of SIT functional end in December). Increasing the probability as the planning assumptions underpinning the SIT functional testing plans are predicated on CR-30 approvalI | 30/09/20
62764 |  | Testing | There is a risk that the Ofgem Switching Volumetrics specified in the CSS NFRs may be outdated/inaccurate, because Ofgem has made a volumetric assumption based on historic numbers and this assumption may be incorrect. PERF060 specifies that the average number of daily switching requests (gas and elec) is 42300, and peak number of daily switches (gas and elec) is 281,600. From metrics collected in Xoserve, average daily gas switching requests are around 90,000 during the week, and this shows an increasing trend, leading to a situation where the solution being developed for CSS, is being built and tested for a lower set of volumes than will actually be encountered when the system goes live. Failure upon going live due to excessive switching loads will incur additional financial and time costs. | A design issue should be raised in JIRA, and reviewed by the Ofgem Design Review Board | Volumetrics analysis and response in progress. | 31/07/20

## Slide 6: Key Programme Risks (2/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62748 |  | Programme | There is a risk that the later test phases such as DMT Live Rehearsals, Transition Testing and Operational Testing are not sufficiently defined or planned with clear understanding of the scope or the associated roles & responsibilities of participating industry parties because the SI have been working predominantly on the near term plan without taking into consideration the scope and objectives or the later phases | Escalate to the SI for addressing as part of the re-planning exercise | This has been highlighted as part of various forums as well as part of the MAD log review. Xoserve have also been provided with an opportunity to present our alternative options to drive efficiencies into the plan. | 28/08/20
62758 |  | Data Migration | There is a risk that DM Non-functional scenario and script population may not be completed in the allocated time because the timing clashes with DMT functional and the same resources are required for both leading to delayed completion of scripts for DM NF | Discuss with SI | Probability reduced as scenario work completed, and work has started to draft scripts. | 28/08/20
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This RAID item will be kept open for monitoring during SIT | 31/08/20
62897 |  | Data Migration | There is a risk that Xoserve may not be able to provide Landmark with data for UEPT on time leading to late delivery of data and potential delay to the start of UEPT | Review plans, discuss with programme | Xoserve are hoping to understand from Stuart Chalmers at test review meeting when Landmark are going to provide REL and REG ID. | 31/07/20

## Slide 7: Key Programme Risks (3/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62682 |  | Data Migration | There is a risk that DMT will not complete on time because of extremely tight schedule | Risk raised with the SI prior to the start of DMT. The SI reported at SI-TDG that the schedule would be reviewed, but this has not happened, or the outcome has not been implemented. DMT is currently on day 2 and is significantly behind schedule | Probability reduced in light of revised approach from SI. Exit documentation is being completed in parallel to the end of testing and cycle 2 and 3 approach has been moved to a more risk based approach. | 28/08/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | This RAID item will be kept open for monitoring during SIT. | 31/08/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 31/08/20
62747 |  | Programme | There is a risk that SI working groups such SI Transition Group & Technical Data working group are working in silo because of the way working groups are set up and co-ordinated leading to conflicting assumptions and decisions being made by different working groups. | Escalate to the SI & Ofgem via working group discussion to bring together related workgroups or ensure there are feed-ins between workrgoups | This risk continues to be monitored. Awaiting confirmation via working group artefacts that considerations across working groups are being considered in planning (particularly within the Transition working group) | 31/08/20

## Slide 8: Key Programme Risks (4/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62830 |  | Data Migration | There is a risk that we may not be able to access the datacentre in order to connect the databox, to move the 31st prod cut to the azure environment eading to Xoserve being unable to load the data copy onto the environment to begin extract work, and test preparation | Escalate with TechOps to explore options for gaining access to the data centre. | Continues to be a risk until access is confirmed but as lockdown easing continues the probability of this risk is reducing. | 14/08/20
63061 |  | Data Migration | There is a risk of delays in transferring the production data copy from the databox to Azure by Microsoft leading to delays in provision of data extracts for Landmark for UEPT | Discuss MS service levels and agreements with Steve Concannon | Discussions underway with our Microsoft account team | 30/10/20
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Update requested within the July forum. Advise that meetings were arranged between DCC & Ofgem to discuss and would provide an update as soon as possible. | 07/08/20
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | Xoserve's activities all continue to be on track to the delivery plan and future dates are being aligned to the replan | 30/09/20

## Slide 9: Key Programme Risks (5/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | Within the July forum, it was advised that the latest process maps would be issued to all parties to review and provide feedback. These were issued on 21st July and included non core processes. Target review date set by DCC is 21/08/20 - this will be ambitious to review all the documents that they have sent (10 in total) by 21st however, we will focus on the core processes initially. | 31/08/20
63062 |  | Data Migration | There is a risk that REL and RegId data may be provided late in February / March because of 2 weeks programme shutdown at Landmark / SI over Christmas leading to shortened timeline for loading the data or a delayed load | Review with SI | Awaiting confirmation of eta on REL and RegID data for UEPT from Stuart Chalmers | 11/12/20

## Slide 10: Key Programme Issues
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62919 |  | Programme | SI Functional Re-plan assumptions state " It is assumed that each PUI has a backup of their environment and data and can restore the configuration within 1 working day." Xoserve requested clarification from the SI about the maintenance windows and we were assured no Environment or Data refreshes would be required. Hence we have not factored this activity into our planning and to do so would require extra cost and the timeline would be considerable longer. | Raise with SI. SI to review and respond. | No formal confirmation has been received from Alan Matthews but the issue and Xoserve's position is clearly understood. This issue will remain open until Chan and Amerjeet can pin down confirmation from SI. | 31/07/20

## Slide 11
High Level Plan