## Slide 1: Minor Release Drop 8 Update

## Slide 2: XRN5225 – Minor Release Drop 8 - Status Update
28/09/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 3 changes for XRN5225 to be implemented. The proposed implementation date is 21st November: XRN5181 - Acceptance of Consumption Adjustments where meter is removed XRN5174 - Agreed FINT Replacement Reads incorrectly triggering rolling AQ calculation XRN5118 - Change how the actual MR data is populated in UK Link Design Phase completed Build Phase in progress, planned completion 2nd Oct Test Phase to start w/c 5th Oct |  |  | 
Risks and Issues | No major risks to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 

## Slide 3: XRN5225 – Minor Release Drop 8 Timelines
Key Proposed Dates (not yet baselined):
Impact Assessment Complete – 28/8/20
Design Complete / signed off – 11/09/20
Build Complete – 02/10/20
Testing Complete – 14/11/20
Implementation Complete – 21/11/20
PIS Complete – 05/12/20