## Slide 1: CSSC Programme Dashboard
October 2020

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme continues at Amber due to the inflight Switching Programme re-plan, outstanding issues of SIT NF remaining paused (expected to commence shortly) as well as the delays experienced within SIT Functional testing. In addition, there are a number of CRs in the pipeline that has the potential to impact programme costs and delivery timelines RTG Actions include review and feedback of the latest version of the programme plan (expected to be issued 25/09) and working with the SI to reduce impacts on Xoserve where possible | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Key Progress & Milestones (Last Month)
Key Programme Updates: All key external milestones impacting Xoserve, to date have been met. Re-Plan: The programme have reviewed the 2nd phase of Switching Programme Plan and have provided Xoserve’s Dependencies and Assumptions for incorporation into the next iteration of the Mad Log. The latest iteration of the Programme plan is expected to be issued for final consultation on 25/09 with a view to baseline by end October 2020. Change Requests: We have observed that one of the early Switching Programme CRs (CR-E01) was missing from CSS design. We have confirmation that Landmark is implementing this CR now. Additionally, we have requested confirmation that all previous CRs/REC requirements are incorporated within the CSS Design. External Testing: SIT Cycle 2 is underway currently, with some delays experienced at the central programme but with lower failure rates than forecast. Xoserve has had minimal defects to date. SlT NF testing is still on hold due to environmental issues within the central programme but there have been communications that it will resume for CSS on 25/09. Xoserve’s dates for rejoining this phase is yet to be clarified. Planning and preparation continues towards upcoming test phases such as UEPT, Transition and Operational Testing. External Data Migration Functional Testing concluded successfully with no outstanding defects. Xoserve completed our testing ahead of schedule. External Data Migration Non Functional Testing: Detailed planning continues. Due to the changes that are being reviewed by the wider programme, the CSSC team are not clear if this is impacted by the re-plan activities. Clarification is expected as part of the re-plan exercise. Internal Activities: Internal testing including SIT, UAT and Performance testing continue to plan. These are not expected to be impacted by the re-plan exercise CCMT: Xoserve continues engagement with industry, in relation to consequential market trials. Revised dates to be tabled with Ofgem and our customers following Switching Programme re-plan. |  |  |  | DMT: Cycle 2 & Cycle 3 complete External SIT: Cycle 1 testing finished with 3 Xoserve defects, all being fixed Internal UAT: Started – 50% complete Internal SIT: Phase 3 completed Programme: 2nd review of MAD log complete. Transition: after months of feedback from CSSC, SI have started to address our concerns CRs: Delivery and IAs continue Performance Testing: Peak of Peak trans/second achieved Internal NFT: Complete Performance Testing Phase 2A
 |  |  |  | Upcoming Activities & Milestones (Next Month)
 |  |  |  | DMT NFR: Planning and prep External SIT: Continue External SIT External NFR: Start Internal Test: Continue both SIT phase 4 and UAT Phase 1 Internal NFT: Continue Performance Testing Phase 2B DES: Continue DES Re-write activities and review Ofgem request for changes to DES. Secondary APIs: Progress DBT Transition: Transition planning – initial planning underway Costs: Continue cost analysis and control
Programme Update

## Slide 3: Amber Workstream Updates
Kirsty to update
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Provision | RAG is Amber. Schedule is Amber due to changing plans for UEPT. There is a strong dependency on the Switching Programme plan being agreed and re-baselined to allow Xoserve to plan effectively towards the Data provision requirements for both external test phases as well as Market Trials
 |  | Data Migration | RAG is Amber: Resource is amber due to the SI Data requirements which include significant data generation for DMT NF. Discussions are underway to determine how this can be achieved with minimal spend
 |  | Market Trials | Overall the workstream is amber as Market Trials is still being re-assessed in light of the Programme re-plan and the lengthening of the SIT phases, which potentially poses a risk to CSS code stability.
 |  | Performance Test & OAT | Overall status amber due to environmental issues delaying performance testing and dependency on Switching Programme re-plan for OT timelines. Average run completed successfully with secured active and background class 3 & 4 meter read loads. Scope of OAT is being agreed with a view to align to Switching Programme Operational Test (OT) requirements and internal Xoserve requirements. There also exists a dependency on the SI to clarify OT requirements in order for Xoserve to plan effectively.
 |  | UK Link | Overall status is Green. CRs emerging from the central programme continue to be assessed against baseline design and delivered as they progress through the governance
 |  | Environments | Overall status is Green, however there exists a dependency on the Switching Programme re-plan activity.
 |  | Secondary API | Design Build and Test activities continue to plan

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Internal Testing | Status remains Green (Internal Test Phases) as continuing to make good progress on User Acceptance Testing with 115 of 215 scripts passed. Resource remains amber as awaiting External SIT revised baselined plan from the SI. UAT testing is in progress and on track, Secondary API Test Preparation is in progress and analysis of scope of testing underway. SME workshops carried out, follow up session to be planned. UEPT Test Planning in progress, SIT Phase 2 and UAT Assurance has started. Phase1 IS assurance is 80% complete. External SIT “Initial Integration Sequence”, “TW1 and 2” test execution phases are running in parallel.
 |  | Service Management | DCC ServiceNow integration is being cost-benefit assessed. All non-core processes have been reviewed and feedback issued to the DCC. Next steps will be to agree 1-2-1 sessions to address feedback and validate our mapped processes. Internal sessions to review the non core processes have been scheduled. PID is out for review.
 |  | Batch | Overall status is green however schedule is amber until details of the Ofgem Programme re-plan are confirmed. UAT for both Control-M and EFT have completed and the team are preparing the evidences. TCS are running adhoc jobs for the UAT team when requested. The AMT job setup is in progress as requested. The Control-M Gateway issue has occurred again and the team are meeting to analyse next week. Planning of the configuration of the Gemini Control-M Production dump is ongoing.
 |  | Gemini | Overall status is green however schedule is amber until details of the Ofgem Programme re-plan are confirmed. A Production defect has been identified during UAT on one of the Gemini triggers. A meeting is taking place this week to discuss the defect with National Grid and agree next steps to resolve the defect. A data refresh has taken place on ECP UT1. Once the code merge activity has taken place, the transition testing can take place ahead of testing the final triggers for UAT on 01/10.
 |  | Reporting | Overall RAG is Green however schedule is amber due to additional work required to raise a CR plus the additional report identified. Re-planning taking place. Working with the Portfolio Governance Team to raise the CR for the ETL job changes to be applied within BW. As the programme Go live moves out and the business develop new reports, we are looking at creating a document for the business which would detail the new switch document types that need to be considered when any new reports are being created.
 |  | REC | The overall status of the REC project is currently green with Capture Stage in progress and approach being formed. Draft REC Schedules under review with Mike Payley reviewing the REC Faster Switching Schedules (7 out of 18). Meeting scheduled 7th Sep to discuss Ofgem letter regarding Display of Pending Registration Data on the Data Enquiry Service (DES). REC strategy options analysis work underway. Capture Document drafting in progress. External RECCo alignment meeting scheduled 4th Sep to feedback on RECCo. Framework Agreement for adoption for CDSP Further Services. External: Ofgem RDUG hosted 6th August. Key CSS discussion point was Address Management validation against Enquiry Service.

## Slide 5: Key Programme Risks (1/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
63538 |  | Programme | There is a risk that all CRs (particularly those raised in the early phases of the Switching Programme), may not been incorporated into design and build by the relevant parties because these CRs might have not been incorporated correctly into requirements leading to additional efforts required to incorporate these CRs and testing through the relevant test phases (and as a subsequence delays to already delayed timelines. | Escalate to the SI to revisit the traceability exercise to identify any gaps (if any) and reflect the impacts of these CRs on the plan | Awaiting response from SI | 30/10/20
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | Xoserve believes that testing will resume in October and Xoserve activities commence later in the month. Because SIT F is now nearing completion of cycle 1 the probability of this risk is reduced. | 21/12/20
63411 |  | Transition and Cutover | Lack of adequate Transition Test cycles within the Switching Programme Plan | Raise with the SI & Ofgem via the established forums Ensure that Xoserve internally tests our Transition plan adequately even if this is without involvement from external stakeholders (with as robust assumptions as possible) | Meeting held with SI and an initial plan was presented. Xoserve are digesting what was presented | 30/10/20

## Slide 6: Key Programme Risks (2/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | A further impact of the lack of the E2E process maps has come to light with CSS confirming that CR-E01, a key Xoserve CR has not been incorporated into CSS design. | 30/10/20
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | This was discussed within the September forum. DCC have provided their view of expected response and resolution times - we will now carry out an exercise to validate against Xoserve’s targets and start the discussions with DCC and the internal teams within Xoserve. DCC suggested that the resolver group will have the time minus response time for resolution. However, CAPGemini suggested that the SLA from a service provider would only be applicable once the ticket is assigned to them. | 25/09/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | A further impact of the lack of the E2E process maps has come to light with CSS confirming that CR-E01, a key Xoserve CR has not been incorporated into CSS design. | 30/10//20
62747 |  | Programme | There is a risk that SI working groups such SI Transition Group & Technical Data working group are working in silo because of the way working groups are set up and co-ordinated leading to conflicting assumptions and decisions being made by different working groups. | Escalate to the SI & Ofgem via working group discussion to bring together related workgroups or ensure there are feed-ins between workrgoups | Discussed with Amit at the SI. Amit has advised this is being raised with SI PMO and also to Sam on the action raised in June. | 30/09/20

## Slide 7: Key Programme Risks (3/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62748 |  | Programme | There is a risk that the later test phases such as DMT Live Rehearsals, Transition Testing and Operational Testing are not sufficiently defined or planned with clear understanding of the scope or the associated roles & responsibilities of participating industry parties because the SI have been working predominantly on the near term plan without taking into consideration the scope and objectives or the later phases | Escalate to the SI for addressing as part of the re-planning exercise | Risk remains open until re-plan has been fully reviewed and agreed internally.. | 30/10/20
62897 |  | Data Migration | There is a risk that Xoserve may not be able to provide Landmark with data for UEPT on time leading to late delivery of data and potential delay to the start of UEPT | Review plans, discuss with programme | Prod data copy now looks to be 20th Nov. Plans to be revised and risk re-assessed. | 20/11/20
63285 |  | Data Migration | Xoserve may not have data prepared in time for UEPT due to change in prod data approach | Review with SI | Revised date now 20th Nov. Although the date has not been confirmed, work must now start as the required 10 week lead time for a prod data copy has begun. | 28/11/20
63431 |  | Data Migration | Risk of additional cost of generating and loading high volumes of synthetic data into UK Link for DM NF | Review with SI | Xoserve are working through the options to provide costings. Awaiting outcome of tests on deltas run by Landmark to confirm the go live and T2 dates | 25/09/20

## Slide 8: Key Programme Risks (4/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This RAID item will be kept open for monitoring until the end of SIT phase 1. | 30/10//20
62830 |  | Data Migration | There is a risk that we may not be able to access the datacentre in order to connect the databox, to move the 31st prod cut to the azure environment eading to Xoserve being unable to load the data copy onto the environment to begin extract work, and test preparation | Escalate with TechOps to explore options for gaining access to the data centre. | No further update. Risk remains as local lockdowns may be imposed | 31/10/20
63061 |  | Data Migration | There is a risk of delays in transferring the production data copy from the databox to Azure by Microsoft leading to delays in provision of data extracts for Landmark for UEPT | Discuss MS service levels and agreements with Steve Concannon | Plan for prod data copy is expected to change. Risk downgraded until revised dates communicated - risk will then be re-assessed | 30/10/20
62942 |  | Programme | There is a risk that Xoserve systems will be out of sync with CSS during British Summer Time because CSSP intend to use UTC within the CSS solution and both UK Link and Gemini are believed to use BST leading to incorrect reporting of switches and all relevant data from Xoserve systems during the period where BST is one hour ahead of UTC. | Ofgem have now made a decision that BST will continue to be used across the gas industry so a CR is expected requiring Landmark to make the necessary changes to CSS. | Xoserve are keeping this risk open until the CR is raised and the design issue in Jira has been closed off accordingly. | 30/09/20

## Slide 9: Key Programme Risks (5/5)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
50199 |  | Programme | There is a risk that CSS Consequential may be unable to meet switching Programme timelines and end up delaying the overall Ofgem Switching Programme because of the fact that Xoserve consequential changes are complex and significant in scale, leading to potential delays to the Industry plan & reputation impact to Xoserve | Continued engagement with SI and other Switching Programme stakeholders to ensure that all inbound dependencies are met within expected timelines. | Xoserve's activities all continue to be on track to the delivery plan and future dates are being aligned to the Ofgem replan which should be baselined in September | 30/10/20
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | We have completed our review of the core processes and provided all our feedback to the DCC. As a result, an initial workshop has been scheduled for 23rd September with the DCC to start to work through our feedback and agree any next steps. We are also reviewing the non core processes and will provide our feedback by 18th September. We have already identified the need for a workshop to discuss Release Management in more detail - a request has been sent to the DCC. | 30/10/20

## Slide 10
High Level Plan

## Slide 11: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  |  | On Hold
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  |  | Not Received
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  |  | Not Received
Total |  | £0.00 |  | 

## Slide 12: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Approved - Internal CR Created
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £85,000.00 | 02/03/2020 | Withdrawn
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £250,000.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Awaiting Decision
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Awaiting Decision
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Awaiting Decision
CSS Change from UTC to Local Time | CR-D035 |  | 22/09/2020 | Pending PIA
Total |  | £565,293.00 |  |