## Slide 1: Amendment Invoice Update
14th October 2020

## Slide 2
Amendment Invoice Taskforce Update
Health – RAG |  |  | Return to Green Plan | 
Overall Status | Previous | Current | A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid November 2020. This will enable the Plan to return to green and the defect SLAs will be met. Dedicated team to progress defects The number of unique MPRNs with an exception has reduced to 29,813 – down from last month’s reported figure of 35,561. A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid November 2020 | 
Plan | Previous | Current |  | 
Exceptions | Previous | Current |  | 
Defects | Previous | Current |  | 
Executive Summary |  |  |  | Key Progress & Milestones (Last Month: September)
Key Updates: ASP file merge activities ensured the 40 MPRNS with mismatch were included in the relevant customer ASP files. All AML file delivered ahead of payment due date. Unique MPRNs in exception has reduced to 29,813 (last month’s figure = 35,561). Risks/Issues: Defects impacting the Amendment invoice continue to miss SLA. A dedicated Project Team has been assigned with the aim of clearing the backlog of defects by mid November 2020. This will enable the Plan to return to green and the defect SLAs will be met. The backlog of exceptions (although significantly reduced in recent months) means the exceptions SLA is not being met, meaning customers have reconciliations that are being excluded for their invoices. |  |  |  | ASP Mismatch file merge activities continue to ensure customers receive full supporting information for their LSP sites on invoice issue date. All AML files delivered to customers ahead of SLA.
 |  |  |  | Upcoming Activities & Milestones (Next Month: October)
 |  |  |  | Automation of exception resolution steps for specific MN09 scenarios. Work on resolving the backlog of defects continue – plan to clear backlog by mid Nov-20.

## Slide 3: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
GREEN
RAG Justification
40 MPRNs out of the 180,969 LSPs (0.2%) that were billed incurred an ASP mismatch.
40 unique MPRNs with ASP mismatch. File merge activities ensured mismatch data was included in ASP file issue on the invoice issue date.
All AML files were delivered ahead of the SLA.
 |  |  | ASP Mismatches |  | AML Mismatches |  | 
Billing Month | Billed Contracts | LSP Invoiced | Unique LSP MPRNs causing ASP mismatch | % of invoiced LSPs causing ASP mismatches | SSP Invoiced | Unique SSP MPRNs causing AML mismatch | % of invoiced SSP causing AML mismatches
Aug-19 | 9,977,884 | 230,802 | 254 | 0.11% | 9,747,082 | 208 | 0.00%
Sep-19 | 11,133,817 | 310,321 | 284 | 0.09% | 10,823,496 | 2,701 | 0.02%
Oct-19 | 11,067,074 | 252,181 | 855 | 0.34% | 10,814,893 | 9,235 | 0.09%
Nov-19 | 10,746,544 | 235,402 | 110 | 0.05% | 10,511,142 | 585 | 0.01%
Dec-19 | 9,907,903 | 227,508 | 133 | 0.06% | 9,680,395 | 2,019 | 0.02%
Jan-20 | 11,143,336 | 190,009 | 189 | 0.10% | 10,953,327 | 1,521 | 0.01%
Feb-20 | 10,672,939 | 206,203 | 151 | 0.07% | 10,466,736 | 247 | 0.002%
Mar-20 | 11,210,849 | 257,092 | 172 | 0.07% | 10,953,757 | 1,113 | 0.010%
Apr-20 | 10,308,100 | 249,620 | 120 | 0.05% | 10,058,480 | 4,582 | 0.046%
May-20 | 10,227,416 | 240,451 | 54 | 0.02% | 9,986,965 | 419 | 0.004%
Jun-20 | 9,897,048 | 183,092 | 48 | 0.03% | 9,713,956 | 191 | 0.002%
Jul-20 | 10,584,643 | 183,410 | 44 | 0.02% | 10,401,233 | 222 | 0.002%
Aug-20 | 10,334,318 | 180,969 | 40 | 0.02% | 10,153,349 | 146 | 0.001%

## Slide 4: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
AMBER
RAG Justification
Automation of exception resolution steps continuing to be worked upon – a number of codes have now been automated
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
29,813 distinct MPRNs currently have unresolved exceptions within our systems (as of 6th October 2020).
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 5: AMS Invoice – Billed MPRNs vs MPRNs with exception
Chart: AMS - MPRNs Billed vs MPRNs with exception
| 43922 | 43952 | 43983 | 44013 | 44044 | 44075
Total MPRNS Billed | 10672939 | 11210849 | 10308100 | 10227416 | 9897048 | 10584643
MPRNS with Exception | 219491 | 320023 | 130441 | 186437 | 74660 | 33561
% MPRNs with exception vs MPRN Billed | 0.020565 | 0.028546 | 0.012654 | 0.018229 | 0.0075437 | 0.0031707

## Slide 6: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
GREEN
RAG Justification
Cataloguing of all scenario resolution steps to ensure accuracy now completed.
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
146 distinct MPRNs for the August 2020 billing period currently have bill blocks placed upon them (as at 6th October 2020). Bill blocks are placed on MPRNs where there are known issues that will result in incorrect charges being calculated.
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) has been shared with all customers.

## Slide 7: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
RED
RAG Justification
1 Defect did not meet Septembers SLA: 62784 – Defect was placed on hold on 09/07 as code locked with 60999. On Hold status was removed on 10/08 and is currently in UAT Execution.
15 open ASP/AML related defects as of 2nd October 2020
(16 defects open at last month’s update)
Defect ID | Defect Title | Date Detected | Target Fix Date | SLA Resolution Date
61159 | Class change from 4 to 1 not updating total check to check volume and energy against MRD | 24/01/2020 | TBC | 03/04/2020
62060 | (On HOLD objects are currently locked under defect#61926 and defect#1458. and defect#60996) The cyclical read received with read on class change end date should be made inactive to avoid issues with rec | 03/04/2020 | TBC | 05/06/2020
62513 | ON HOLD object locked with Defect #61926 and Defect#62060. (Introduced by Defect 1464) - When the Cyclic read is received in the Class 3 period before RGMA activity date(D-1), the Profile values are being loaded. | 29/05/2020 | TBC | 07/08/2020
62784 | (Issue on TC6 of defect 62185 will be fixed under defect 62784 ) Read is inserted between OPNN and OPNT after a REC is performed, OPNT read should not be ignored during the Re-REC (June 20 Potential BAU defect ¦¦ 62337 ¦¦) | 19/06/2020 | 04/09/2020 | 04/09/2020
63243 | High priority - Incorrect Reconciliation For DM Sites; where the energy charges for billing document do not appear to have taken into account previous billing, so that the prevailing energy is based on the original commodity billing and not on the reconciliation values | 30/07/2020 | 09/10/2020 | 09/10/2020
63346 | (On Hold object lock with defect 62784 ) High priority - Volume and Energy is being calculated incorrectly between the Estimated Read (LDEX) and the subsequent Cyclic (CYCL) Read for a Class 3 Meter Point (UBR File) | 10/08/2020 | 06/11/2020 | 06/11/2020
63392 | (On HOLD object lock with defect 61967) High priority - Estimated Reads are getting derived incorrectly for the Shipper Transfer; hence shipper transfers incorrectly estimated | 14/08/2020 | 06/11/2020 | 06/11/2020
63393 | High Priority - For an NDM Prime Site, the Sub site volume and energy is not getting calculated if there is an Meter Reading Unit (MRU) frequency change for the same class | 14/08/2020 | 06/11/2020 | 06/11/2020
63394 | High Priority - The Class 3 read Tolerance Validation is passing due to an Incorrect CV calculation, when the last actual read date is before the Go-live Date | 14/08/2020 | 06/11/2020 | 06/11/2020
63480 | (Linked to @63486) Low Priority - The Last Check Read Date is getting fetched incorrectly for Twin Stream Sites when Reads are uploaded through Portal, resulting in either the Read wrongly rejected, or a break in the check to check period. | 26/08/2020 | 06/11/2020 | 06/11/2020
63485 | Medium Priority - Class 2 Reads (UDR) File process is unable to perform corrective estimation for Class 2 sites post class change from class 2 to any other class, when the actual read is in the Class 2 period | 26/08/2020 | 06/11/2020 | 06/11/2020
63486 | (Linked to @63480) High priority - Site visit Reads submitted via Portal are getting accepted, when an SFN Read already exists for a later date, hence breaking the Check to Check Rec period. Therefore should be rejected for Class 1 & 2 Sites | 26/08/2020 | 06/11/2020 | 06/11/2020
63566 | (WB) Medium priority - Inconsistent RGMA behaviour of class 2 sites with or without DRE/AMR | 10/09/2020 | 04/12/2020 | 04/12/2020
63690 | (On Hold - objects locked under Defect #63485 and Defect#61093) Medium priority - Issue with the Class change re-estimation; whenever the previous Class is either Class 3 or 4, and the Read is received in the Class 2 period, the Class change estimated Read on the Class 2 start date does not get updated | 28/09/2020 | 04/12/2020 | 04/12/2020
63691 | (WB) Medium priority - Inconsistent RGMA behaviour of class 2 sites with or without DRE/AMR | 28/09/2020 | 04/12/2020 | 04/12/2020

## Slide 8: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
Reports shared with all customers and general and individual WebEx’s are ongoing.
MI reports continue to be shared with our customers 2 business days after Amendment invoice issue date.
Ongoing individual customer meetings to discuss what the MI means specifically to them.
If any customer would like an explanation of the MI reports they receive just let us know and we will arrange a session (contact Dan Donovan, Xoserve Invoicing Business Process Manager - dan.l.Donovan@xoserve.com).