## Slide 1: CSSC Programme Dashboard
November 2020

## Slide 2
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | RAG status remains at Amber whilst we review the latest milestone plan in line with milestones, assumption and dependencies log in conjunction with this. This review will be assessed against internal plans from a timeline, cost and resource perspective. Queries and concerns have been raised with the Central Programme team with agreed actions being tracked via programme governance and weekly with our account manager within NetCompany (SI). | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Key Progress & Milestones (Last Month)
Key Programme Update Re-Plan: The CSS programme have received the re-plan from Ofgem. Key highlights for your information: SIT NFR completes 12/2/21 SIT Functional completes 4/3/21 UEPT moves to start 10/5/21 ends 5/11/21 E2E moves to start 12/7/21 ends 10/12/21 Transition Testing to start 8/11/21 ends 4/04/22 Transition to Live to start 21/3/22 ends 6/6/22 Go-Live window is between 6/6/22 ends 15/8/22 RBAC security solution has been removed from the “core” delivery and will be included in a separate release, potentially post go-live. SI have been informed that the costs for this will be significant to support development, internal test, regression and full test as well as deployment. We have not produced any figures to support the proposed solution, we will do so as soon as we receive further information via a formal CR. External Test Phases: The SI have raised a risk that SIT Phase 2 will not hit it’s completion. Testing at the point of production of this pack was 83% complete. Defects raised in SIT Cycle 1 continue to be re-tested in Cycle 2 as well as blocked Cycle 1 scripts. External NFR will resume mid November for ESP’s. Internal NFR & Performance Testing: Internal NFR metric of 17 transaction/second for Peak Of Peak achieved and stable. Throughput issues have been observed, these are being tracked through to resolution.. DES & API: DES development continues. Schema evolving to support screen requirements and secondary API data queries. REL and Switching screen re-factoring done and existing screen re-platforming in progress. “Data API” being expanded to support additional Ofgem requirements CCMT: Timelines to be considered against the revised re-plan. Engagement will continue via the Market Trials working group |  |  |  | DM NFR: Planning continues to start DMT NFR External SIT: Cycle 2 functional testing continues Internal UAT: Started – Test Execution complete Internal SIT: Phase 4 in progress with limited defec Programme: MAD Log v2 being reviewed. Transition: Xoserve Strawman planning continues CRs: Impact assessment and implementation continue Performance Testing: 17 trans/second achieved Peak of peak Internal NFT: Performance Test Phase 2a complete Secondary APIs: Design, build and test activities continue in line with plan
 |  |  |  | Upcoming Activities & Milestones (Next Month)
 |  |  |  | DMT NFR: Start test execution Environments: Continue final roll out of API environments and complete UKLink backup strategy changes External SIT: Continue External SIT External NFR: Continue planning to start in November Internal Test: Continue SIT phase 4, Performance test 2b, SIT & UAT assurance, DES 4 and Maintenance release regression test prep Internal NFT: Continue Performance Test Phase 2B DES: Complete DES Re-write activities and commence DBT for Ofgem requested API Secondary APIs: Design, build and test activities continue Transition: Transition planning – straw man to be completed by SI Costs: Continue cost analysis and control
Programme Update

## Slide 3: Amber and Green workstream updates
Kirsty to update
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Data Provision | Overall status is at Amber whilst UEPT data extract work is re-planned for 21st November production data copy. Market Trials data portfolio extracts are to be re-planned for Jan 2021. Data quality Analysis reports for cycle 3 (DA070) have been submitted to SI. Data team are investigating options for data extraction to support the SI’s future quarterly requests for these reports. Data cleansing activity continues. Planning for REL cycle 3 is underway
 |  | Performance Test & OAT | Overall status is at amber due to delays incurred due to environmental issues. We are as a consequence forecasting a three week delay to the completion of Phase 2b. Controlled runs carried out with test logs being analysed. Control-M issue has been resolved and schedule corrected. Further meter read testing carried with good results identified. Time Slice 2 testing has commenced.
 |  | Secondary API | Overall status is green. Design Build and Test activities continue to plan. Schema evolving to support screen requirements and secondary API data queries. REL and Switching screen re-factoring done and existing screen re-platforming in progress. “Data API” being expanded to support additional Ofgem requirements
 |  | UK Link | Overall status is Green. CRs emerging from the central programme continue to be assessed against baseline design and delivered as they progress through the governance. At the point of creating this update there are 8 external Programme CR’s inflight. .
 |  | Testing | User Acceptance Testing completed on the 30/9, Test Exit report creation in progress. Secondary API Test Preparation for Transport Rates API and MAP API is in progress, Test execution for Settlement and Nomination API delayed to 1/10. Switch-Stream Test Scenario creation for PIT, Option 2(Full functionality) and Option 1(Full Functionality) is in progress. UEPT Test Planning progress – Awaiting confirmation from SI of PIT and UEPT testing required as an Adaptor Service. Test Evidence Assurance is in progress Phase 1 - 122 of 142 Assured, Phase 2 - 93 of 132 Assured and UAT 10 of 195 Assured. External SIT “TW2” is in currently on track to finish on the 16/10 - 70.35.% Test Scripts passed (726 of total 1032 Test Scripts)

## Slide 4: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | Service Management | The first of a series of 1-2-1 sessions with DCC was held last week to address previous feedback we provided against the core process review. This first session was based around a very detailed discussion around DCC proposed SLA’s, these discussions will continue. DCC are suggesting that the proposed SLA’s are within the REC but this is not our understanding within the reviews we have undertaken to date. DCC have an action to confirm and provide the appropriate REC schedule where these are being included. REC schedule review continues.
 |  | Batch | The UAT Evidences are being updated to include some additional jobs ahead of formal review. There have been lots of troubleshooting calls to resolve the Control-M Gateway issue but this has now been resolved. Analysis is underway to establish the root cause. The AMT job setup is in progress as requested now the Control-M Gateway issue has been resolved. There are ongoing discussions with ECMS to try and obtain a regular report detailing any Control-M changes that have been made to Production as per risk 62881.
 |  | Gemini | There are ongoing discussions and analysis taking place to agree the solution of the Production defect recently identified. Regression testing on the new ECP environment has been completed and a code deployment has been requested.
 |  | Reporting | CR has now been drafted and contains the details for each report identified as impacted. This is going through internal governance.
 |  | Environments | Schedule is amber due to Environment re-plan in progress following release of SI re-plan. All planned environment activites in-light are tracking to plan. Continued assessment will continue to save costs where environment re-purpose can be identified.

## Slide 5: Appendix A – Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES, API | DES Full Re-platform (DES4) Build has now recommenced as Environment build outs are completed in QAS1 and QAS2. We have further work to convert PPTE2/3 shortly. SITNF and DMT environment builds underway for delivery this month. An additional round of SME ‘beta’ internal testing is being planned prior to Market Trials. . Environment templating is for the QAS environments, with QAS2 delivered and QAS1 in smoke testing. SITNF is now in progress, to be delivered by mid October along with DMT for support data migration testing. Pen Testing for DES4 now planned for November, and a new non-functional test phase for Browser Compatibility added to the project.
 |  | REC | The overall status of the REC project is currently green with Capture Stage in progress and Strategic approach being finalised. Original target was to complete Capture by 18th December 2020. Draft REC Schedules under review with the appropriate Xoserve SME’s. Transition Schedule and review of Service Management Schedule and Performance Assurance Schedules are being reviewed by the CSSC service management workstream in conjunction with Xoserve Tech Ops team. External RECCo alignment meeting hosted 18th Sep to initially review Model Services Contract for Gas Enquiry Service (GES). Meeting scheduled 2nd Oct to progress Framework Agreement for CDSP FS provisions. Ofgem RDUG hosted 24th Sep and included review of Transition, SPAA Transition, Transfer of Consumer Data & Pre-Payment Arrangement Schedules as well as Gas Transporter Licence changes.
 |  | Data Migration | Resource is in place for DM non functional testing. The SI have rescinded the requirement to generate additional “growth volume” data for bulk extracts. System testing for CR-D016 (CR0081) RegID has completed and a review of the test evidence is scheduled. DMT (functional) is in closedown, The Xoserve team have received the Test Completion report from the SI for review this week. Work on populating test scripts in Jira for DM non-functional has completed, however the SI are looking to issue additional scenarios for Smoke testing and CR functional testing outside of the DM NF scenarios. A CR for a dedicated environment for DM non-functional is being progressed. Approval to start work has been given and progress is to be tracked.
 |  | Market Trials | Overall the workstream is has returned to green following the change in timelines to align with the re-planned UEPT/E2E timelines, these will be assessed again against the Programme re-plan. The revised timelines will be discussed in detail with the industry at CCMTWG. Smoke testing and connectivity testing will start with the industry on 22nd March with test execution starting on 12th April . Milestones updated to reflect new plan.

## Slide 6: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
63538 |  | Programme | There is a risk that all CRs (particularly those raised in the early phases of the Switching Programme), may not been incorporated into design and build by the relevant parties because these CRs might have not been incorporated correctly into requirements leading to additional efforts required to incorporate these CRs and testing through the relevant test phases (and as a subsequence delays to already delayed timelines. | Escalate to the SI to revisit the traceability exercise to identify any gaps (if any) and reflect the impacts of these CRs on the plan | DCC have agreed that this is a very high priority to review and confirm all CRE entries have been included. | 30/11/20
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | All functionality bar 1 defect blocking completion of TW2. test team confident that the testing will be completed on 30/10. Testing have advised that this can be closed w/c 2/11. | 06/11/20
62448 |  | Data Migration | There is a risk that Xoserve's solution delivery is incompatible with the CSS being delivered by Landmark because of poor version control and ambiguity as to which is the live version of the CSS Interface Design Specification that the CSSP have built to, leading to avoidable defects arising in SIT and the subsequent rework required by one or both parties. | Confirm with SI the correct version of this document and support them in improving the version control in future | Awaiting update from SI from discussions with CSSP | 06/11/20

## Slide 7: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This is being monitored. The lack of this level of documentation has already manifested. CR-E01 and CR-E09 has not been incorporated in CSS Design. This should have come to light earlier | 30/10/20
61894 |  | Service Management | There is a risk that the CSS proposed SLA's do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | This has been highlighted to the SI. SI is picking this up to discuss with DCC to understand where in the process this is and reopen discussions around SLAs. DCC has fed back that SLAs are baselined following a presentation at the August Design forum. Xoserve has previously fed back our concerns and queries. | 02/11/20
54378 |  | Programme | There is a risk that the logical model contained in Abacus may not fully reflect the CSS processes and interactions with existing service providers because of limited engagement of all Programme stakeholders during the industry wide design phase. Leading to rework of the consequential design activities that have already been completed. | Engage with SI to ensure that Abacus update to fully reflect CSS processes | Discussed with Ofgem and DCC on 23/10 during the meeting on readiness assesment. DCC taken an action to investigate. | 03/03/21

## Slide 8: Key Programme Risks (3/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62897 |  | Data Migration | There is a risk that Xoserve may not be able to provide Landmark with data for UEPT on time leading to late delivery of data and potential delay to the start of UEPT | Review plans, discuss with programme | Planning underway. Azure team (Microsoft) on standby to support. Confirmation on "finalk environment" to be used will be provided 28/10 | 20/11/20
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This is being monitored. The lack of this level of documentation has already manifested. CR-E01 and CR-E09 has not been incorporated in CSS Design. This should have come to light earlier. | 30/10//20
62830 |  | Data Migration | There is a risk that we may not be able to access the data centre in order to connect the databox, to move the 31st prod cut to the azure environment leading to Xoserve being unable to load the data copy onto the environment to begin extract work, and test preparation | Escalate with TechOps to explore options for gaining access to the data centre. | No further update. Risk remains as local lockdowns may be imposed | 30/11/20
63061 |  | Data Migration | There is a risk of delays in transferring the production data copy from the databox to Azure by Microsoft leading to delays in provision of data extracts for Landmark for UEPT | Discuss MS service levels and agreements with Steve Concannon | To be reviewed alongside detailed plans for prod copy and transfer work | 23/11/20

## Slide 9: Key Programme Risks (4/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62942 |  | Programme | There is a risk that Xoserve systems will be out of sync with CSS during British Summer Time because CSSP intend to use UTC within the CSS solution and both UK Link and Gemini are believed to use BST leading to incorrect reporting of switches and all relevant data from Xoserve systems during the period where BST is one hour ahead of UTC. | Ofgem have now made a decision that BST will continue to be used across the gas industry so a CR is expected requiring Landmark to make the necessary changes to CSS. | Keeping this open until the CR is tested | 31/12/20
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | Continue to schedule workshops with DCC to discuss the feedback provided against all process documents that have been received from them. | 13/11/20
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | This was not added to the October agenda - advised that it will carry over to November forum | 31/12/20
63645 |  | Service Management | There is a risk that the Performance Assurance board will be formed to assure that that Switching Service is meeting market Participants expectation. There is a risk that Xoserve will be unable to provide the appropriate supporting information in the required timescales because DCC have not confirmed what Service Providers will need to feed into the board and it was discussed at the last Switching - Monthly Engagement Session that this board could ask for anything leading to the Performance Assurance Board not providing an accurate view to market participants and this having a reputational impact on Xoserve as the required information could not be provided in time. | XOS will push DCC for clarity within the monthly forums & 1:1 sessions | This was not added to the October agenda - advised that it will carry over to November forum | 31/12/20

## Slide 10
High Level Plan

## Slide 11: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  |  | On Hold
Introduction of Validation Message to Logical Mode | CR-D005 | £41,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £0.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 |  | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  |  | Not Received
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  |  | Withdrawn
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 |  |  | Not Received
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact

## Slide 12: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £0.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Awaiting Decision
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Awaiting Decision
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Awaiting Decision
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 |  | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Total |  | £15,412,789.00 |  |