## Slide 1
4.5 UK Link June’20 Release
XRN4850 Network Reporting –
Delivery Mechanism Options
2nd Dec 2020

## Slide 2
Approval Required:
Project name: June 20
Background
Networks have requested to automate the generation and delivery of the Network Delivery Report following delivery of broadcast notifications to end consumers. Three options are being considered: via existing IX channels to deliver the reports using new Twilio service to email Network users a link to access the reports via DDP portal access the reports Xoserve is recommending using the Data Discovery Platform to delivery the reporting. This approach has been ratified by our technical architects as the optimal delivery mechanism in order to provide a consistent customer experience. DDP is our enduring solution and has the necessary security protocols in place.
Decision Required
A decision is required as to which report delivery option is preferred so that Xoserve can proceed with build, test and deliver.
Decisions and Approvals

## Slide 3
Decisions and Approvals
Options: Deliver Mechanism for the Network Reporting | Outcome
IX Solution: Strategic Delivery timescale: late January/early February 2021 Delivery cost: £0 Considerations: 6 month notification period for IX changes, this can be reduced/waived subject to Network agreement | 
Azure/Twilio Service Solution: Strategic Delivery timescale: late January 2021 Delivery cost: £ included within SMS/Email notification allowance Considerations: switch will need to be made to enduring solution at some point in the future, at this point additional costs may be incurred | 
Data Discovery Platform (DDP) Solution: Enduring Delivery timescale: late January/early February 2021 Delivery cost: £18,375 Considerations: existing delivery mechanism for data delivered by Xoserve | 
Project Name: June 20
In this meeting the above will be discussed
Decisions and Approvals

## Slide 4: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: To date we had had 1 network use the service for both extract and SMS service for a limited number of meter points due to the limited data availability in UK Link which is currently circa 5-million-meter points with a further 2 million planned by end of December 2020, discussions ongoing with Supply Point Administration Agreement (SPAA) group to encourage greater population of data, please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Post Implementation Support: XRN4850 – Post Implementation Support for implementation of the new SMS/Email service is on track to complete on 27th November. Scope Variations: XRN4850 requirements and design for scope variation for report automation in progress. Report delivery mechanism for the enduring solution agreed to be via the Data Discovery Platform (DDP) to be delivered in late January. Manual reporting will be available in the interim should the service be used. XRN4780(B) MAP ID – MAP ID changes were successfully implementation on 28th November with migration of data have commenced from 30th November (expected completion by 14th December). All portfolio data has been received from participating MAPs and has been validated in preparation for migration activities |  |  | 
Risks and Issues | Risk – DN's/IGT's do not use the new SMS/Email broadcast functionality during Post Implementation Support, because of the limited number of customer contact details uploaded to UK Link or networks do not need to send broadcasts during this period. To mitigate, we are looking to develop a report to detail % of sites in each LDZ which has BRO data populated therefore providing visibility to Networks of available data |  |  | 
Cost | Core UK Link Project Delivery costs are in line with approved BER XRN4850 Costs are being finalised in the CCR following approval of Twilio as service provider and scope variations Mitigation is to share the final costs at next Change Management meeting |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 
Updates as of the 30th November 2020

## Slide 5: XRN4850 – BRO Data LDZ Saturation Report – Approval Required
As part of the Network usage report for xrn4850 SMS/Email Notification service a number of Networks have requested Xoserve to identify the percentage saturation per LDZ of the Broadcast 'BRO' data held in UK Link. This will enable Networks to determine whether sufficient data exists to make using the notification service effective.
Xoserve have analysed the request and are proposing to produce a report, which can be generated monthly, to provide Network Operators visibility of the percentage of BRO data populated in UK Link by LDZ.
Below is an example of what this report would look like. The report would cost a total figure of £1,800, for initial 6 months of reporting, which includes, build, test and delivery of 6 monthly reports, commencing early February 21.
Updates as of the 30th November 2020
Shipper Org ID | ShipperShort Code | Supplier Org ID | SupplierShortCode | LDZ | LIVE BRO Count
399 | BUS | 462 | BGT | LO | XXXXX
399 | BUS | 462 | BGT | SC | XXXXX
399 | BUS | 10001768 | BGB | SC | XXXXX
451 | SCP | 10000039 | SCT | SC | XXXXX
10000164 | SGL | 10000164 | SGL | SC | XXXXX
10001399 | LEP | 10000264 | LED | SC | XXXXX

## Slide 6: XRN4850 – SMS/Email Broadcast Notification Timeline
Post Implementation Support is on track to complete on 27th November.
Daily/Monthly Network Usage report delivery in progress, to be delivered late January via the Data Discovery Platform (DDP)
Updates as of the 30th November 2020
TODAY

## Slide 7: XRN4996 June 20 Release Summary
June 20 Release consists of 7 changes, Implementation was completed for June 20:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 - Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters (UKLink file formats, new service to follow)
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining change requests. Descoped at ChMC on 8th January 2020
** Descoped at eChMC on 22nd November 2019
*** Added to scope (revised scope from original)
Updates as of the 30th November 2020