## Slide 1: XRN5225 – Minor Release 8 Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 3 changes for XRN5225 to be implemented. The proposed implementation date is 21st November 2020: XRN5181 - Acceptance of Consumption Adjustments where meter is removed XRN5174 - Agreed FINT Replacement Reads incorrectly triggering rolling AQ calculation XRN5118 - Change how the actual MR data is populated in UK Link Implementation successfully completed 21st November 2020 PIS in progress, no defects raised to date |  |  | 
Risks and Issues | No major risks to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 30th November 2020

## Slide 2: XRN5225 – Minor Release 8 Timelines
Key Proposed Dates:
Impact Assessment Complete – 28/8/20
Design Complete / signed off – 11/09/20
Build Complete – 02/10/20
Testing Complete – 14/11/20
Implementation Complete – 21/11/20
PIS Complete – 05/12/20
Updated 30th November 2020
TODAY

## Slide 3: XRN5225 – Minor Release 8 Summary
There are 3 changes for XRN5225 to be implemented. The proposed implementation date is 21st November:
  XRN5181 - Acceptance of Consumption Adjustments where meter is removed
  XRN5174 - Agreed FINT Replacement Reads incorrectly triggering rolling AQ calculation
  XRN5118 - Change how the actual MR data is populated in UK Link
Updated 30th November 2020