## Slide 1: UK Link Releases Update
December 2020 ChMC

## Slide 2: UK Link Releases Update
Agenda:
UK Link Releases Governance Timeline 2020 – 2021
Allocated Changes - in delivery
Unallocated Changes – in Capture and changes that have completed Capture
January 2021 ChMC agenda items
Glossary

## Slide 3: 2020-2022 UK Link Governance Timeline
Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
2020 | 2021 | 2022
Please note that this slide includes potential activity within UK Link over the next 24 months
On track
At risk
Key:
Complete
CSSC activity
CSSC
Nov 21
Jun 21
MiR 10
MiR 9
Nov 20
Retro POC
Scope Approved – August ChMC
MiR
Major
Retro POC
Potential Activity
Potential Activity
Potential Activity
Potential Activity – Minor Releases
Potential Activity – Major Releases
Scope Approved Nov 2020 eChMC
Scope Approval Nov 2020 ChMC
Scope Approval Feb 2021 ChMC
EQR Approved
Sep ChMC
BER approval
Dec ChMC
Retro
Potential Activity
EQR Approval
Jan ChMC

## Slide 4: UK Link Allocated Changes – In Delivery
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DN
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DN
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DN
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DN
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4780c | MAP ID Part C | In Capture | tbc – June 2021 | Large | Shippers
 | 4627 | Consequential Central Switching Services | In Delivery | tbc | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DN
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DN
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DN
MiR Drop 8 | 5181 | Acceptance of consumption adjustments where meter point moved after meter set to dead | In Delivery | Nov 2020 | Small | MiR Delivery
 | 5118 / 5174 | Service sustaining activity – Change how actual MR data is populated in UK Link / Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | In Delivery | Nov 2020 | Small | MiR Delivery

## Slide 5: UK Link Allocated Changes - Continued
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
MiR Drop 9 | 5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | Impact assessment | March 2021 | Small | MiR
 | 5080 | Failure to supply Gas (FSG/GSOP1) - System Changes | Impact assessment | March 2021 | Small | MiR
Jun-21 | 5093 | MOD0711 – Update of AUG Table to reflect new EUC bands | Solution Option approved | June 2021 | X-Large | Shippers
Nov-21 | 4941 | MOD0692 - Auto updates to meter read frequency | Descoped from June 21. Solution approved | Nov 2021 | Large | Shippers
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Descoped from June 21 release. Solution approved | Nov 2021 | Large | DN/IGT/Shipper
 | 5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | Solution approval | Nov 2021 | Large | DN
 | 5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Solution approval | Nov 2021 | Medium | DN
 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | HLSO | Nov 2021 | Large to XL | Shipper
 | 5091 | Deferral of creation of Class change reads at transfer of ownership | Solution approval | Nov 2021 | Large | Shipper
 | 5180 | Inner tolerance validation for replacement reads and read insertions | Solution approval | Nov 2021 | Large | Shipper
 | 5007 | Enhancement to reconciliation process where prevailing volume is zero | HLSO | Nov 2021 | tbc | Shipper

## Slide 6: UK Link Unallocated Changes
Potential Release | XRN | Change Title | Comments | Status | Complexity | Points | Finance
tbc | 4931 | Submission of space in mandatory data on multiple SPA files | Descoped from Nov 20 Major Release. Analysis underway to determine validate new solution and identify release | Capture Complete | tbc | tbc | Nov 20 BER
tbc | 4990 | MOD0664 – Transfer of sites with low read submission performance |  | Requirements | tbc | tbc | Shipper
tbc | 4992 | MOD0687 - Creation of new charge to recover last resort supply payments | MOD not yet approved. ChMC voted to descope from June 21 release. MOD expected to be replaced/amended by Ofgem. | Capture Complete | tbc | tbc | Shipper
tbc | 5081 | No actual read present in previous class for read validation |  | Requirements | tbc | tbc | tbc
tbc | 5143 | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP |  | Requirements | tbc | tbc | tbc
tbc | 5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions |  | Requirements | tbc | tbc | tbc
tbc | 5188 | Interim Data loads of MAP ID into UK Link |  | Requirements | tbc | tbc | tbc
tbc | 5195 | Ceased responsibility date following shipper withdrawal (IDL) | Potential MiR Drop 10 candidate | Solution Approval | Small | 5 | MiR
tbc | 5218 | CDSP Provision of Class 1 read service |  | Requirements | tbc | tbc | DN/Shipper
tbc | 5231 | MOD0719R – Flow Weighted Average Service |  | Requirements | tbc | tbc | DN
tbc | 5235 | Include SOQ in UIG additional data report |  | Requirements | tbc | tbc | DN/Shipper
tbc | 5236 | MOD0734 – Reporting Valid Confirmed Theft of Gas into Central Systems |  | Requirements | tbc | tbc | tbc
tbc | 5238 | New Distribution Network Report – Forecast Invoice Values |  | Requirements | tbc | tbc | DN

## Slide 7: January ChMC
UK Link Future Releases Updates:
November 2021
  EQR for approval

## Slide 8: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal – an external request for a change to UK Link
CR | Change Request – an internal request for a change to UK Link
HLSO(s) | High Level Solution Option(s)