## Slide 1: Change Management Committee
9th December 2020

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: 2.1 - DSC Change Budget BP20 (Financial Year To Date)

## Slide 4: Budget v Spend BP20/21 Financial Year To Date (FYTD)
Available funds have reduced by £51k as a result of multiple changes moving through the lifecycle (i.e. HLSO) and estimated costs being entered for Nov-21 candidates. Excel doc embedded:
Costs that remain uncommitted at end of financial year will be offset against future change budget (BP21) as consensus could not be reached via addendum to BP21 or in DSC committee as to otherwise use shipper underspend in BP20
Governance to be reviewed ahead of any future discussion around management of underspend

## Slide 5: 2.2 - Bubbling Under (pre-capture regulatory change)

## Slide 6: Section 3: Capture

## Slide 7: 3.1 Capture: Prioritisation & Target Out Of Capture Dates

## Slide 8
In progress - target out of capture date

## Slide 9
Withdrawn / Complete

## Slide 10: 3.2 New Change Proposals – Initial Review
XRN / Title | Voting |  |  |  | DSC Service Area
 | Shipper | DNO | IGT | NTS | 
XRN5285 - COVID-19 Capacity Retention Process (MOD 0730) | X | X |  | X | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoice
XRN5286 Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746) | X | X | X |  | Service Area 1: Manage supply point registration New Service Line(s) anticipated to identify and action retrospective invalid AQ corrections.

## Slide 11: XRN5285 - COVID-19 Capacity Retention Process (MOD 0730)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | X
IGT’s | 
Voting Parties
DSC Service Area: | Service Area 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoice
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Due to the impacts of Covid-19 some sites are using minimal levels of gas, but capacity charges are still being applied which customers are unable to utilise.
Sponsor Representative | Xoserve
Change Description
This Change Proposal has been raised to deliver Modification 730. The Modification was raised to provide relief to customers who have been adversely impacted by Covid-19. As sites have had to cease production as a result of the pandemic, the current arrangements have still meant that capacity charges have been applied. Therefore, where an isolated status has been applied to a Supply Meter Point, partial relief from the capacity charges will be given, without requiring a full Supply Point Withdrawal. This change aims to apply a discount of 50% to LDZ Capacity Costs for sites that are set as Isolated (utilising the process introduced by UNC Modification 0723 - Use of the Isolation Flag to identify sites with abnormal load reduction during COVID-19 period). The remaining 50% payment is to be seen as a Capacity retention payment guaranteeing the continued availability of capacity at that site. This should be managed through a short-term manual process. Please see CP for full description
Change Type | Regulatory
Priority Score | High

## Slide 12: XRN5286 Clarificatory change to the AQ amendment process to be applied retrospectively (Modification 0746)
Customer Class | Voting Party?
Shipper | X
Distribution Network Operators (DNOs) | X
National Grid Transmission | 
IGT’s | X
Voting Parties
DSC Service Area: | Service Area 1: Manage supply point registration New Service Line(s) anticipated to identify and action retrospective invalid AQ corrections.
Link to Change Proposal | Link to CP
Change Details
Problem Statement
Shippers within the same organisation or group have had the ability to utilise AQ Corrections reason code 3 to amend the AQ of a site, so AQ Corrections have been accepted from this scenario.
Sponsor Representative | Xoserve
Change Description
Modification 746 has been raised to clarify the circumstances in which specific AQ Corrections can be made and to apply this clarification from the 1 April 2020. Therefore, this Change Proposal has been raised to deliver the changes required as set out within this Mod 746. Please note, that this Modification was previously ‘736A’, an alternate to Modification 736 before both Modifications were decoupled. This change seeks to seeks to clarify that where a User is affiliated to the previously Registered User, they cannot utilise ‘Reason Code 3’ to submit an AQ correction Please see the CP for full description
Change Type | Regulatory
Priority Score | High

## Slide 13: 3.3 Change Proposal updates
XRN5218 CDSP provision of Class 1 read service
XRN5144 Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions

## Slide 14: XRN5218 CDSP provision of Class 1 read service
Verbal update to be presented by Ellie Rogers

## Slide 15: XRN 5144 - Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions
DSC ChMC – December Update

## Slide 16: Update
XRN5144 was raised at Ofgem’s request to assess reallocation of the Supplier Short Code at SoLR
An alternative change was drafted within the Faster Switching Programme (CR025) – but has not progressed
DSC ChMC indicated that they were not prepared to undertake any detailed [paid for] analysis at this time
  CDSP progressed with internal process assessment to identify potential impacts
  This would create issues with Data Permissions for display of historic data
Ofgem have requested a ROM is provided to understand the impacts to the UK Link system of progression of XRN5144
  This is being assessed
  We have highlighted that this will not include impacts on other gas industry participant systems
  We will share the outcome of this with DSC ChMC

## Slide 17: 3.4 New Change Proposals – Post Initial Review
None for this meeting

## Slide 18: 3.4 New Change Proposals – Post Solution Review
Removal of Shipper Supplier Access to Emergency Contact Details in DES
XRN5206 - TPI_PCW Access
XRN5237 - Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736 ONLY)

## Slide 19: Removal of Shipper Supplier Access to Emergency Contact Details in DES
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: CSS Link to Change Pack ref: 2718.1 - RT - PO Voting: Shipper High level Solution cost: Funding to be covered by CSSC programme Service Area: N/A | Option 1 | SSE | X |  |  | We agree that access can be withdrawn from shippers and suppliers to consumer Emergency Contact Details in DES. Currently, we do use DES to perform some manual checks on what Emergency Contacts are held by Xoserve to ensure they are up to date. Could a flag be included in DES, to confirm that Emergency Contact Details are held against an MPRN, and a date indicating when they were last updated?
 |  | EDF | X |  |  | We agree with proposed solution and timescales

## Slide 20: XRN5206 - TPI_PCW Access
Proposed Release Link to Change Proposal Comm Ref | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: AdHoc Link to CP Link to Change Pack ref: 2718.4 - RT - PO - XRN5206 Voting: Shipper High level Solution cost: Option 1: 10 – 15K Service Area: Service Area 24 - Additional Service Request or Third Party Request Funding: 100% Shipper | Option 1 | SGN | X |  |  | We support Option 1 to utilise the Supply Point Switching API but would ask that the definitions of a TPI/PCW are transparent and agreed with networks as it is our obligation being discharged.
 |  | Centrica | X |  |  | "Yes we support this change as this change is required by Centrica (and in all probabilities other Suppliers and Shippers) for the Faster Switching Programme. As part of Faster Switching Programme XOSERVE is making additional changes to include the REL address and current supplier Reg Effective Date to the Supply Point Switching API. The current supplier Reg Effective Date is needed by suppliers to check whether a customer is in the ‘Standstill Period’ or not and this is needed for both Dom and Non-Dom sites. As part of the XOSERVE change to make certain data elements available on the DES API’s we were expecting that the Confirmation Effective Date(Portfolio View) which is a part of the Supply Point Enquiry API would have the restriction for “Portfolio view “ removed. Although a request was raised for this by Centrica it was not considered as part of the recent XRN 4801 change (nor are they a part of the upcoming changes for the DES API’s discussed by XOSERVE in the recent Extraordinary DSEG meeting). This field is required by the Faster Switching Program for calculating the Supply Start Date correctly; by determining whether a customer is in the standstill period or not. We would like to also • To remove the restriction of Portfolio view from the field- Confirmation Effective Date(Portfolio View) of Supply Point Enquiry and • Add the REL address output to the Supply Pont Enquiry API . This would mean it is not necessary to make two separate calls for the XOSERVE API’s (Supply Point Enquiry and Supply Point Switching API) to obtain as the required information getting all the details needed as part of FMRS Details- https://www.xoserve.com/services/gas-api-services/Supply Point Enquiry(https://umbraco.xoserve.com/media/41375/xoserve-query-apis-technical-specification-v102-tracked.pdf)"
 |  | SSE | X |  |  | We agree in principle with removing the restriction on TPIs/PCWs from accessing non-domestic data in the Supply Point Switching API. However, allowing this may increase a potential risk that TPIs/PCWs will rely on this data rather than seeking data from the customer which could be more accurate. For example, instead of asking the customer to provide their current consumption in order to quote, the TPI/PCW may just take the AQ from the Supply Point Switching API. The AQ may not accurately reflect the customer’s ongoing requirements (especially due to Covid-19), which could lead to inaccurate initial quotation.

## Slide 21: XRN5237 - Maintenance of a User relationship table for the purpose of AQ amendments (Modification 0736 ONLY)
XRN / Title Proposed Release Link to Change Proposal Comm Ref | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: Ad hoc – expected January 2021 Link to CP Link to Change Pack ref: 2718.5 - RT - PO - XRN5237 Voting: IGT, Shipper & DNO High level Solution cost: Option 1 – 20k-30k Service Area: Service Area 1 - Manage Supply Point Registration Funding: 100% Shipper | Option 1 | EDF |  |  | X | We agree with updating UNC to clarify, however I have been unable to find quantification anywhere for how much of a problem this is financially and why we are proposing to put in a safety net which is not encouraging shippers to change behaviours, moreover allowing them to submit and do nothing as reversal will be done for them. This is an obligation within the UNC and as a result should be treated as such, where not complying shippers should be pulled up through PAC and dealt with accordingly whether that be through proportional fines at the level of the detriment to the industry. We believe change should not be implemented to hand hold non performing shippers – where cost of initial change is financed by the rest of the industry. This – as stated by Xoserve – is a rushed solution in order to implement in Jan 2021 (understanding that there is a proposal for a part B solution which as per my earlier points – don’t deem to be the right approach). We seem to be focussing on cure rather than prevention across the industry of late and don’t feel this is the right approach .
 |  | SSE | X |  |  | We support this change to provide clarity in the UNC around where a Shipper can utilise AQ correction reason code 3.
 |  | Cadent | X |  |  | We are happy that the solution delivers on the intent of Modification 0736S.

## Slide 22: 3.5 Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified/updated Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
11024 | UK Link Portal; UK Link On-line Service; DES and CMS | 04/12/2020 | 23:00 | 05/12/2020 | 10:00 | UK Link Disaster Recovery Test 2020 (Failover to DR site) - the UK Link system will operate normally from the DR site in the period between Failover and Failback. NB: UK Link System Application will not be available during this period – but no impacts to Users are expected | 11/11//2020
11024 | UK Link Portal; UK Link On-line Service; DES and CMS | 05/12/2020 | 23:00 | 06/12/2020 | 07:00 | UK Link Disaster Recovery Test 2020 (Failback to primary site) - contingency dates for the test are Friday 15th to Sunday 17th January 2021 with the same timings as above. NB: UK Link System Application will not be available during this period – but no impacts to Users are expected | 11/11//2020
 | UK Link | 02/01/2021 | 04:00 | 06/01/2021 | 07:00 | In order that the UK Link platform continues to be supported we will be carrying out a programme of upgrades to existing systems over the next few months. The upgrades to production systems are planned for early January and will require some system outages which we will aim to carry out over a weekend to ensure impact to the industry is minimised. The detailed upgrade and outage schedule will be shared in November. | Times and Dates updated 30/11//2020
 | UK Link | 08/01/2021 | 04:00 | 09/01/2021 | 07:00 |  | 
 | UK Link | 12/01/2021 | 04:00 | 16/01/2021 | 07:00 |  | 
 | UK Link | 17/01/2021 | 18:00 | 17/01/2021 | 01:00 |  | 

## Slide 23: 4. Design & Delivery

## Slide 24: 4.1 Design Change Pack
XRN5093 Update of AUG Table to reflect new EUC bands MOD0711
XRN5122 Gemini System Enhancements – External Screens pack and API Specification
Administrative update to UK Link Manual documents following CDSP Review
Settlement Data API Technical Specification, Query APIs Technical Specification & Secondary API Error Handling Strategy
UK Link Settlement Data API Design Specification

## Slide 25
XRN5093 Update of AUG Table to reflect new EUC bands MOD0711
Functional Changes |  |  |  |  | 
Change Pack ref: 2718.2 - RT - PO Release: June 21 Major Release Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | Scottish Power | X |  |  | None

## Slide 26
XRN5122 Gemini System Enhancements – External Screens pack and API Specification
Functional Changes |  |  |  |  | 
Change Pack ref: 2718.3 - RT - PO Release: 25th July 2021 - Individual change outside of the release window Voting: NTS | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 |  |  |  |  | No responses were received for this Change Pack

## Slide 27
Administrative update to UK Link Manual documents following CDSP Review
Functional Changes |  |  |  |  | 
Change Pack ref: 2718.6 – RT - PO Release: We intend to set to live after December ChMC if approved Voting: Shipper, DNO, NTS & IGT | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | EDF | X |  |  | None

## Slide 28
Settlement Data API Technical Specification, Query APIs Technical Specification & Secondary API Error Handling Strategy
Functional Changes |  |  |  |  | 
Change Pack ref: 2719.1 - RT – PO Release: CSSC Programme Voting: Shipper & DNO | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | Centrica | None stated |  |  | "For the Address Search – • How is XOSERVE going to handle exception scenarios where either MPL/REL address unavailable (likely if manual update is being done to the address).What would be returned in the Address Search for Supply Point Switching API. • What validations are carried out while matching the REL and MPL address for a MPRN. Will there be a scenario where there is a major mismatch between the two address data? • Can there be any identifier added for the addresses, currently the document mentions the first one is the UK Link Address followed by the REL Addresses. Comments on the document-Query APIs Technical Specification • The document mentions - ""4 Nomination Enquiry API The nomination Enquiry API (previously known as the Supply Point Enquiry alternative to the existing traditional IX nomination enquiry and response. In a meeting with XOSERVE we were told that it is not a replacement for the ‘Supply Point Enquiry API’ and that the Supply Point Enquiry API will continue to exist as it is. • Supply Point Switching API –The document mentions – 6.1 Scope The supply point Switching API will return data for domestic sites. • CSS is applicable for both ‘Domestic’ and ‘Non-Domestic’ sites and hence the extra data items being made available via this API is needed for both Dom and Non-Dom"
 | OVO | X |  |  | None

## Slide 29
UK Link Settlement Data API Design Specification
Functional Changes |  |  |  |  | 
Change Pack ref: 2719.2 - RT - PO Release: CSSC Programme Voting: Shipper | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Deferred | Reject | 
 | OVO | X |  |  | None

## Slide 30: 4.2 Change Documents
CCR for XRN4645a - Rejection of incrementing reads following Isolation (RGMA Flows)
  Voting - Shipper
CCR for XRN5168 MOD0721 (Urgent) - Shipper submitted AQ Corrections during COVID-19
  Voting - Shipper
CCR for XRN5172 MOD0725 (Urgent) - Ability to Reflect the Correct Customer Network Use and System Offtake Quantity (SOQ) During COVID-19
  Voting - Shipper
CCR for XRN4738 Shipper Portfolio Update of Proposed Formula Year AQ/SOQ
  Voting - Shipper
BER for XRN5120 - MAP to UKL Monthly Comparison Service
  Voting - Shipper

## Slide 31: 4.3 Gemini Updates
CCR for XRN5092 – iConversion Phase 2
  Voting - NTS
Gemini Horizon Plan

## Slide 32: 4.4 XRN5253 June 21 Release - Status Update
BER for XRN5253 – June 21 Release
  Voting - Shipper

## Slide 33: XRN5253 - June 21 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | BER to be presented to Change Management Committee on 9th December June 21 Major Release scope now consists of XRN5093 MOD0711 – Update of AUG Table to reflect new EUC bands. 2 changes have been descoped, XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments and XRN4941 – MOD0692 – Auto updates to meter read frequency Project Start Up phase completed Detailed Design execution completed and Change Pack for XRN5093 published on 16th November. Test & Implementation Approach under internal review Build to commence on 14th December following approval of BER Due to Internal nature of change no Market Trials phase included in project release as no external testing is required |  |  | 
Risks and Issues | Issue: The project is progressing 2 months behind plan leading to overlap between multiple phases and risk that approvals may not fall in order. It also reduces overall delivery timescales. Mitigation: Detailed Plan up to end of Design to be completed as part of Start Up to ensure tight project control and critical path management |  |  | 
Cost | Final EQR approved at CHMC on 7th October, BER to be presented in December |  |  | 
Resources | Resource RAG Status will return to green on completion of detailed design & initiation phases (inclusive of Test Approach sign off) Resource Forecasts and Plans have been defined at a high level for future stages |  |  | 

## Slide 34: XRN5253 – Proposed June 21 High-Level Plan
TODAY

## Slide 35: XRN5253 - June 21 Release Summary
In Scope
XRN5093 - MOD0711 – Update of AUG Table to reflect new EUC bands
De-Scoped at Extraordinary Change Management Committee on 26th October 2020
XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments
De-Scoped at Change Management Committee on 11th November 2020
XRN4941 - MOD0692 - Auto updates to meter read frequency
June 21 Release now consists of 1 change

## Slide 36
4.5 UK Link June’20 Release
XRN4850 Network Reporting –
Delivery Mechanism Options
2nd Dec 2020

## Slide 37
Approval Required:
Project name: June 20
Background
Networks have requested to automate the generation and delivery of the Network Delivery Report following delivery of broadcast notifications to end consumers. Three options are being considered: via existing IX channels to deliver the reports using new Twilio service to email Network users a link to access the reports via DDP portal access the reports Xoserve is recommending using the Data Discovery Platform to delivery the reporting. This approach has been ratified by our technical architects as the optimal delivery mechanism in order to provide a consistent customer experience. DDP is our enduring solution and has the necessary security protocols in place.
Decision Required
A decision is required as to which report delivery option is preferred so that Xoserve can proceed with build, test and deliver.
Decisions and Approvals

## Slide 38
Decisions and Approvals
Options: Deliver Mechanism for the Network Reporting | Outcome
IX Solution: Strategic Delivery timescale: late January/early February 2021 Delivery cost: £0 Considerations: 6 month notification period for IX changes, this can be reduced/waived subject to Network agreement | 
Azure/Twilio Service Solution: Strategic Delivery timescale: late January 2021 Delivery cost: £ included within SMS/Email notification allowance Considerations: switch will need to be made to enduring solution at some point in the future, at this point additional costs may be incurred | 
Data Discovery Platform (DDP) Solution: Enduring Delivery timescale: late January/early February 2021 Delivery cost: £18,375 Considerations: existing delivery mechanism for data delivered by Xoserve | 
Project Name: June 20
In this meeting the above will be discussed
Decisions and Approvals

## Slide 39: XRN4996 - June 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | XRN4850 SMS/Email Notification: To date we had had 1 network use the service for both extract and SMS service for a limited number of meter points due to the limited data availability in UK Link which is currently circa 5-million-meter points with a further 2 million planned by end of December 2020, discussions ongoing with Supply Point Administration Agreement (SPAA) group to encourage greater population of data, please contact Max Pemberton at customerexperience@xoserve.com prior to submitting any contact details. Post Implementation Support: XRN4850 – Post Implementation Support for implementation of the new SMS/Email service is on track to complete on 27th November. Scope Variations: XRN4850 requirements and design for scope variation for report automation in progress. Report delivery mechanism for the enduring solution agreed to be via the Data Discovery Platform (DDP) to be delivered in late January. Manual reporting will be available in the interim should the service be used. XRN4780(B) MAP ID – MAP ID changes were successfully implementation on 28th November with migration of data have commenced from 30th November (expected completion by 14th December). All portfolio data has been received from participating MAPs and has been validated in preparation for migration activities |  |  | 
Risks and Issues | Risk – DN's/IGT's do not use the new SMS/Email broadcast functionality during Post Implementation Support, because of the limited number of customer contact details uploaded to UK Link or networks do not need to send broadcasts during this period. To mitigate, we are looking to develop a report to detail % of sites in each LDZ which has BRO data populated therefore providing visibility to Networks of available data |  |  | 
Cost | Core UK Link Project Delivery costs are in line with approved BER XRN4850 Costs are being finalised in the CCR following approval of Twilio as service provider and scope variations Mitigation is to share the final costs at next Change Management meeting |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc.) is ongoing |  |  | 
Updates as of the 30h November 2020

## Slide 40: XRN4850 – BRO Data LDZ Saturation Report – Approval Required
As part of the Network usage report for XRN4850 SMS/Email Notification service a number of Networks have requested Xoserve to identify the percentage saturation per LDZ of the Broadcast 'BRO' data held in UK Link. This will enable Networks to determine whether sufficient data exists to make using the notification service effective.
Xoserve have analysed the request and are proposing to produce a report, which can be generated monthly, to provide Network Operators visibility of the percentage of BRO data populated in UK Link by LDZ.
Below is an example of what this report would look like. The report would cost a total figure of £1,800, for initial 6 months of reporting, which includes, build, test and delivery of 6 monthly reports, commencing early February 21.
Updates as of the 30th November 2020
Shipper Org ID | ShipperShort Code | Supplier Org ID | SupplierShortCode | LDZ | LIVE BRO Count
399 | BUS | 462 | BGT | LO | XXXXX
399 | BUS | 462 | BGT | SC | XXXXX
399 | BUS | 10001768 | BGB | SC | XXXXX
451 | SCP | 10000039 | SCT | SC | XXXXX
10000164 | SGL | 10000164 | SGL | SC | XXXXX
10001399 | LEP | 10000264 | LED | SC | XXXXX

## Slide 41: XRN4850 – SMS/Email Broadcast Notification Timeline
Post Implementation Support is on track to complete on 27th November.
Daily/Monthly Network Usage report delivery in progress, to be delivered late January via the Data Discovery Platform (DDP)
Updates as of the 30th November 2020
TODAY

## Slide 42: XRN4996 June 20 Release Summary
June 20 Release consists of 7 changes, Implementation was completed for June 20:
In Scope
XRN4772 - Composite Weather Variable (CWV) Improvements
XRN4888 - Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS)
XRN4930 - Requirement to Inform Shipper of Meter Link Code Change
XRN4850 - Notification of Customer Contact Details to Transporters (UKLink file formats, new service to follow)
XRN4865 - Amendment to Treatment and Reporting of CYCL Reads
XRN4932 - Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S)
XRN4780 (B)*** – Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
Descoped
XRN4691** - CSEPs: IGT and GT File Formats (CGI Files)
XRN4692** - CSEPs: IGT and GT File Formats (CIN Files)
XRN4780 (B) - Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change)
XRN4871 (B)** - Changes to Ratchet Regime (MOD0665)
XRN4941* - Auto updates to meter read frequency (MOD0692)
* Pending Solution/MOD approval by ChMC/DSG for remaining change requests. Descoped at ChMC on 8th January 2020
** Descoped at eChMC on 22nd November 2019
*** Added to scope (revised scope from original)
Updates as of the 30th November 2020

## Slide 43: 4.6 UK Link Releases Update
December 2020 ChMC

## Slide 44: UK Link Releases Update
Agenda:
UK Link Releases Governance Timeline 2020 – 2021
Allocated Changes - in delivery
Unallocated Changes – in Capture and changes that have completed Capture
January 2021 ChMC agenda items
Glossary

## Slide 45: 2020-2022 UK Link Governance Timeline
Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
2020 | 2021 | 2022
Please note that this slide includes potential activity within UK Link over the next 24 months
On track
At risk
Key:
Complete
CSSC activity
CSSC
Nov 21
Jun 21
MiR 10
MiR 9
Nov 20
Retro POC
Scope Approved – August ChMC
MiR
Major
Retro POC
Potential Activity
Potential Activity
Potential Activity
Potential Activity – Minor Releases
Potential Activity – Major Releases
Scope Approved Nov 2020 eChMC
Scope Approval Nov 2020 ChMC
Scope Approval Feb 2021 ChMC
EQR Approved
Sep ChMC
BER approval
Dec ChMC
Retro
Potential Activity
EQR Approval
Jan ChMC

## Slide 46: UK Link Allocated Changes – In Delivery
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
Jun-20 | 4865 | Amendment to Treatment and Reporting of CYCL Reads | In Delivery | June 2020 | Small | Shippers / DN
 | 4772 | Composite Weather Variable (CWV) Improvements | In Delivery | June 2020 | X-Large | Shippers / DN
 | 4930 | Requirement to Inform Shipper of Meter Link Code Change | In Delivery | June 2020 | Small | Shippers
 | 4932 | Improvements to the quality of the Conversion Factor values held on the Supply Point Register (MOD0681S) | In Delivery | June 2020 | Medium | Shippers / DN
 | 4850 | Notification of Customer Contact Details to Transporters | In Delivery | June 2020 | X-Large | IGTs / DN
 | 4888 | Removing Duplicate Address Update Validation for IGT Supply Meter Points via Contact Management Service (CMS) | In Delivery | June 2020 | Medium | IGTs
 | 4780b | MAP ID Part B | In Delivery | June 2020 | Large | Shippers
CSSC | 4780c | MAP ID Part C | In Capture | tbc – June 2021 | Large | Shippers
 | 4627 | Consequential Central Switching Services | In Delivery | tbc | N/A | Shippers
Retro | 4914 | Retro Proof of Concept | In Delivery | Standalone | N/A | DN
Nov 2020 | 5014 | Hydeploy Live Trial | In Delivery | Nov 2020 | Large | Northern/DN
 | 4897/ 4899 | Contact details – resolution of deleted contact details and PSR data at change of shipper event | In Delivery | Nov 2020 | Large | Shippers
 | 4931 | Submission of space in mandatory data on multiple SPA files | In Delivery | Nov 2020 | Medium | Shippers
 | 4801 | Additional info into DES | In Delivery | Nov 2020 | Medium | Shippers
 | 4871b | Ratchet regime changes part B | In Delivery | Nov 2020 | Large | DN
MiR Drop 8 | 5181 | Acceptance of consumption adjustments where meter point moved after meter set to dead | In Delivery | Nov 2020 | Small | MiR Delivery
 | 5118 / 5174 | Service sustaining activity – Change how actual MR data is populated in UK Link / Agreed FINT Replacement Reads Incorrectly Triggering Rolling AQ Calculation | In Delivery | Nov 2020 | Small | MiR Delivery

## Slide 47: UK Link Allocated Changes - Continued
Confirmed Release | XRN | Change Title | Current Status | UK Link Release Date | Complexity | Finance
MiR Drop 9 | 5135 | DNO and NTS Invoices to Shippers and DNs VAT compliance | Impact assessment | March 2021 | Small | MiR
 | 5080 | Failure to supply Gas (FSG/GSOP1) - System Changes | Impact assessment | March 2021 | Small | MiR
Jun-21 | 5093 | MOD0711 – Update of AUG Table to reflect new EUC bands | Solution Option approved | June 2021 | X-Large | Shippers
Nov-21 | 4941 | MOD0692 - Auto updates to meter read frequency | Descoped from June 21. Solution approved | Nov 2021 | Large | Shippers
 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Descoped from June 21 release. Solution approved | Nov 2021 | Large | DN/IGT/Shipper
 | 5186 | MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | Solution approval | Nov 2021 | Large | DN
 | 5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Solution approval | Nov 2021 | Medium | DN
 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | HLSO | Nov 2021 | Large to XL | Shipper
 | 5091 | Deferral of creation of Class change reads at transfer of ownership | Solution approval | Nov 2021 | Large | Shipper
 | 5180 | Inner tolerance validation for replacement reads and read insertions | Solution approval | Nov 2021 | Large | Shipper
 | 5007 | Enhancement to reconciliation process where prevailing volume is zero | HLSO | Nov 2021 | tbc | Shipper

## Slide 48: UK Link Unallocated Changes
Potential Release | XRN | Change Title | Comments | Status | Complexity | Points | Finance
tbc | 4931 | Submission of space in mandatory data on multiple SPA files | Descoped from Nov 20 Major Release. Analysis underway to determine validate new solution and identify release | Capture Complete | tbc | tbc | Nov 20 BER
tbc | 4990 | MOD0664 – Transfer of sites with low read submission performance |  | Requirements | tbc | tbc | Shipper
tbc | 4992 | MOD0687 - Creation of new charge to recover last resort supply payments | MOD not yet approved. ChMC voted to descope from June 21 release. MOD expected to be replaced/amended by Ofgem. | Capture Complete | tbc | tbc | Shipper
tbc | 5081 | No actual read present in previous class for read validation |  | Requirements | tbc | tbc | tbc
tbc | 5143 | Discharge of Cadent, WWU and NGN NDM sampling obligations by the CDSP |  | Requirements | tbc | tbc | tbc
tbc | 5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions |  | Requirements | tbc | tbc | tbc
tbc | 5188 | Interim Data loads of MAP ID into UK Link |  | Requirements | tbc | tbc | tbc
tbc | 5195 | Ceased responsibility date following shipper withdrawal (IDL) | Potential MiR Drop 10 candidate | Solution Approval | Small | 5 | MiR
tbc | 5218 | CDSP Provision of Class 1 read service |  | Requirements | tbc | tbc | DN/Shipper
tbc | 5231 | MOD0719R – Flow Weighted Average Service |  | Requirements | tbc | tbc | DN
tbc | 5235 | Include SOQ in UIG additional data report |  | Requirements | tbc | tbc | DN/Shipper
tbc | 5236 | MOD0734 – Reporting Valid Confirmed Theft of Gas into Central Systems |  | Requirements | tbc | tbc | tbc
tbc | 5238 | New Distribution Network Report – Forecast Invoice Values |  | Requirements | tbc | tbc | DN

## Slide 49: January ChMC
UK Link Future Releases Updates:
November 2021
  EQR for approval

## Slide 50: Glossary
Project Phase Abbrev. | Project Phase
FUT | Factory Unit Testing
IA | Impact Assessment
IDR | Implementation Dress Rehearsal
PIS | Post Implementation Support
PT | Performance Testing
RT | Regression Testing
SIT | System Integration Testing
ST | System Testing
Capture Artefact Abbrev. | Capture Artefact
CP | Change Proposal – an external request for a change to UK Link
CR | Change Request – an internal request for a change to UK Link
HLSO(s) | High Level Solution Option(s)

## Slide 51: Portfolio POAP

## Slide 52: 4.7 XRN5110 - Nov 20 Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | PIS Progressing through first usage plan 34 instances of first usage have been captured out of a total of 107 planned across all changes 4 defects have been raised – all defects have been fixed and deployed 10 incidents have been raised in total – 1 outstanding Incident relates to data that had been incorrectly deleted as part of the historical cleanse job, there has been no customer impact and the data was restored quickly and affected 18 MPRN’s out of 18k The daily and historical cleansing jobs are currently on hold, following the above incident and the data is being analysed to ensure the data items we are planning to delete are correct before we continue running these jobs Change Requests XRN4871b has now been implemented on the 22nd November 2020 |  |  | 
Risks and Issues | Risk: DES users may experience a downgrade in performance – monitoring access – no tickets raised so far for slowness Risk: XRN4897/99 delivery verifying 100% GDPR compliance – PIS plans in place to assure – Risk probability being understood. Expecting project to remain Amber for the entire PIS period because the above 2 risks will be monitored until the end of PIS. Risk: Deployment of defect fixes may be delayed due to the code freeze window – urgent and P1/P2 defects will still be deployed. Return to Green for above risk is that defect fixes will return to normal once the code freeze finishes on 18th January 2021 |  |  | 
Cost | BER approved - 10th June 2020 Full Business Case approved XEC – 23rd June 2020 Forecast to complete within budget |  |  | 
Resources | SME resources have been requested to support the first usage and PIS Tech Ops resource has been allocated to support PIS |  |  | 
Updates as of the 30th November 2020

## Slide 53: XRN5110 - Nov 20 Delivery Timeline & Progress
Updated as of the 30th November
TODAY

## Slide 54: PIS First Usage and Defects
Updated as of the 30th November

## Slide 55: XRN5110 - Nov 20 Scope
In Scope
  XRN 4897 - Resolution of deleted Contact Details (contained within the S66 records) at a Change of Shipper event
  XRN 4899 - Treatment of Priority Service Register Data and Contact Details on Change of Supplier Event
  XRN 4801 - Additional Information in DES
  XRN 4871b - Rachet Regime Changes
  XRN 5014 - Facilitating HyDeploy2 Live Pilot
Descoped changes
  XRN 4931 - Submission of a Space in Mandatory Data on Multiple SPA Files
  XRN 4941 - MOD 692 – Auto Updates to Read Frequency
  XRN 4992 - Supplier of Last Resort Charge Types
To be delivered by CSSC
  XRN 4780c - MAP ID
XRN5110 November 20 Release consists of 5 changes. Implementation is planned for November 2020
Updated as of the 30th November

## Slide 56: 4.8 XRN5225 – Minor Release Drop 8 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 3 changes for XRN5225 to be implemented. The proposed implementation date is 21st November 2020: XRN5181 - Acceptance of Consumption Adjustments where meter is removed XRN5174 - Agreed FINT Replacement Reads incorrectly triggering rolling AQ calculation XRN5118 - Change how the actual MR data is populated in UK Link Implementation successfully completed 21st November 2020 PIS in progress, no defects raised to date |  |  | 
Risks and Issues | No major risks to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 30th November 2020

## Slide 57: XRN5225 – Minor Release 8 Timelines
Key Proposed Dates:
Impact Assessment Complete – 28/8/20
Design Complete / signed off – 11/09/20
Build Complete – 02/10/20
Testing Complete – 14/11/20
Implementation Complete – 21/11/20
PIS Complete – 05/12/20
Updated 30th November 2020
TODAY

## Slide 58: XRN5225 – Minor Release 8 Summary
There are 3 changes for XRN5225 to be implemented. The proposed implementation date is 21st November:
  XRN5181 - Acceptance of Consumption Adjustments where meter is removed
  XRN5174 - Agreed FINT Replacement Reads incorrectly triggering rolling AQ calculation
  XRN5118 - Change how the actual MR data is populated in UK Link
Updated 30th November 2020

## Slide 59: 4.9 Minor Release Drop 9 - Status Update
28/11/20 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | There are 2 changes for Minor Release Drop 9 to be implemented. The proposed implementation date is 20th March 21: XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​ XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance Impact Assessment sessions to start 27th Nov |  |  | 
Risks and Issues | No major risks to highlight |  |  | 
Cost | Changes are being delivered as part of Minor Release Budget 20/21 |  |  | 
Resources | Weekly monitoring of Xoserve SME and Business Process Users to support testing phase and Implementation |  |  | 
Updated 30th November 2020

## Slide 60: Minor Release Drop 9 Timelines
Updated 30th November 2020

## Slide 61: Minor Release 9 Summary
There are 2 changes for Minor Release 9 to be implemented. The proposed implementation date is 20th March 21:
  XRN5080 - Failure to Supply Gas (FSG_GSOP1) - System Changes​
  XRN5135 – DNO and NTS Invoices to Shippers and DN’s VAT compliance
Updated 30th November 2020

## Slide 62: 4.10 Retro Proof of Concept – Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Delivery: Proof of Concept exercise completed Outputs and recommendations provided to CHMC in November Closure Report to be presented to ChMC in January for approval |  |  | 
Risks and Issues | None identified |  |  | 
Cost | Approval received from DN’s for BER of £270k for Proof of Concept Costs within approved budget |  |  | 
Resources | Project Team to complete closedown activities for Proof of Concept activity |  |  | 

## Slide 63: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 64: 5.1 CSSC Programme Dashboard
December 2020

## Slide 65
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme continues at Amber status. This is due to the open issues agreed with the Central Programme team. It is likely that we will reflect an Amber status until SIT and SIT NF are successfully completed and entry criteria into UEPT is met by all parties. Xoserve’s delivery status continues to be Green | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates To date, all Xoserve key internal and external milestones have been met Programme Re-plan: Following the Ogem programme re-baseline, caveated with the actions to mitigate concerns that Xoserve raised, we have been tracking these to closure with SI & DCC. Most actions are on track Costs: The central programme is standing down for the two weeks over Christmas. We will be following suit by standing down all our contractor resources during that period Missing design changes We continue to track these with DCC, who are working to close by 30th November. We believe the numbers are small following conversations at the programme level. External SIT: Testing is continuing largely to plan with volunteer licence party testing in progress currently. Xoserve have no open defects at this point External NFR SIT: There have been delays of circa 2 weeks in this phase. Si are tracking this closely and are confident that these delays will not cause any downstream impacts. Defects are open with Landmark currently which are being tracked by the SI. Xosserve will commence testing on 30/11. Internal Testing: Internal Testing continues to plan addressing consequential changes and Switching Programme CRs. Transition: Internal planning activities continue alongside engagement with the SI/ Data Migration: DM NF Testing is set to commence on 7th December, all pre-testing activities are complete. Data delivery to Landmark for the UIT phases is on track with extraction completed successfully on 21st November. DES & API: DES and Secondary API development continues to track to feed into internal testing CCMT: Engagement continues with industry following the Ofgem re-baseline |  |  |  | DMT NFR: Commence test execution Environments: Complete UEPT env provision External SIT: Continue External SIT support External NFR: Commence test execution Internal Test: Continue SIT & UAT assurance DES:& Secondary APIs Continue development and system test activities. Transition: Continue Transition planning
Programme Update

## Slide 66: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | Overall green. Settlement Data APIs SIT support in progress. Nom Enquiry API System Test in progress. DES delivery remains on track for the next instalment of screens on 14/12. User story development continues for upcoming releases alongside test engagement and development of test artefacts
 |  | Testing | The overall status remains Green, Secondary API testing has commenced for “Settlement Data” API’s. Secondary API Test – Settlement API testing currently in progress – Re-plan of delivery dates for subsequent functionality releases has been received. External SIT support in progress, no Xoserve defects are open at this point. Planning underway for all upcoming test phases such as UEPT, E2E, OT
 |  | Service Management | Impact assessment continues to understand the impact of the proposed Switching Programme SLAs alongside review of the proposed ITIL processes. Awaiting confirmed dates back from the DCC of when the remaining 1-2-1 sessions will take place to address all of the outstanding feedback against the core process maps. Planning for Operational testing is underway for the external OT phase.
 |  | Batch | The overall status is green, with testing support underway.
 |  | Gemini | The overall status is green. Planning underway to undertake a connected Gas Day testing with UK Link.
 |  | Reporting | An internal CR will be raised to incorporate the impact of one newly identified report that will need changes.
 |  | UK Link | Status continues to be Green with work underway to impact assess and deliver Switching Programme changes raised through the last few months whilst supporting test phases.

## Slide 67: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | Ofgem Capture Stage in progress and strategic approach now finalised. Original target was to complete Capture by 18th Dec 20; this is still on track. tolerance in schedule to accommodate re-planned dates. REC Departmental Impact Assessment initiated and work in progress. Dentons, Xoserve & Ofgem meeting hosted 16th Oct to discuss Protect information (PI). Concluded PI not a blocker & no legal reason why the Codes cannot interface to release data. Ofgem action taken to review Data mastery of UNC data. Both CDSP Further Services (FS) & Gas Enquiry Service (GES) ISA’s & DPIA’s submitted and still under review. External RECCo alignment meeting 16th Oct to discuss PI and agree next steps for Framework Agreement for CDSP FS and Model Service Contract for GES. Ofgem RDUG 22nd Oct: overview of Data Access Schedule and Service Definitions for CDSP FS, Electricity Enquiry Service (not did not include GES which will be published in Q1 21 along with Faster Switching Schedules)
 |  | Data Migration & Provision | CR-D016 testing has been completed with one defect highlighted against Landmark. We understand that this defect will be incorporated during the implementation of CR-D037. Smoke Testing is complete ahead of DMT NF, scheduled to commence on 07/12. Data Extraction for UEPT has been completed and on track for delivery in January.
 |  | Market Trials | Overall the workstream is green following the change in timelines to align with the re-planned UEPT/E2E timelines. There are no dependencies with the CSS plan, however, the move in CCMT reflects Xoserve customer requests. Discussions planned with the Market Trials Work Group on Friday., 27th November.
 |  | Environments | Workstream continues to be Green with all activities continuing to track to plan.

## Slide 68: Key Programme Risks (1/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62741 |  | Programme | There is a risk that SIT NFR testing will be deemed invalid if carried out as currently planned because SIT Functional would not have reached the necessary level of code stability for Non functional testing to be carried out leading to additional costs related to resources and environments required to support further cycles of NFR testing once a stable code level has been achieved. High volumes of defects are currently being found in SIT which in turn is impacting progression and therefore delays in completing the SIT cycles required to establish a suitable level of code stability. The current timelines still plan for NFR testing to be carried out prior to the completion of sufficient functional SIT required to establish a stable code set. | Escalate to the SI via all established forums to instigate a near term plan review to ensure these phases are re-planned appropriately. | This risk is still relevant and will continue to be monitored until SIT is complete.. | 03/03/21
62448 |  | Data Migration | There is a risk that Xoserve's solution delivery is incompatible with the CSS being delivered by Landmark because of poor version control and ambiguity as to which is the live version of the CSS Interface Design Specification that the CSSP have built to, leading to avoidable defects arising in SIT and the subsequent rework required by one or both parties. | Confirm with SI the correct version of this document and support them in improving the version control in future | Mtgs held with DCC, as well as project mtgs with SI and DCC. We have explained the issue in detail and the potential impact. This will now be escalated as there seems to be not much appetite to progress this by the CSSP. | 27/11/20

## Slide 69: Key Programme Risks (2/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55513 |  | Programme | There is a risk that in the Programme participants might interpret business rules differently because business rules underpinning the CSS Interfaces have not been published alongside the interface document as well as discrepancies between business rules defined within REC and captured in ABACUS. Leading to significant process mismatches at a later stage (i.e. SIT, UEPT) and potential rework and timeline slippages. | Xoserve to publish design assumptions as part of the RAID reporting to the SI to ensure visibility of Xoserve design assumptions around business rules and processes. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 27/02/21
61894 |  | Service Management | There is a risk that the CSS proposed SLAs do not align to current service model/SLA's because DCC/Ofgem are proposing a new set of SLA's for all parties regardless of existing arrangements, leading to target operating model changes and potential contractual changes with 3rd party suppliers (considerable increase in operational cost) | Our working assumption is that existing SLAs will prevail however, there are ongoing discussions taking place with DCC to understand their expectation. REC review - no such SLA's imposed on us currently. | Update from meeting held on 17/11 • Tony advised that within the response, parties should confirm a) that the incident is in their scope b) provide acceptance of the incident c) detail high level actions taken d) change the status from New to In Progress. DCC will provide written clarification to Xoserve around what is expected within the response time. • DCC advised that they fully expected push back from all parties around the SLAs. Xoserve will provide DCC with high level risks around the proposed SLA’s whilst continuing with an internal impact assessment. We all agreed that the SLAs do not stop the processes being developed and agreed. • DCC are currently working on creating scenarios for each priority level which will be shared with parties. This will also provide clarity around some of the terminology used within the descriptions. Awaiting further info from DCC. In the meantime, we have an internal session planned to map out the types of incidents that we think we could receive and align to priority level. | 31/12/20

## Slide 70: Key Programme Risks (3/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
55549 |  | Programme | There is a risk that that the approval of the CSS Physical Design does not take into consideration the complete E2E impacts of the Switching Programme because the CSS design is solely focused on the core CSS and primary interactions with CSS. Leading to an inaccurate critical path being followed for the Programme and subsequent downstream delays to the delivery timeline. | 1. Raise with Ofgem to identify owner/RACI 2. E2E CSS design needs to be in place involving all components/systems/interactions which needs to be form the architectural baseline that the Programme is governed against. | This is likely to become more evident as tests such as connected 'Day in Life processing of CSS' is undertaken. Leaving this risk to be monitored | 26/02/21
63929 |  | Data Migration | There is a risk that low level tasks will be difficult to plan for and track because of the new SI approach, whereby the CSSIP includes summary level activity with detailed tasks being added to GetOrganised leading to low/granular level activity not being baselined, and moving around without warning or notice. | Review with the SI | SI has confirmed that this risk is also being assessed internally. The current view from the SI is that planning will be undertaken in MSP with detailed activities tracked via GetOrganised. Awaiting confirmation of this approach. | 27/11/2020
63538 |  | Programme | There is a risk that all CRs (particularly those raised in the early phases of the Switching Programme), may not been incorporated into design and build by the relevant parties because these CRs might have not been incorporated correctly into requirements leading to additional efforts required to incorporate these CRs and testing through the relevant test phases (and as a subsequence delays to already delayed timelines. | Escalate to the SI to revisit the traceability exercise to identify any gaps (if any) and reflect the impacts of these CRs on the plan | Latest updates from DCC indicate that their initial assessment will be completed by end November. | 30/11/20

## Slide 71: Key Programme Risks (4/4)
REF | RAG | WORKSTREAM | DESCRIPTION | MITIGATING ACTIONS | LATEST UPDATE | TARGET RESOLUTION DATE
62942 |  | Programme | There is a risk that Xoserve systems will be out of sync with CSS during British Summer Time because CSSP intend to use UTC within the CSS solution and both UK Link and Gemini are believed to use BST leading to incorrect reporting of switches and all relevant data from Xoserve systems during the period where BST is one hour ahead of UTC. | Ofgem have now made a decision that BST will continue to be used across the gas industry so a CR is expected requiring Landmark to make the necessary changes to CSS. | Risk to remain open until CR is tested. | 31/12/20
62695 |  | Service Management | There is a risk that Xoserve is not aware of changes made to the core Service Management processes because of DCC not providing updated process maps leading to re-work to review the revised DCC process maps and update ours accordingly. | Requested copies of the revised process maps to review | Continue to work with DCC to obtain responses to the questions raised against the process maps, The processes have gone through approval within Design Forum - need to understand how any changes will be communicated to parties. | 18/12/20
63646 |  | Service Management | The DCC will be establishing a Service Review. There is a risk that Xoserve will be misrepresented because the DCC have not confirmed what the reporting requirements are for this forum leading to to the Review not providing an accurate view to market participants and a reputation impact on Xoserve. | XOS will push DCC for clarity within the monthly forums. We have requested that this is added as an agenda item within the October forum. | Within the November forum, DCC advised that CSS SMS will be single source of the truth. Reports will be built into the CSS SMS, these can be extracted by SP for further reporting. These will be tested as part of OT. Will continue to monitor this to ensure that we fully understand our responsibilities. | 31/12/20
63645 |  | Service Management | There is a risk that the Performance Assurance board will be formed to assure that that Switching Service is meeting market Participants expectation. There is a risk that Xoserve will be unable to provide the appropriate supporting information in the required timescales because DCC have not confirmed what Service Providers will need to feed into the board and it was discussed at the last Switching - Monthly Engagement Session that this board could ask for anything leading to the Performance Assurance Board not providing an accurate view to market participants and this having a reputational impact on Xoserve as the required information could not be provided in time. | XOS will push DCC for clarity within the monthly forums & 1:1 sessions | Sarah Jones who represents the REC provided a link to the PAB within the monthly forum last week. An internal session will be set up to review. | 31/12/20

## Slide 72
High Level Plan

## Slide 73: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Uplift to the Code of Connection | CR-0046 | £0.00 | 09/11/2020 | Awaiting Decision

## Slide 74: Switching Programme CR Position – CRs not impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | £0.00 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | £0.00 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 | £0.00 |  | On Hold
Introduction of Validation Message to Logical Mode | CR-D005 | £61,000.00 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | £0.00 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | £0.00 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | £0.00 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | £0.00 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | £0.00 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | £0.00 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | £0.00 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | £3,500.00 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | £0.00 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | £0.00 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | £0.00 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | £0.00 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 | £0.00 |  | Not Received
CSS Role-based access control (RBAC) | CR-D031 | £48,530.00 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 | £0.00 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | £0.00 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | £0.00 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | £0.00 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | £0.00 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | £0.00 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | £0.00 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | £0.00 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 |  | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | £0.00 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | £0.00 | 13/11/2020 | On Hold
CSS Environments for Faster Switching Enduring Service | CR-D050 | £0.00 |  | Not Received
Changes to Data Validation Rules | CR-D051 | £0.00 |  | Not Received

## Slide 75: 5.2 Xoserve IX Refresh
Customer Update
December 2020

## Slide 76: IX Refresh Customer Update
The project is not currently being impacted by COVID-19 restrictions
The project end date is February 2021. Our current run rate is tracking a January 2021 completion
The project is targeting to complete all physical installations by 30th November.
  Currently there are 6 sites (3%) that will miss this date
  Remaining 6 sites on track to complete prior to December Change Freeze (within project tolerance)
80% of all migrations have been completed
Project team have engaged with our legacy service provider to secure extension terms, if needed.
  Agreement in place to extend support past February 2021
  Minimum 3 month extension
  A decision will be made mid-December
  Project needs customer support to ensure all remaining sites are migrated by February
If you have any questions or concerns, please reach out to box.xoserve.IXEnquiries@xoserve.com

## Slide 78: Section 6: AOB

## Slide 79: 6.1 Data Catalogue
DSC ChMC – December Update

## Slide 80: Background
Long standing aspiration to review the UK Link Manual Interface Definitions
A change was previously raised – but paused in March / April due to Urgent Modification priorities
As part of the REC work we need to provide interfaces to the Programme to include within the Energy Market Architecture Repository
  Target Date for this is 1st April 2021

## Slide 81: Industry File Consolidation
Scope
Consolidate all data related to the UK Link Manual system interface files into a central repository.
Identify any issues with regards to duplicate files, Incorrect structures and data anomalies across the file base.
Raise fix recommendations to internal and external (DSC Committee) parties to ascertain priorities and resolution paths.
Progress
Data has now been pulled into a consolidated storage location.
Issues have been gathered and logged (Will be brought to DSC for future discussion).
Exercise to map individual fields to a master record (See future activities).
Work commenced on definition parsing to pull out format and value attributes.
Future Activities
Sharing of Data with RECCo to meet V2.0 obligations, due Sept 2021.
Processes for updating and transferring data with RECCo as a business as usual function.
Any remedial fix activities after agreement with concerned parties.
Exposure of the Data through on-line channels.
Augmentation of ‘Plain English’ descriptors to aid the participant bases understanding.
Automated generation of file meta-data standards.

## Slide 82: Industry File Consolidation – Example Issues
Issue | Examples
Inconsistent file naming conventions | Type 1: DCF - AI_O_Discountinued_Confirmations Type 2: DCF - SSMP Discontinued Confirmation Notification File
Reference data in file names | - LPG_DATA_SUBMISSION SCOTIA - LPG_DATA_SUBMISSION FLOGAS - LPG - LPG_Supporting_Information
Conflicting File Purposes | TSI - Interconnector Tariff Switch Request File TSI - Transporter_Site_Visit_Submission
Missing Structure | File RTB does not have a Header or Trailer
Missing Record Types | For the RTR- REJFL Record Identifier states "This identifies the record. If the file has been rejected the value is REJFL, otherwise RESPN.". Should we include another record type "RESPN" as part of the catalogue?
Missing Meta-data | Files CNI, SNO, (Multiple others) missing, - Interface Description - External / Internal – Direction – Role - Source - Destination - Interface Pattern - Transfer Route - FS ID – Frequency
Inconsistency of Data Items | Several examples of position, naming and metadata inconsistency.

## Slide 83: Outputs
We anticipate a number of changes will be:
  Administrative only – e.g. changing the field name to make it consistent
  Functional impacting – e.g. change to formats
  Some will be somewhere in between – e.g. a change to formats but with no impacts to Users
We will need help from the industry to assess the impact of changes
  Proposing to start this via DSG starting in [January 2021] at DSG; and [February] Change Packs

## Slide 84: 6.2 January ChMC Papers
Discussion for the publishing of January ChMC papers