## Alrewas
Task | Start Date | End Date | Owner | Comments
Workgroup meeting with TUV to present initial findings | 2021-08-04 | 2021-08-04 | Cadent
Meter Error Report creation | 2021-08-04 | 2021-09-27 | Cadent
Workgroup meeting with TUV to present final report. | 2021-09-27 | 2021-09-27 | Cadent
Any minor amendments required following presentation of report. | 2021-09-27 | 2021-10-01 | Cadent
Preparation of reconciliation request | 2021-10-04 | 2021-10-12 | National Grid
DoA Sign Off for reconciliation | 2021-10-13 | 2021-10-15 | National Grid
Analysis of final data to provide indicative charges for shippers | 2021-10-25 | 2021-11-05 | Correla/Xoserve | Delay between receipt and calculation of indicative charges is due to prioritisation of the current months invoice production
Indicative charges provided to shippers | 2021-11-08 | 2021-11-08 | Correla/Xoserve | Contact details required for those who wish to receive
Amendment Invoice issued containing the Alrewas SMER UGR Charges | 2021-11-24 | 2021-11-24 | Correla/Xoserve