## Slide 1: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS MAR 2022 – MAR 2024
MARCH 2022

## Slide 2
Programmes & Projects 2022-2024 |  |  |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | XRN5393 Gemini Spring 22 Release |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | PM Hannah Reddy | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Emma Catton | XRN5368.2 Single Sign on Experience |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.3 API Enhancements |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.1 Control M and Batch Processing |  |  |  |  |  |  |  |  |  |  | 
 |  |  | XRN5368.5 Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS MAR 2022 – MAR 2024
Design to PIS -Dec 21 to June 22
Design to PIS – Sept 21 to June 22
API - Design to PIS – Jan 22 to May 22
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk
Testing – Dec 21 to Mar 22
PIS – From Apr 22 to Jun 22
Change Deployment
Apr 22
Pre-implementation/IDR
Mar 22 to Apr 22
Design to PIS - Nov 21 to Jul 22
Go Live
29th Apr
Go Live
30th Jun
Go Live
29th May
Control M - Design to PIS – Jan 22 to Apr 22
Go Live
8th May
Prod ChG 1
Go Live
15th Mar
ChG 2
Go Live
1st Mar
ChG 1
Contingency
12th Jun
Go Live
18th May
Prod ChG 2
Go Live
3rd Apr – Part B
Contingency
10th Apr – Part B
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.