## Slide 1: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, UK Link build phase completed on 30/09 as per plan. Currently on track to complete system testing phase 28/10, with UAT testing prep in progress and execution commencing on 02/11 Progress update: UK Link build completed on 30/09 DDP build for XRN4990 in progress, delivery on track to complete by 20/01 System Testing on track to complete 28/10 User Acceptance Testing (UAT) preparation in progress, test case execution to commence on 02/11 Decision in October ChMC: None |  |  | 
Risks and Issues | XRN5298: There is a risk that UNC Modification 0799 will not be approved, leading to delays in build activities or a need to rework the proposed solution being delivered under XRN5298 in its entirety. While ChMC approved the move to deliver this change at risk under the assumption that the MOD will be approved, any potential regret spend associated with this change should this not be the case increases as build activities continue to progress. Update - SGN confirmed that Ofgem are due to provide an update on the status of the Modification w/c 24/10/22. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0687 - Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process - Inner for replacement reads and read insertions​ XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 27th October 2022
Complete
On Track
At Risk
Overdue