## Slide 1: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber. XRN 5472 (Weather API) descoped from March -23 and will be delivered at a later date. Design phase continues for both XRNs scoped for this release. Build and testing progressing as planned for 5143 and 5379. Return to green is completion of design and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Project Startup and Initiation phase complete Project Build phase complete UK Link SIT & UAT Testing execution complete as planned for 5379 Technolog onboarding underway as DM SP NDM SP procurement continues Weekly engagement sessions with Technolog including resolving of design queries and supporting integrated testing Decision in March ChMC: None |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | 68566 (Issue) Delay to test commencement for March-23 impacting delivery plan, descope of 5472 alleviated pressure on timeline, risk remains open in case of further impact due to design continuing 68488 & 68489: (Risk) The design has not yet completed for the changes in this release, therefore the aspirational delivery timescales are at risk 68126: (Risk) The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) |  |  | 
Slide updated on 21st February 2023
Complete
On Track
At Risk
Overdue