## Slide 1: Change Management Committee
March 2023

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: General Change Budget BP22 YTD

## Slide 4: Forecasted Year End Spend (BP22)
The graph below illustrates the current forecast for financial year-end utilisation of the General Change investment budget (BP22) – this is subject to change should ChMC approve further change delivery
Total committed spend has decreased by £92,473 following approvals in February ChMC
Link to ChMC Change Budget spreadsheet
Chart: Committed to date per constituency
| Shipper | DN | IGT | NTS
Committed | 1923223.5 | 614613.5 | 13821 | 0
Uncommitted | 43938 | 569954 | 171347.5 | 69102.5

## Slide 5: Change Pipeline

## Slide 6: Change Delivery Plan January 23 – April 24
February 23 - Major Release (XRN5533)
XRN4900, XRN4978, XRN4990, XRN4989, XRN4992b, XRN5298
Jan-23
Aug-23
June 23 - Major Release (XRN5562)
XRN5091, XRN5186
Apr-23
Dec-23
Apr-24
November 23 – Major Release
XRN5482, XRN5604, XRN5605
XRN4713
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative Implementation Date – Changes are scoped for delivery – Funding and/or Implementation Date not yet approved by ChMC
= Delivered on Target Implementation Date
Delivery Key
Slide produced 22 January 2023
March 23 - AdHoc Release (XRN5575)
XRN5379, XRN5143
XRN5595
XRN5555
February 24 – Major Release
XRN5607, XRN5573B
XRN5535A
XRN5567
XRN5602
XRN5606
XRN5454
XRN5547

## Slide 7: Change Pipeline - Delivery Plan - January 2023 – May 2023
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Delivered / Firm / Indicative
5555 | Amend existing Large Load Site Reporting | SGN | DN | DN | N/A | 31st January 2023 | Adhoc | Delivered
4900 | Biomethane/Propane Reduction | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
4978 | Notification of Rolling AQ Value (following Transfer of Ownership between M-5 and M) | British Gas | Shipper | Shipper | £90.6k | 25th February 23 | Major | Firm
4990 | Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 – MOD 0664 | SSE | Shipper | Shipper | £232k | 25th February 23 | Major | Firm
4989 | Residual AMT activities | CDSP | Shipper | Shipper | N/A | 25th February 23 | Major | Firm
4992 | XRN4992 - Modification 0687 Clarification of Supplier of Last Resort (SoLR) Cost Recovery Process | Total | Shipper DN | Shipper DNO | £108.7k | 25th February 23 | Major | Firm
5298 | H100 Fife Project – Hydrogen Network Trial | SGN | Shipper DN | DN Decarb | N/A | 25th February 23 | Major | Firm
5595 | Changes to the REC Switching Operator Outage Notification Lead Time (R0055) | Xoserve | Shipper | N/A | N/A | 25th Feb 23 | Major | Firm
5535A | Processing of CSS Switch Requests Received in ‘Time Period 5’ | Xoserve | All DSC Customers | Shipper | £44k | 10th March 23 | Adhoc | Firm
4713 | Actual read following estimated transfer read calculating AQ of 1 | Npower | Shipper | Shipper | £7k | March 2023 | Adhoc | Indicative
5379 | Class 1 Read Service Procurement Exercise - MOD0710 (DM Sampling) | Xoserve | Shipper DN | Shipper | £150k | 1st April 2023 | AdHoc | Firm
5143 | Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP | Cadent | DN | WWU, Cadent, NGN only | £75k | 1st April 2023 | AdHoc | Firm
5606 | Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers (Modification 0813) | NGT | NGT Shipper Supplier | NGT | N/A | Immediately Following Ofgem Decision | Adhoc | Indicative
5602 | Releasing of unused capacity under a specific set of circumstances (Modification 0818) | NGN | Shipper DN | DN | N/A | Immediately Following Ofgem Decision | Adhoc | Indicative

## Slide 8: Change Delivery Plan - June 2023 – February 2024
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5091 | Deferral of creation of Class change reads at transfer of ownership | EDF | Shipper | Shipper | £200k | 24th June 23 | Major | Firm
5186 | *MOD0701 - Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs | NGN | Shipper DN | Shipper DN | £200k | 24th June 23 | Major | Firm
5454 | SoLR Reporting Suite | EDF | Shipper | Shipper | Tbc | July 23 | Tbc | Indicative
5547 | Updating the Comprehensive Invoice Master List and INV template | Eon | Shipper DN | Shipper | Tbc | July 23 | Tbc | Indicative
5482 | Replacement of reads associated to a meter asset technical details change or update (RGMA) | Scottish Power | Shipper | Shipper DN | £300k | November 23 | Major | Indicative
5604 | Shipper Agreed Read (SAR) exceptions process (Modification 0811S) | SEFE | Shipper | Shipper | Tbc | November 23 | Tbc | Indicative
5605 | Amendments to the must read process (IGT159V) | Centrica | Shipper IGT | Shipper IGT | Tbc | November 23 | Tbc | Indicative
5567 | Implementation of Resend Functionality for Messages from CSS to GRDA (REC CP R0067) | Xoserve | All DSC Customers | Shipper | £93k | Awaiting REC Decision – expected December 23 | Adhoc | Indicative
5607 | Update to the AQ correction processes (Modification 0816S) | EON Next | Shipper DN IGT | Shipper | Tbc | February 23 | Major | Indicative
5573B | Updates to the Priority Consumer process (as designated by the Secretary of State for Business, Energy, and Industrial Strategy - BEIS) | Xoserve | Shipper DN IGT | Tbc | Tbc | February 23 | Major | Indicative
*XRN5186 (Mod0701) - Implementation proposed to be deferred until November 2023

## Slide 9
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
5316 | Rejecting Pre LIS Replacement Reads | Xoserve | Shipper | N/A | N/A | Tbc | Tbc | N/A
5531 | Hydrogen Village Trial | SGN | All DSC Customers | DN Decarb | Tbc | Tbc | Tbc | N/A
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | Tbc | Tbc | Tbc | N/A
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Tbc | Tbc | Tbc | N/A
5585 | Flow Weighted Average Calorific Value - Phase 2 Service Improvements | Cadent | DN | DN | Tbc | Tbc | Tbc | N/A
5614 | Improving IGT SMP New Connection Process to support accurate and timely Supplier Registrations | BUUK | Shipper IGT | Shipper IGT | Tbc | Tbc | Tbc | N/A
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | Tbc | Tbc | Tbc | N/A
Change Backlog Details
Title | Description | XRN | Proposer | Impact/Funding | Status | Release Type | Priority
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | TBC | Low
R0073 | Introduction of a Housekeeping Change Proposal Process | N/A | Gemserv | - | Preliminary Assessment | TBC | Low
R0088 | Make Shipper NExA values available on the GES portal | N/A | Xoserve | - | New | Major, June 23 | Medium
REC IA Demand – Priority Change

## Slide 10: Change Backlog – On Hold Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Implementation Date | Release Type | Firm / Indicative
4914 | *Mod0651 – Retrospective Data Update Provisions* | Cadent | Shipper DN | Tbc | £1.8m – £2.4m | Tbc | Major | N/A
5144 | Enabling Re-assignment of Supplier Short Codes to Implement Supplier of Last Resort Directions | Xoserve | Shipper DN IGT | Tbc | Tbc | Tbc | Tbc | N/A
5187 | MOD0696 - Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | Gazprom | Shipper DN | Shipper DN | Tbc | Tbc | Tbc | N/A
5345 | Deferral of creation of Class change reads for DM to NDM and NDM to DM sites at Transfer | CDSP | Xoserve | Shipper | Tbc | Tbc | Tbc | N/A
5453 | GSOS 2, 3 & 13 Payment Automation | SGN | Shipper DN | DN | Tbc | Tbc | Tbc | N/A
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | Tbc | Tbc | Tbc | N/A
5473 | Meter Asset Details Proactive Management Service | CDSP | Shipper | Shipper | Tbc | Tbc | Tbc | N/A
*Mod0651 : 28.01.23 - Change Status remains on hold and will be reviewed on a monthly basis with ChMC – in line with request from UNCC

## Slide 11: DSC Change Pack Consultation Plan (2 month view)
March-23
April-23
May-23
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
Delivery Key
Slide produced 22 February 2023
XRN5454 – SOLR Reporting Suite
XRN5602 - Releasing of unused capacity under a specific set of circumstances (Modification 0818)
XRN5482 - Replacement of reads associated to a meter asset technical details change or update (RGMA)
XRN5605 - Amendments to the must read process (IGT159V)
XRN5604 - Shipper Agreed Read (SAR) exceptions process (Modification 0811S)
UK Link Manual – X09/X10 Record Cosmetic Update
For Information
XRN5607 – Mod0816 – Updates to the AQ Correction Process

## Slide 12: REC Change
8th March 2023

## Slide 13: Introduction
The following 9 slides have been included in this months ChMC pack to give you an overview of the ongoing REC Changes, we have broken these down into the following sections:
In progress – we are currently progressing through the Change journey
Under Prioritisation Review by REC Code Managers – due to CM workload/prioritisation
This month we have included a line describing, from our perspective, the expected Change impact on us as the CDSP and/or GRDA
Note: We are currently undertaking a review of all REC Change and have began removing Changes which we have confirmed have no impact to Gas services. In the coming months, we will continue to monitor the Changes listed and add/remove from this pack as required.
We have included an additional slide at the end of this pack which outlines the approach to be taken regarding resources to account for the increase in REC Change, as requested by the committee last month.
Further information on the Changes can be found on the REC Portal

## Slide 14: Overview of In Progress REC Changes (high level)
Chart: 
| Approved awaiting implementation | Consultation | Solution development | Party Impact Assessment | Final Assessment | New
In Progress | 4 | 1 | 3 | 1 | 2 | 1
Chart: All Change
| Monitoring | Currently working on | Upcoming activity | XRN Changes
All Change | 2 | 5 | 3 | 2
In Progress Change
6

## Slide 15: REC Change Pipeline – In progress
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0025 | Service Provider Performance Charges (DCC) | N/A | Deloitte (RPA) | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | 
This Change was raised to introduce Service Provider Performance Charges linked to performance against service levels defined in the REC. We are monitoring this change as it references future performance charges on other service providers – including the GRDS. |  |  |  |  |  |  |  |  | 
R0047 | Metering Code of Practice Consolidation Review | N/A | RECCo | - | Approved - awaiting implementation | 01/04/2023 – Proposed Implementation date | Standalone | High | N/A
This Change was raised to to consolidate the current Metering Codes of Practice into a single set of arrangements. Although we are not a directly impacted party, if and when this takes place, we may need to adapt our interactions with MEMs, DNOs and Suppliers. |  |  |  |  |  |  |  |  | 
R0052 | GES Service Definition Document | N/A | Deloitte | GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major, Feb 23 | Medium | N/A
This Change was raised to align the frequency of certain reports detailed in the GES Service definition with the Retail Energy Code. As the GES Service provider, we need to monitor the outputs of this Change to ensure that everything is aligned following implementation. |  |  |  |  |  |  |  |  | 
Please note that we have provided our view of the Change summary and impacts however we recommend that DSC Customers monitor the REC Portal to form their own opinion regarding the impact to their organisation
Currently working on
Key:
Upcoming
Monitoring

## Slide 16
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0055 | Switching Operator Outage Notification Lead Time | XRN 5595 | DCC | GRDS, GES | Approved - awaiting implementation | 24/02/2023 – Proposed Implementation date | Major, Feb 23 | Medium | N/A
This is a documentation Change that was raised to align the outage notification time. The original time was 10 working days (WD) however in the CSS Provider’s (DCC) processes and the Switching Operator Change Management Process Category 3 document the notification time is 8 WD. As a result of this Change, as a Switching Data Service Provider, we need to amend internal documents that include processes surrounding interactions with the CSS Provider, to allow for the revised 8WD notice. |  |  |  |  |  |  |  |  | 
R0063 | Addition of key information to all Service Now tickets | N/A | St Clements Ltd (on behalf of DNOs) | - | Solution development | 21/02/2023 – Presenting solution to the Change Panel | TBC | Medium | N/A
This Change was raised to improve the information that’s included on DCC’s Service Now Tickets which have been asynchronously rejected. We interact with DCC via SNow so we need to monitor and input into development. |  |  |  |  |  |  |  |  | 
R0067 | Introduction of CSS refresh functionality | XRN 5567 / UNC Mod expected | Capgemini (RTS) | GRDS | Party Impact Assessment | 01/03/2023 – Detailed Impact Assessment closeout (this is the 2nd DIA that has been released as a result of replanning) | Legal text – Major, June 23 Technical Change - Standalone | High | 
This Change will introduce a resend and refresh functionality to help with the message interactions between the CSS and Switching Data Service Providers. Currently, there are cases were messages are being received after Gate Closure or not being received at all. We are one of the impacted Service Providers which means this Change is very important to us so that we are able to complete customer switches successfully. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring

## Slide 17
Currently working on
Key:
Upcoming
Monitoring
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0070 | Provision of Enduring Test Environments | N/A | Capgemini | GRDS, GES | Solution Development | 02/2023 – Awaiting Impact Assessment from Code Managers | Standalone | High | N/A
This Change was raised to introduce an obligation under the Retail Energy Code for the CSS or the Switching Operator (SO) to provide enduring test environments for REC parties to make the necessary system changes for REC Change Proposals (CPs) or internal system updates. We need to monitor this to ensure that the obligations on GRDS are understood, and that we contribute to the development of this Change. |  |  |  |  |  |  |  |  | 
R0073 | Introduction of a Housekeeping Change Proposal Process | N/A | Gemserv | - | Final Assessment | 24/02/2023 – Consolidated Consultation Response and Final Change Report published | TBC | Low | N/A
This Change was introduced to create a process which allows parties to amend typographical errors, formatting, and consistency errors (such as Paragraph numbering), out-of-date references to documents and updating addresses (including email) in the Retail Energy Code. Although it is a housekeeping Change, there are also amendments to legal text that we need to be involved in. Its important we monitor the outputs of this Change to capture any amendments that might be needed to our internal documents as a result, or if it creates inadvertent Change. |  |  |  |  |  |  |  |  | 

## Slide 18
Currently working on
Key:
Upcoming
Monitoring
Title | Description | XRN / UNC Mod | Proposer | Impact/ Funding | Status | Next Action date | Release Type | REC Priority | Attachments
R0074 | Release of Community View Data Items to MEMs in GES | N/A | Xoserve | GES | Final Assessment | 24/02/2023 - Changes to the DAM 27/02/2023 – Functional Change planning | Changes to the DAM – Major, Feb 23 Functional Change - TBC | High | 
This Change was raised to enable MEMs to ‘Community View’ access to a limited set of data in the GES, for sites where they are not the appointed MEM. As the GES Provider we are heavily involved in the planning and delivery of this Change. |  |  |  |  |  |  |  |  | 
R0091 | Clarifications to the Theft Detection Incentive Scheme | XRN 5236 MOD 0734 | Deloitte (RPA) | - | Consultation | 10/03/2023 – Consultation closeout | TBC | Low | N/A
Following implementation of UNC Mod 0734 the RECCo are responsible for providing details of Confirmed Theft to the CDSP. We expect this to be the REC change that implements this obligation. |  |  |  |  |  |  |  |  | 

## Slide 19
Title | Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority | Attachments
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | N/A | DCC | - | Solution development | 10/03/2023 -Preliminary Change Report and consultation closeout | TBC | Low | 
Currently, the CSS Provider is obligated to undertake system organisation control type 2 (SOC2) assessments on the CSS’s cloud-based infrastructure. This Change was raised to assess if the SOC2 assessment provides a proportionate level of assurance or the best value for money and if it should be change to ‘independently assessed’. We are monitoring to determine whether there are impacts to GRDS / GES. |  |  |  |  |  |  |  |  | 
R0088 | Make Shipper NExA values available on the GES portal | XRN 5186 MOD 0701 | Xoserve | - | New | w/c 27/02/2023 – Lead analyst being assigned 02/2023 - Impact assessment | Major, June 23 to align with | Medium | 
XRN 5186 - Modification 0701: Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs makes additional information available to GES Users which require reflection in the REC. Although all of the technical change has already been developed. |  |  |  |  |  |  |  |  | 
Currently working on
Key:
Upcoming
Monitoring
REC IA Demand

## Slide 20
REC Related XRN Changes
Description | XRN | Proposer | Impact/ Funding | Status | Next Action date | Release Type | Priority
Processing of CSS Switch Requests Received in ‘Time Period 5 | XRN 5535A | Xoserve | GRDS | In Delivery | 13/03/2023 – Detailed Design Change Pack for approval | TBC | High
Resolution of Address Interactions between DCC and CDSP | XRN 5546 | Xoserve | GRDS | Under development | Regular conversations with DCC as work is ongoing | TBC | Medium
Currently working on
Key:
Upcoming
Monitoring

## Slide 21: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0049 | Intellectual Property Rights and Services Data Main Body changes | Initial Assessment
R0051 | Switch Request Objections (Change of Occupier) | Initial Assessment
R0056 | EES/GES additional service request for Housing Associations to be added to the Matrix | Initial Assessment
R0059 | Maintenance of Qualification Schedule Change | Initial Assessment
R0068 | REC Data Protection Changes | Initial Assessment
R0069 | Amendments to Sample Access Agreement | Initial Assessment
R0071 | DCC access to EES and GES | Initial Assessment
R0075 | Enabling Software Product Qualification | Initial Assessment
R0080 | Improvements to "Failed to deliver" CSS messages | Initial Assessment
R0081 | CSS Market message retry strategy | Initial Assessment
R0082 | Formalising the Submission of PPMIP Unallocated Transaction Report (UTR) Files | Initial Assessment
R0084 | Housekeeping changes to the approved legal text for R0047 | Initial Assessment
R0085 | Switching Programme Designation of the Steady State Commencement Date | Initial Assessment
R0087 | MAP GES data access | Initial Assessment

## Slide 22: (Gas) REC Change Pipeline - Under Prioritisation Review
Title | Description | Status
R0089 | Removal of Pre-COVID AQ Value from Data Access Matrix | Initial Assessment
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | Initial Assessment
R0093 | Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | Initial Assessment
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | Initial Assessment
R0095 | Changes to allow DNOs to reinstate disconnected MPANs | Initial Assessment
R0096 | CSS Message Regeneration Functionality | Initial Assessment
R0097 | Consequential Change for CSS Smart Meter Data Retriever Appointments | Initial Assessment

## Slide 23: For Information
Background
In October-22, ChMC agreed to include 350k in BP23 (within the General Change budget) for use against REC Change, specifically to mitigate against the expected increase in REC Change demand, as at the time, this was unknown.
Forward Projections
The REC have advised that this upward trend is not looking to tail off but potentially increase further as the year progresses, as well as expressing the desire for increased engagement with the development of change.
Observations
In recent months, we’ve seen the number of REC Change Requests being raised exceed even the expected increase, with a large number awaiting initial assessment by the REC Code Manager.
DSC Risk
As a result, without increasing resources to carry out impact assessments, DSC change development will suffer and get deprioritised or even cease entirely as REC change takes priority.
Driver
This includes an increasing backlog on Gas related change proposals that ultimately will require varying levels of Impact Assessments to be carried out by the CDSP within the formal timescales set out in the REC.
Mitigation
CDSP will, from April-23, drawdown on the General Change budget (BP23) to increase its ability to progress REC Impact Assessments ensuring its continued conformity to regulatory obligations, while still being able to develop DSC related change.

## Slide 24: Section 3: Capture

## Slide 25: New Change Proposals
For Approval
XRN5615 - Establishing/Amending a Gas Vacant Site Process (Modification 0819)
For Information
XRN5579A - Long-Term Flow Swap Automation
XRN5622 - Amendments to v28 of the Service Description Table

## Slide 26: XRN5615 - Establishing/Amending a Gas Vacant Site Process (Modification 0819)
Customer Parties | Impacted/Voting Party
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission (NGT) | 
IGTs | X
This vote is to approve the change into development | 
DSC Service Area Associated Funding Splits | Service Area 2: Monthly AQ Processes (100% Shipper) Service Area 3: Manage updates to customer portfolio (90% Shipper, 10% DNO) Service Area 10: Invoicing Customers (88% DNO, 12% NGT)
Proposed Funding split from Proposer | 50% Shipper 50% DNO
Change Description - Link to CP
This Change Proposal has been raised to deliver the requirements outlined in Modification 0819 Establishing/Amending a Gas Vacant Site Process. Modification 0819 aims to create a new process for Vacant Product Class 4 Non-Daily Metered (NDM) sites which would allow Shippers to receive commodity and performance relief (immediately) and capacity relief (after 12 months at vacant status) for sites in their ownership. A SMP must meet the Vacant Site criteria outlined in Modification 0819 and associated guidance documentation for the Shipper to have the ability to effectively manage their Settlement Performance Obligations and Transportation Costs.
Change Type | Regulatory
Priority | High
Proposer | Centrica

## Slide 27: XRN5579A - Long-Term Flow Swap Automation
Customer Parties | Impacted Parties
Shipper | 
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | 
For information | 
DSC Service Area Associated Funding Split | Service Area 14: Gemini Services 100% NGT
Change Description - Link to CP
This is the first Change proposal raised against the umbrella CP XRN5579, which covers regulatory, or business value change initiated from November 2022 to March 2023. NGT would like to review the options for automating all or part of the Long-Term Flow Swap process in Gemini Exit (only) for Flow Swaps with the Distribution Network Operators. Currently the Long-term flow swap process involves a lot of manual effort which results in a risk of errors and re-working which then impact National Gas Transmission’s (NGT) reporting obligations through RRP to Ofgem. Please note - a change Pack for XRN5579A has been issued and is included within Section 4 of the slide pack.
Change Type | Regulatory
Priority | High
Proposer | National Gas Transmission

## Slide 28: XRN5622 - Amendments to v28 of the Service Description Table
Customer Parties | Impacted Parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | X
For information – for approval at CoMC 15/03/2023 | 
DSC Service Area Associated Funding Split | N/A
Change Description (Link to CP)
This Change Proposal is to deliver a number of amendments to the DSC Service Description Table to support: 1) Amendments to the Service Description Table that are required to support Mod 0710 – Provision of Class 1 Service by CDSP 2) New Service Line to support the implementation of XRN5143 3) The Introduction of a new service Line to support XRN4990 which is part of the February 2023 Major Release 4) The introduction of a new Service Line to initiate registration in the absence of Secured active Notification from CSS
Change Type | Document Change
Priority | Low
Proposer | Xoserve

## Slide 29: Change Proposals – Post Solution Review for Approval
For approval:
XRN5547 - Updating the Comprehensive Invoice Master List and INV Template

## Slide 30: XRN5547 - Updating the Comprehensive Invoice Master List and INV Template
Solution Review Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.3 - VO - PO | Option 1: 4 Option 2: 1 |  | 
Service Area | Funding Split | Solution Impacted Parties | HLSO Cost | Proposed Delivery | Link to CP
Service Area 10 Invoicing Customers | DNO 88% NGT 12% | DNO Shipper | Solution Option 1: 35-75K Solution Option 2: N/A | Solution Option 1: Minor Solution Option 2: Adhoc | ChMC approved CP on 10/08/22
ChMC Action: | Two separate votes required. | Comments
Vote 1: Solution Option (impacting parties) Select which Solution Option (if any) to progress with into Detail Design. |  | Pease note that if approval of a solution option is reached, this will go straight into detailed design with no EQR being presented at ChMC.
Vote 2: Funding Split Agree the funding split between ChMC Constituents for the approved option. |  | 

## Slide 31: section 4. Design & Delivery

## Slide 32: Design Change Pack
For approval:
XRN5579A - Long-Term flow Swap Automation
XRN5606 - Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers Detailed Design (Modification 0813)
XRN5535A - Processing of CSS Switch Requests Received in ‘Time Period 5’
XRN5556D - CMS Rebuild Version 1.3
For information:
XRN5379 - Class 1 read service Procurement Exercise MOD 0710 - Transitional arrangements

## Slide 33: XRN5579A - Long-Term flow Swap Automation
Change Proposal | Service Area | Comments
CP is issued for information at March-23 ChMC Link to CP | Service Area 14: Gemini Services 100% | None
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.1 - VO - PO | 3 |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery. | DNOs, NGT | DNOs, NGT | March 2023

## Slide 34: XRN5606 - Revision of Virtual Last Resort User and Contingent Procurement of Supplier Demand Event Triggers Detailed Design (Modification 0813)
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery. | Shippers NGT | Shippers NGT | Adhoc (see comments)
Approval into development | Service Area | Comments
ChMC approval 11/01/2023 Link to CP | Service Area 8: Energy Balancing (Credit Risk Management) 100% NGT | Mod 0813 is with Ofgem for decision, implementation of the agreed Solution will commence following this decision
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.2 - VO - PO | No Representations received |  | 

## Slide 35: XRN5535A - Processing of CSS Switch Requests Received in ‘Time Period 5’
Approval into development | Service Area | Comments
Approved on 13/07/2022 Link to CP | Service Area 3: Manage updates to customer portfolio 90% Shipper 10% DNO | None
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.5 - VO - PO | 1 |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery. | Shipper, DNO, IGT, NGT | Shipper, DNO, IGT, NGT | Adhoc

## Slide 36: XRN5556D - CMS Rebuild Version 1.3
Approval into development | Service Area | Comments
Presented for information at ChMC on 11/01/2023 Link to CP | N/A | None
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.6 - VO - PO | 1 |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
Vote to approve the Detailed Design and progress into delivery. | Shipper, DNO, IGT, NGT | Shipper, DNO, IGT, NGT | Adhoc

## Slide 37: XRN5379 - Class 1 read service Procurement Exercise MOD 0710 - Transitional arrangements
Approval into development | Service Area | Comments
Approved at ChMC 07/07/2021 Link to CP | N/A | ChMC approved Solution Option 1 on 10/08/2022
Detailed Design Summary
Change Pack Ref | Representation Summary |  | 
 | Approve | Defer | Reject
3139.4 - VO - PO | No Representations received |  | 
ChMC Action | Voting Parties | Impacted Parties | Release
None – For Information | N/A | Shipper, DNO, IGT, NGT | March 2023

## Slide 38: Standalone Change Documents for Approval (EQR, BER, CCR)

## Slide 39: Standalone Change Documents for Approval (BER, CCR)
Document link | XRN | Voting
CCR | XRN5555 - Amend existing Large Load Site Reporting | DNO

## Slide 40: June 23 Release Scope Deferral Impact Assessment
ChMC Decision Required

## Slide 41
Impact Assessment - Deferring Implementation of XRN5186
Background
Northern Gas Networks have requested an impact assessment be undertaken by the June-23 Project Team to assess what options are available if XRN5186 (MOD0701) is deferred and implemented at a later date
Assumption
Four options have been identified and were considered within this Impact Assessment
The options and costs provided have considered an alternative implementation date for the related June-23 scope
Considerations
Impacts on Release capacity for November-23 have not been assessed at this stage
Potential that moving June-23 could lead to delay in delivery of other DSC change
Increase risk profile of November-23 if multiple changes are progressed in tandem
Options
Remove XRN5186 from June-23 Release after completion of related project deliverables up until 28/04
Remove XRN5186 from June-23 Release after completion of related project deliverables up until 09/06
Stop the delivery of June-23 Release after completion of all project deliverables up until 28/04
Stop the delivery of June-23 Release after completion of all project deliverables up until 09/06
*Options 1 and 3 were assessed but discounted as no benefit could be identified in stopping project activities earlier than is necessary to achieve the objective – i.e. both prevent project deliverables from being progressed and completed earlier than is necessary

## Slide 42
Impact Assessment – Project Plan Option Timeline
The above plan reflects that both Option 2 (Defer XRN5186) and Option 4 (Defer XRN5186 & XRN5091) would stop circa 9th June 2023
Performance Testing, Implementation Dress Rehearsals, Implementation and Post Implementation Support activities would need to be planned for delivery at a later date

## Slide 43
Options | Description | Pros | Cons | Activities required if deferred
Remove XRN5186 from June23 Release after completion of Regression Test phase *Xoserve Recommended Option* | This option will look to complete all testing (excluding Performance Test) prior to removing XRN5186 from the Release. Any outstanding activities and implementation of XRN5186 to take place at a later date De-scoped change work would stop approx. 09/06/23 | All test phases will be completed except Performance Test. Build and all test will be complete for AMT Market Flow and Gas Enquiry Service Provides additional opportunity for all DNs and Shippers to align their NExA and Capacity values Developed system code will remain stable in project track whilst alternative delivery date is confirmed Allows XRN5091 to progress and avoid delay of Shipper benefitting change Minimises regret spend to customers by proceeding with delivery of XRN5186 as far as reasonably possible whilst also delivering XRN5091 | Will lead to additional work to re-plan delivery of XRN5186 Checks will need to be performed against system code to ensure tested solution remains fit for purpose Possible risk of additional test activities (e.g. Regression Testing) Risk of knowledge loss to carry out 1st usage activities – additional effort to ensure all project resource are up to speed on project deliverables Review and possible re-test of AMT Market Flow code and integration | Environment and system code checks required Review of AMT Market Flow code and integration Performance Test Implementation Dress Rehearsal Pre-implementation activities Implementation and cut over activities Post Implementation Support Low risk that additional Build and Test activities are identified due to common system code and workflow changes to support other Release deliverables (Supply Point Administration processes)
Stop the delivery of June23 Release after completion of Regression Test phase | This option will stop the delivery of both associated changes once all testing (excluding Performance Test) have concluded. Any outstanding activities and implementation moved for both changes to a later date De-scoped change work would stop approx. 09/06/23 | All test phases will be completed except Performance Test. Build and all test will be complete for AMT Market Flow and Gas Enquiry Service Provides additional opportunity for all DNs and Shippers to align their NExA and Capacity values Developed system code will remain stable in project track whilst alternative delivery date is confirmed | Will lead to additional work to re-plan delivery of both XRN5186 and XRN5091 Checks will need to be performed against system code to ensure tested solution remains fit for purpose Possible risk of additional test activities (e.g. Regression Testing) Risk of knowledge loss to carry out 1st usage activities – additional effort to ensure all project resource are up to speed on project deliverables Review and possible re-test of AMT Market Flow code and integration Impact to Change Pipeline if entire Release is deferred Risk that additional project efforts may be identified dependent on Nov-23 Release Scope | Environment and system code checks required Review of AMT Market Flow code and integration Performance Test Implementation Dress Rehearsal Pre-implementation activities Implementation and cut over activities Post Implementation Support Moderate risk that additional Build and Test activities are identified due to common system code and workflow changes to support other Release deliverables (Meter Read and Settlement processes)
Impact Assessment – Option Comparison

## Slide 44
 | Option2 Defer XRN5186 Only | Option4 Defer XRN5186 & XRN5091
XRN5091 Approved BER Cost | £218,760 | £218,760
XRN5186 Approved BER Cost | £245,192 | £245,192
Total June-23 BER Cost | £463,952 | £463,952
June-23 Costs up until Scope Change | £333,419 | £333,419
Cost Reduction to June-23 BER | £65,513 | £130,533
Cost to Deliver remainder of June-23 Scope | £65,020 | N/A
Cost of known additional work and risk margin to Deliver Changes Later | £34,619 | £66,193
Total Cost to Deliver Deferred Changes later | £100,132 | £196,726
IA for Deferring Implementation – Financial Details

## Slide 45: Summary and June-23 Scope Decision
Final Considerations
Additional costs to deliver XRN5186 are based on delivering the change as an independent project
These costs reflect known risks that may materialise during the remaining project activities
Any unspent risk margin would be returned to customers once change is successfully delivered
Combining XRN5186 with other changes within a Release would allow costs to be saved through shared Project resource, technology and support costs
DSC ChMC Decision – Approval of Xoserve recommendation (Option 2) - defer implementation of XRN5186 to November-23 Release
Vote required from DN and Shipper Customer Classes

## Slide 46: June 2023 Major Release Update

## Slide 47: XRN5562 – June 23 Major Release- Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking Green, Start up and initiation phase is completed. Build in progress for class change requirement. ​Progress update:​ Start up and initiation completed on 02/02 Build complete for all ISU build for XRN5186 and XRN5091 against original plan Build phase extended to include received delivery plans for Market Flow and GES changes and the missed requirement for Class Change (issue 68667); on track to complete including documentation by 28/04 Build for Market Flow changes relating to XRN5186 to commence on 27/02 System integration testing in progress on track to be completed 03/03 User Acceptance Testing scenarios in review approval to be provided on 24/02 Decision in March ChMC: Decision required on impact assessment to descope XRN5186 from June23 or stop June23 altogether and implement later. |  | Implementation date of 24th June, with a contingency implementation date of 1st July | 
Risks and Issues | Issue 68667 – The build for a “Class change” requirement was missed from xrn5091. Mitigation Action – A delivery timeline has been agreed with supplier, the build for this requirement to be completed on 03/03 Issue :There is an issue that some of the customer data held is inaccurate prior to the implementation of XRN5186. Mitigation Action – Xoserve are current working with customers to understand the best solution for this issue prior to the implementation of this change Issue: There is an associated issue that the current migration rules pre-implementation for XRN5186 are not currently defined and agreed. Mitigation Action - As above Issue: There is a risk that the June23 delivery could have one or both of its changes descoped pending a decision at the March ChMC meeting. Mitigation Action: An impact assessment is currently being carried out to understand all the available options. Xoserve will share options for approval at the March ChMC. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5091 - Deferral of creation of Class change reads at transfer of ownership XRN5186 - MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NEXAs |  |  | 
Slide updated on 21st February 2023
Complete
On Track
At Risk
Overdue

## Slide 48: XRN5575 March 23 Release

## Slide 49: XRN5575 – March 23 Adhoc Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking at risk; Amber. XRN 5472 (Weather API) descoped from March -23 and will be delivered at a later date. Design phase continues for both XRNs scoped for this release. Build and testing progressing as planned for 5143 and 5379. Return to green is completion of design and approved detailed project plan for delivery including touch-points with DM and NDM service providers. Progress update: Project Startup and Initiation phase complete Project Build phase complete UK Link SIT & UAT Testing execution complete as planned for 5379 Technolog onboarding underway as DM SP NDM SP procurement continues Weekly engagement sessions with Technolog including resolving of design queries and supporting integrated testing Decision in March ChMC: None |  | Implementation date of 25th March with a go-live of 1st April, the contingency implementation date is 1st April with a go-live of 1st April | 
Risks and Issues | 68566 (Issue) Delay to test commencement for March-23 impacting delivery plan, descope of 5472 alleviated pressure on timeline, risk remains open in case of further impact due to design continuing 68488 & 68489: (Risk) The design has not yet completed for the changes in this release, therefore the aspirational delivery timescales are at risk 68126: (Risk) The NDM service provider (SP) is not yet agreed, until the NDM SP is engaged and plans shared there is a risk that plans will not align to validate end to end functionality before 1st April |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN5143 - Transfer of NDM sampling obligations from Cadent, WWU, and NGN to the CDSP XRN5379 - Class 1 Read Service Procurement Exercise (Modification 0710) |  |  | 
Slide updated on 21st February 2023
Complete
On Track
At Risk
Overdue

## Slide 50: February 2023 Major Release

## Slide 51: XRN5533 – February 23 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Overall release is tracking on target; Green, all UK Link testing completed on 17/02 as per plan. Currently on track to implement on 25/02 Progress update: Performance testing complete on 17/02 DDP testing for XRN4990 complete on 20/02 Implementation preparation in progress ready for planned go live on 25/02 Decision in March ChMC: None |  | Implementation date of 25th February; with a contingency implementation date of 4th March | 
Risks and Issues | There is a risk that the solutions being delivered under XRN4900 and XRN5298 may not work as expected at the point SGN go live with the Biomethane and H100 projects, due to the gap between these changes being delivered within the Feb 23 release and the respective go live dates of the projects. Update - SGN have confirmed that the first H100 connection will be sometime between June-Sept 2024. CDSP are awaiting further clarification regarding the go live date of the Girvan Biomethane project. Discussions are underway regarding options for carrying out additional testing closer to the project go live dates, which may incur additional charges that weren't originally accounted for. |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | XRN4900 - Biomethane/Propane Reduction XRN4978 - Shipper - Notification of Rolling AQ Value XRN4989B - Residual AMT activities XRN4990 - MOD0664 – Transfer of Sites with Low Read Submission Performance from Class 2 and 3 into Class 4 XRN4992B - MOD0797 - Last Resort Supply Payments Volumetric Charges XRN5298 - H100 Fife Project – Hydrogen Network Trial |  |  | 
Slide updated on 22nd February 2023
Complete
On Track
At Risk
Overdue

## Slide 52: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS FEB 2023 – MAR 2025

## Slide 53
Programmes & Projects 2023-2025 |  |  | 2023 |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 | 
 |  |  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
MAJOR RELEASES | Regulatory / Customer Requested Change | XRN5455 Autumn Release |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes | XRN5231 Flow Weighted Average CV FWACV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain Yr 1 | XRN5368 Gemini Change Programme Sustain Yr1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain + | CP5564 Gemini Change Programme Sustain + |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Regulatory / Customer Requested Change | XRN5579 Gemini Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS 2023 – 2025
Design to PIS Oct 22 to Oct 24
Jan 23 to Mar 23
Feb 23 Closedown
in Progress (ChMC)
XRN5455
Autumn Release
XRN5231
Flow Weighted Average CV
FWACV
XRN5231
Flow Weighted Average CV
FWACV
Notes: XRN5393 – Gemini Spring 22 Release - RFC
CHG0033706 - Go Live 25/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033667 - Contingency 27/02 - UNC785 - Aggregate Bacton Exit Points - Part A (Operational)
CHG0033668 - Go Live 03/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory)
CHG0033767 - Contingency 10/04 - UNC785 - Aggregate Bacton Exit Points - Part B (Charging Theory
XRN5231 - Flow Weighted Average - RFC
CHG0033749 – Go Live 30/06 - Flow weighted Average CV Calculation
XRN5368.2 - Single Sign on Experience - RFC
CHG0033809 – Go Live 29/05 - SSO/MFA /SSPR
CHG0033828 – Contingency 12/06 - SSO/MFA /SSPR - Placeholder
XRN5368.3 - API Enhancements - RFC
CHG0033766 Go Live 10/04 - Azure APIM API’s over the internet - TBC
XRN5368.1 - Control M and Batch Processing - RFC
CHG0033808 Go Live 01/03 - Deletion & Housekeeping
CHG0033810 Go Live 15/03 - Deletion & Housekeeping
XRN5368.5 - Site Minder Upgrade - RFC
CHG0033777 - Siteminder upgrade - Prod change 1
CHG0033778 - Siteminder upgrade - Prod change 2 - Log4j re-fix.

## Slide 54: DDP March CHMC update

## Slide 55: Agenda
Roadmap update
Latest Sprint update

## Slide 56
Roadmap
PRODUCT DEVELOPMENT AND ROLLOUT
2022
04
05
06
07
08
09
10
11
12
01
02
03
04
05
06
07
08
09
10
11
12
01
02
2023
2024
Release 1 – Shipper Pack
03
ACTIVITY
Change freeze
Issue – (Requires escalation/support)
At risk - (Risk is being managed)
On track
KEY
Complete
Milestone
Release 2 – Golden Bullet forecast & IGT MDD data analysis
Release 3 – Golden Bullet invoice
Release 4 – XRN4990
Release 5 – XRN4990
Release 6 –XRN 4990 implement and DN financial reporting

## Slide 57
Data Discovery Platform | Current Sprint (part of release 6)
Goals: Complete MOD664 Shipper testing - Complete in line with milestone Complete MOD664 PAC testing – Complete in line with milestone Implement MOD664 Shipper dashboards – in progress Implement MOD664 PAC dashboards – in progress Establish DN sprint goal for release 6 – ongoing Refine and priortise DN financial reporting user stories – Complete | 
Outcomes: XRN4490 testing milestone met – complete Implement Shipper MOD664 dashboards Implement PAC MOD664 dashboard Implement new functionality to highlight sites to be updated by CDSP and auto loaded into CDSP dataset. Refine Financial reporting user stories with DNs in preparation for the next sprint | 

## Slide 58: Section 5: Non-DSC Change Budget Impacting Programmes

## Slide 59: March ChMC CMS Rebuild Update

## Slide 60: Progress to Date
During the Customer Focus Group in February, attendees were given three votes each to vote on the priority of the remaining processes. The below table is how the attendees at the customer focus group voted:
We are working with the UKLink Change team to deliver two change proposals that have CMS Rebuild Impacts, these are scheduled for the November UKLink release which will have an impact on the delivery of the Must Reads Process. Please note that this impact has not yet been reflected into the roadmap:
  XRN5604 – Shipper Agreed Reads
  XRN5605 – IGT Must Reads
The Customer Focus Group placeholders for the remainder of the year have now been issued and these will be updated on the Xoserve Webpage
The CMS Rebuild webpage (https://www.xoserve.com/products-services/data-products/contact-management-service-cms/cms-rebuild/) contains the link to register for future Customer Focus Groups which are captured below, please note the agenda for the Focus Groups will be issued between 3 - 7 days prior to the session.
Process | Score
ADD/UNC | 28
RFA/CDQ | 16
TOG | 16
MUR | 10
GSR | 9
MUS | 7
FOM | 7
DMQ | 3
Bulk STE | 1

## Slide 61
XRN 5556.b
Release Content
Now
Next
Later
A little Later
Supplier Theft of Gas (SUT)
Meter Number Creation (MNC)
Duplicate MPRNs (DUP)
Set to Extinct
Isolations
(ISO)
Dead to Live
(DTL)
DUP Enhancements
Generic to desk workflows – AGG, PSI, PSR
Address Amendments (ADD/ UNC)
Enhancements to MNC Process including Network
Generic to desk
workflows – GIC
Main Release
Additional Stretch Enhancements
Request for Adjustment (RFA)
Consumption Dispute Query (CDQ)
Theft of Gas
(TOG)–
Network Raised
Generic to desk
workflows – FLE
Must Reads
(MUR)
Gas Safety Regulation
(GSR)
Manage Unregistered Sites
(MUS)
SUT Enhancements
Generic Enhancements
XRN 5556.a
New Process
New MPRN Creation
(FOM)
Daily Metered Query (DMQ)
XRN 5556.d
24th April 2023
Bulk Upload file
XRN 5556.c
CMS Rebuild Roadmap

## Slide 62: Section 6: AnY Other Business

## Slide 63: Change Pack Response updates

## Slide 64: Change Pack Quick Response
If you approve the Change Pack and have no comments, you can now submit a quick response.
Open the Change Pack using the URL link
Click the Quick Approval button
Enter your email address
Submit
You will receive an email confirming that it has been submitted

## Slide 65: New Email Responses

## Slide 66: Appendix

## Slide 67: DDP Appendix

## Slide 68
Data Discovery Platform | Previous sprint (part of release 5)
Goals: Complete Build – complete Establish beta team – complete Establish DN sprint goal for release 6 – ongoing | 
Outcomes: XRN4490 build milestone met – complete Beta team working with delivery team refine dashboards in preparation for implementation (in line with Feb release) – ongoing Work with DNs to establish sprint goal ahead of release 6 | 

## Slide 69
Data Discovery Platform | Release 4
Goals: Complete detailed design Complete source to target Build 50% data model Enable additional Shipper Pack reports to be self served via DDP Facilitate MDD vs UKLink analysis for IGTs – Stretch | 
Outcomes: Detailed Design for the XRN4990 Solution pertaining to DDP Source to target completed for XRN4990 50% of XRN4990 data model built Additional Shipper pack delivery enabling Incorrect read factor and units to be self served via DDP Additional shipper pack delivery Shipper read frequency giving shipper portfolio count by MRF and a view of the average industry % by MRF code Stretch Targets: Additional analysis of UKLink / MDD data quality Industry view of read rejections by reasons code to compare company performance against industry average | 

## Slide 70
Data Discovery Platform | Release 2
Goal: Enable Distribution Network Users to access a financial forecasting report (part of the golden bullet), to understand variances between formula year AQ / SOQ and rolling AQ / SOQ to understand the impact this has on revenue. | 
User Stories: As a DN I want a view of my Formula year AQ/ SOQ and Rolling AQ / SOQ simulation data grouped by: LDZ, Exit Zone, Shipper Short, EUC, Code, Charge Type, Charge Rate, Asset Type, AQ Band and Class As a DN I want total FY AQ / SOQ and Rolling AQ / SOQ displayed in kwh and as a percentage, and the difference between the two As a DN I want total charges by Rolling and Formula Year AQ / SOQ totals and difference As a DN I want the number of MPRNs grouped by charge type between Formula year AQ / SOQ and Rolling AQ /SOQ (by kwh and percentage difference) so I can see how many MPRNs fall into each group and the difference between FY and Rolling for each charge type in both kwh and percent age and split by LDZ, Exit Zone, Class, AQ band, Shipper Short Code and Asset Type Charge types: ZCA, 891, CCA, CFI, ECN, C04 As a DN I want a trend view between Formula Year and Rolling AQ and SOQ with the total charge position for both Stretch element: As a DN I want the number of MPRNs grouped by % difference between FY AQ and rolling AQ and between FY SOQ and Rolling SOQ As a DN I want the number of MPRNs grouped by kwh difference between FY AQ and Rolling AQ and FY SOQ and rolling SOQ so I can see how many MPRNs fall into each group As a DN I want to see the total number of MPRNs that have had a rate change within the last month, and have these split by reason for the rate change (Shipper change, Class change, other) so I can understand how rate changes are affecting my revenues | 

## Slide 71
Data Discovery Platform | Release 3
Goals: Complete model to enable the aggregated invoice element of the Golden Bullet Report Enable more elements of the Shipper pack to be self served | 
User Stories: Build the data model to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on aswell that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year As a Shipper I want to be able to report on Dead meters via a monthly snapshot and see a trend over 12 months, so that the dead report in the Shipper pack can be retired As a Shipper I want my read performance for class 3 sites to be displayed as 'MET' when I have achieved 90% of reads accepted so that I can monitor my read performance Analysis of the below user story; As a Shipper I want an industry view of read rejection reasons so that I can compare my performance with industry Read rejections by reason code (numbers). Existing report need enhancing to give; Read rejections by reason code percentage value for a Shipper needs to be added to current dashboard Industry average number of read rejections (number and percentage) needs adding Performance enhancement to give a greater user experience of the large volumes Stretch targets: As a Shipper I want to see a list of sites in my portfolio containing plot addresses so that I can assess and update the address details correctly & in a timely manner. As a Shipper I want the WAR Bands dashboard to be moved out of UIG area of DDP and added to the Reads area of DDP so that it sits more logically from a business process perspective | 

## Slide 72
Data Discovery Platform | Inflight Sprint (part of release 3)
Goals: Build the golden bullet invoice report Build the detailed design for the XRN4990 solution | 
User Stories: Build the dashboards to enable the DN aggregated invoice element of the golden bullet to be delivered via DDP including A new monthly report that consolidates all the detail information shown in : BOPRI SCH606 Geninf shows the cash invoices values on as well that we have received Summarises it separately by EUC and also by Load Band It is also to be used to generate the December ""snapshot"" position and a forward forecast of new charging years monthly invoices so we would like to know in December what the new invoice values will be the following April - so forward forecast what the new capacity values will be inclusive of the new load factors and latest snapshot AQ use this report to populate the results Note: December snapshot: Capacity charges are established based on the December AQ / SOQ for the following financial year Performance optimisation for read dashboards Detailed Design for the XRN4990 Solution pertaining to DDP Stretch Target: Must read enhancement to align BAU enhancement to DDP Industry view of number of MPRN associated to MRF (part of Shipper Pack XRN 5200) | 

## Slide 73: Portfolio POAP

## Slide 74: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
 | Gemini | 19/03/2023 | 03:15:00 | 19/03/2023 | 5:15:00 | Long Term Flow Swap National Gas Transmission (NGT) has proposed an update to the Gemini System to improve the Long-Term Flow Swap (LTFS) process. Currently, users can only manually add daily LTFS details. This can lead to errors which add significant workload to NGT’s time-constrained month-end financial reporting processes. When this change is completed, NGT and Distribution Network Operators (DNOs) will be able to enter LTFS details for a period of time. We’ll also introduce ‘cancel’ and ‘accept’ functionality to reject/accept the flow swap details. | 08/03/2023
CHG0036680 | Gemini | 03/06/2023 | 03:15:00 | 03/06/2023 | 07:30:00 | Gemini Disaster Recovery Test 2023 This is an annual activity to confirm Gemini services can be migrated to a secondary data centre location should there be a catastrophic failure within the primary data centre. During this phase of the test Gemini services will failover from the primary site to the secondary site. The activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 08/03/2023
CHG0036680 | Gemini | 04/06/2023 | 03:15:00 | 04/06/2023 | 07:30:00 | Gemini Disaster Recovery Test 2023 During this phase of the test Gemini services will failback from the secondary site to the primary site. Again the activity starts within the scheduled maintenance window and the system will operate normally during times where there is no outage. | 08/03/2023