## Completion Guidelines
DRAFT DOCUMENT
Overview
To frame discussions and inform the recommendations of the Change Overview Board, Xoserve has devised a process to capture an industry wide view of risk, issues and delivery milestone progress across the current Change Portfolio.
This workbook contains the data capture tools that will be employed to collect information from industry stakeholders.
The Change Programmes that are to be factored into this process will be defined by the 'Change Horizon' view that is periodically assessed at the Change Overview Board. Change Programmes with 'Firm Deliverables' which are due for implementation within the next 1-2 years will be considered. The Change Programmes which are currently considered for assessment are detailed in the table below.
Assessed Change Programmes | Target Implementation Date
Faster Switching | 2014-11-01
UK Link Programme | 2015-10-01
EU Reform | 2015-10-01
SMIP | 2015-12-01
Xoserve will collate, anonymise and package information collected from industry stakeholders and present a summary view at each Change Overview Board meeting.
Tool 1: Risk and Issue Logs
Industry Stakeholders are invited to record risks and issues within the relevant tabs of the data capture form. The process is intended to collate information which will inform the discussion within the Change Overview Board. Accordingly please consider the 'level' of the risk and issue items recorded and ensure they have wider industry relevance.
Respondents should complete all fields within the risk and issue logs using input lists as appropriate.
Risks and issues must be classified against the parameters outlined in the table below.
Parameter | Description | Weighting | Example Risks and Issues
System Readiness | Risks / issues which fundamentally impact the delivery schedule of system changes | 40% | 1. Major delay experienced within a phase of the programme risking the implementation date 2. Lack of contingency within the plan 3. Major constraints on SME resource 4. Extensive customisation required to the solution
Delivery Quality | Risks / issues which impact delivery quality and could compromise meeting industry requirements | 30% | 1. The delivery schedule dictates that test phases must be truncated / streamlined in order to meet the delivery timelines 2. Ambiguous / unclear industry requirements
Business Readiness | Risks / issues which impact the organisation’s ability to have their people and processes ready to support system changes | 30% | 1. The demands of BAU activities are preventing resources from undertaking the required training to support the Change Programme 2. Delays in system development impacting business change activities
Tool 2: Milestone Reporting
Respondents are requested to submit details of the status of their internal Change Programmes in form of progress against delivery milestones.
Please complete the Milestone Reporting tab by providing a baseline and forecast or actual completion date for each phase (as applicable) for each Change Programme (as applicable). Please enter dates in the format dd/mm/yyyy. To help inform this submission the forecast dates for Xoserve's key delivery milestones are populated within the form.
Xoserve will produce an anonymised graph in the format outlined below to demonstrate milestone progress across the industry for each Change Programme.

## Risk Log
DRAFT DOCUMENT
Change Overview Board: Risk Log
ID | Risk Raised Date | Change Programme | Risk Parameter | Risk Headline | Risk Summary | Impact Date | Probability | Impact | Weighting | Risk Score | Risk Status | Mitigation Options
Unique Identifier | Date raised | Please specify the change programme which the risk relates to | Please specify the risk parameter which the risk relates to | Please provide a single line 'risk headline' to describe the risk | Please provide a clear summary of the risk and specific details of its root cause | Please specify when the risk could / will impact the programme | Please specify the likelihood of the risk materialising (please refer to scoring mechanism tab) 1 - Remote 2 - Less likely 3 - Equally as likely as unlikely 4 - More likely 5 - Almost certain | Please specify the impact if the risk materialises (please refer to scoring mechanism tab) 1 - Low 2 - Medium 3 - High | Prepopulated based on the risk parameter selected | A quantification of the risk based on probability / impact / risk weighting | Marks the risk as 'Open' or 'Closed' | Proposed mitigations for the identified risk
R_COB_001 | [8 empty] | #N/A | #N/A
R_COB_002 | [8 empty] | #N/A | #N/A
R_COB_003 | [8 empty] | #N/A | #N/A
R_COB_004 | [8 empty] | #N/A | #N/A
R_COB_005 | [8 empty] | #N/A | #N/A
R_COB_006 | [8 empty] | #N/A | #N/A
R_COB_007 | [8 empty] | #N/A | #N/A
R_COB_008 | [8 empty] | #N/A | #N/A
R_COB_009 | [8 empty] | #N/A | #N/A
R_COB_010 | [8 empty] | #N/A | #N/A
R_COB_011 | [8 empty] | #N/A | #N/A
R_COB_012 | [8 empty] | #N/A | #N/A
R_COB_013 | [8 empty] | #N/A | #N/A
R_COB_014 | [8 empty] | #N/A | #N/A
R_COB_015 | [8 empty] | #N/A | #N/A
R_COB_016 | [8 empty] | #N/A | #N/A
R_COB_017 | [8 empty] | #N/A | #N/A
R_COB_018 | [8 empty] | #N/A | #N/A
R_COB_019 | [8 empty] | #N/A | #N/A
R_COB_020 | [8 empty] | #N/A | #N/A

## Issue Log
DRAFT DOCUMENT
Change Overview Board: Issue Log
ID | Issue Raised Date | Change Programme | Issue Parameter | Issue Headline | Issue Summary | Impact Date | Impact | Weighting | Issue Score | Issue Status | Resolution Options
Unique Identifier | Date raised | Please specify the change programme which the issue relates to | Please specify the issue parameter which the issue relates to | Please provide a single line 'issue headline' to describe the issue | Please provide a clear summary of the issue and specific details of its root cause | Please specify when the issue materialised | Please assess the impact of the issue (please refer to scoring mechanism tab) 1 - Low 2- Medium 3 - High | Prepopulated based on the issue parameter selected | A quantification of the issue based on impact and issue weighting | Marks the issue as 'Open' or 'Closed' | Proposed resolution options for the identified issue
I_COB_001 | [7 empty] | #N/A | #N/A
I_COB_002 | [7 empty] | #N/A | #N/A
I_COB_003 | [7 empty] | #N/A | #N/A
I_COB_004 | [7 empty] | #N/A | #N/A
I_COB_005 | [7 empty] | #N/A | #N/A
I_COB_006 | [7 empty] | #N/A | #N/A
I_COB_007 | [7 empty] | #N/A | #N/A
I_COB_008 | [7 empty] | #N/A | #N/A
I_COB_009 | [7 empty] | #N/A | #N/A
I_COB_010 | [7 empty] | #N/A | #N/A
I_COB_011 | [7 empty] | #N/A | #N/A
I_COB_012 | [7 empty] | #N/A | #N/A
I_COB_013 | [7 empty] | #N/A | #N/A
I_COB_014 | [7 empty] | #N/A | #N/A
I_COB_015 | [7 empty] | #N/A | #N/A
I_COB_016 | [7 empty] | #N/A | #N/A
I_COB_017 | [7 empty] | #N/A | #N/A
I_COB_018 | [7 empty] | #N/A | #N/A
I_COB_019 | [7 empty] | #N/A | #N/A
I_COB_020 | [7 empty] | #N/A | #N/A

## Milestone Reporting
DRAFT DOCUMENT
Change Overview Board Milestone Reporting
Change Programme | Faster Switching
Faster Switching Milestones
Milestones | Detailed Design Baseline | Detailed Design Forecast / Actual | Internal Test Baseline | Internal Test Forecast / Actual | Market Testing Baseline | Market Testing Forecast / Actual | Implementation Baseline | Implementation Forecast / Actual
Xoserve Delivery Schedule | 2014-05-30 | 2014-05-30 | 2014-10-17 | 2014-10-17 | N/A | N/A | 2014-11-07 | 2014-11-07
Industry Stakeholder Delivery Schedule |  |  |  |  | N/A | N/A
Change Programme | UK Link Programme
UK Link Programme Milestones
Milestones | Detailed Design Baseline | Detailed Design Forecast / Actual | Internal Test Baseline | Internal Test Forecast / Actual | Market Testing Baseline | Market Testing Forecast / Actual | Implementation Baseline | Implementation Forecast / Actual
Xoserve Delivery Schedule | 2014-08-29 | 2014-09-26 | 2015-05-28 | 2015-05-28 | 2015-08-28 | 2015-08-28 | 2015-10-01 | 2015-10-01
Industry Stakeholder Delivery Schedule
Change Programme | 2014-08-29: EU Reform
EU Reform Milestones
Milestones | Detailed Design Baseline | Detailed Design Forecast / Actual | Internal Test Baseline | Internal Test Forecast / Actual | Market Testing Baseline | Market Testing Forecast / Actual | Implementation Baseline | Implementation Forecast / Actual
Xoserve Delivery Schedule | 2014-08-15 | 2014-08-20 | 2015-07-31 | 2015-07-15 | N/A | N/A | 2015-10-01 | 2015-10-01
Industry Stakeholder Delivery Schedule | 2015-08-28: N/A; 2015-08-28: N/A
Change Programme | 2014-08-29: SMIP
SMIP Milestones
Milestones | Detailed Design Baseline | Detailed Design Forecast / Actual | Internal Test Baseline | Internal Test Forecast / Actual | Market Testing Baseline** | Market Testing Forecast / Actual | Implementation Baseline | Implementation Forecast / Actual
Xoserve Delivery Schedule* | 2014-10-23 | 2014-10-23 | 2014-12-31 | 2014-12-31 | 2015-07-31 | 2015-07-31 | 2015-01-18 | 2015-01-18
Industry Stakeholder Delivery Schedule
* The Xoserve delivery dates relate to the Xoserve DCC Gateway Programme which Xoserve must deliver in readiness for the SMIP System Integration Testing phase.
** Market Testing dates relate to the SIT phase of the DECC SMIP plan

## Risk & Issue Scoring Mechanism
| Risk Scoring Mechanism |  |  |  | PROBABILITY OF RISK MATERIALISING
[5 empty] | (≤ 10%) Remote | > 10% ≤40% Less likely | > 40% ≤ 60% Equally as likely as unlikely | > 60% ≤90% More likely | > 90% Almost certain
Impact
| System Readiness | Delivery Quality | Business Readiness |  | 1 | 2 | 3 | 4 | 5
| Should the risk materialise there will be a minor to moderate impact on the delivery schedule of system changes with potential impact on the overall feasibility of the target implementation date. | Should the risk materialise solution quality will be moderately impacted yet overall requirements uncompromised | Should the risk materialise there will be a minor to moderate impact on business change activities with potential impact on the readiness of people and process change required for implementation | 1 | 1 | 2 | 3 | 4 | 5
| Should the risk materialise there will be a moderate to major impact on the delivery schedule of system changes with probable impact on the overall feasibility of the target implementation date. | Should the risk materialise solution quality will be majorly impacted and some requirements potentially compromised | Should the risk materialise there will be a moderate to major impact on business change activities with probable impact on the readiness of people and process change required for implementation | 2 | 2 | 4 | 6 | 8 | 10
| Should the risk materialise there will be a major impact on the delivery schedule of system changes with unavoidable impact on the overall feasibility of the target implementation date. | Should the risk materialise solution quality will be majorly impacted and requirements definitely compromised | Should the risk materialise there will be major impact on business change activities with unavoidable impact on the readiness of people and process change required for implementation | 3 | 3 | 6 | 9 | 12 | 15
Issue Scoring Mechanism
| System Readiness | Delivery Quality | Business Readiness
Low | Issue has caused a minor to moderate impact on the delivery schedule of system changes and potential impact on the overall feasibility of the target implementation date. | Solution quality is moderately impacted but overall requirements uncompromised | Issue has caused a minor to moderate impact on business change activities and potential impact on the readiness of people and process change required for implementation
Medium | Issue has caused a moderate to major impact on the delivery schedule of system changes and probable impact on the overall feasibility of the target implementation date. | Solution quality is majorly impacted and some requirements potentially compromised | Issue has caused a moderate to major impact on business change activities with probable impact on the readiness of people and process change required for implementation
High | Issue has caused a major impact on the delivery schedule of system changes and unavoidable impact on the overall feasibility of the target implementation date. | Solution quality is majorly impacted and requirements definitely compromised | Issue has caused a major impact on business change activities with unavoidable impact on the readiness of people and process change required for implementation

## Milestone Reporting Graph (hidden)
Phase Dates
| DD B | DD F/A | T B | T F/A | MT B | MT F/A | IMP B | IMP F/A
Xoserve | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 1 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 2 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 3 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 4 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 5 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Shipper 6 | 2014-08-01 | 2014-08-15 | 2014-12-01 | 2014-12-15 | 2015-08-29 | 2015-09-12 | 2015-10-01 | 2015-10-01
Example Risk Assessment Heat Map
Risk Parameter
[9 empty] | Change Driver | System Readiness | Delivery Quality | Business Readiness
[9 empty] | Change Driver XYZ | High | Low | High
[9 empty] | Change Driver XYZ | Medium | Medium | Medium
[9 empty] | Change Driver XYZ | Low | High | Medium
[9 empty] | Change Driver XYZ | High | Medium | Low
Formulas:
DD F/A = [DD B]+14
T F/A = [T B]+14
MT F/A = [MT B]+14

## Inputs (hidden)
Risk Parameter Weightings |  | Risk Status | Change Programme | Risk Parameter | Probability | Impact | Date
System Readiness | 4 | Open | UK Link Programme | System Readiness | 1 | 1 | 2014-01-01
Delivery Quality | 3 | Closed | Faster Switching | Delivery Quality | 2 | 2 | 2014-02-01
Organisational Readiness | 3 |  | SMIP | Organisational Readiness | 3 | 3 | 2014-03-01
|  |  | EU Reform |  | 4 |  | 2014-04-01
[5 empty] | 5 |  | 2014-05-01
2014-06-01
2014-07-01
2014-08-01
2014-09-01
2014-10-01
2014-11-01
2014-12-01
2015-01-01
2015-02-01
2015-03-01
2015-04-01
2015-05-01
2015-06-01
2015-07-01
2015-08-01
2015-09-01
2015-10-01
2015-11-01
2015-12-01
2016-01-01
2016-02-01
2016-03-01
2016-04-01
2016-05-01
2016-06-01
2016-07-01
2016-08-01
2016-09-01
2016-10-01
2016-11-01
2016-12-01