## Completion Guidelines
DRAFT DOCUMENT
Overview
To frame discussions and inform the recommendations of the Change Overview Board, Xoserve has devised a process to capture an industry wide view of risk and delivery milestone progress across the current Change Portfolio.
This workbook contains the data capture tools that will be employed to collect information from industry stakeholders.
The Change Programmes that are to be factored into this process will be defined by the 'Change Horizon' view that is periodically assessed at the Change Overview Board. Change Programmes with 'Firm Deliverables' which are due for implementation within the next 1-2 years will be considered. The Change Programmes which are currently considered for assessment are detailed in the table below.
Assessed Change Programmes | Target Implementation Date
Faster Switching | 2014-11-01
UK Link Programme | 2015-10-01
EU Reform | 2015-10-01
SMIP | 2015-12-01
Xoserve will collate, anonymise and package information collected from industry stakeholders and present a summary view at each Change Overview Board meeting.
Tool 1: Risk Log
Industry Stakeholders are invited to record risk items that they wish to bring to consciousness of the wider industry within the Risk Log tab.
Respondents should complete all fields within the risk log using input lists as appropriate.
Risks must be classified against the risk parameters outlined in the table below.
Parameter | Description | Weighting | Examples Risks
System Readiness | Risks which fundamentally impact the delivery schedule of system changes. | 40% | 1. Major delay experienced within a phase of the programme risking the implementation date 2. Lack of contingency within the plan 3. Major constraints on SME resource 4. Extensive customisation required to the solution
Delivery Quality | Risks which impact the delivery quality and could compromise meeting industry requirements | 30% | 1. The delivery schedule dictates that test phases must be truncated / streamlined in order to meet the delivery timelines 2. Ambiguous / unclear industry requirements
Business Readiness | Risks which impact the organisation’s ability to have their people and processes ready to support the system changes | 30% | 1. The demands of BAU activities are preventing resources from undertaking the required training to support the Change Programme 2. Delays in system development impacting business change activities
Tool 2: Milestone Reporting
Respondents are requested to submit details of the status of their internal Change Programmes in form of progress against delivery milestones.
Please complete the Milestone Reporting tab by providing a baseline and forecast or actual completion date for each phase (as applicable) for each Change Programme (as applicable). Please enter dates in the format dd/mm/yyyy.
Xoserve will produce an anonymised graph in the format outlined below to demonstrate milestone progress across the industry for each Change Programme.

## Risk Log
DRAFT DOCUMENT
Change Overview Board Risk Assessment
ID | Risk Raised Date | Change Programme | Risk Parameter | Risk Description | Impact Date | Probability | Impact | Weighting | Risk Score | Risk Status | Mitigation Options
Unique Identifier | Date raised | Please specify the change programme which the risk is relates to | Please specify the risk parameter which the risk relates to | Please provide a short description of the risk | Please specify when the risk could / will impact the programme | Please specify the likelihood of the risk materialising 1 - Low 2 - Medium 3 - High | Please specify the impact if the risk materialises 1 - Low 2 - Medium 3 - High | Prepopulated based on the risk parameter selected | A quantification of the risk based on probability / impact / risk weighting | Marks the risk as 'Open' or 'Closed' | Proposed mitigations for the identified risk
COB_001 | [7 empty] | #N/A | #N/A
COB_002 | [7 empty] | #N/A | #N/A
COB_003 | [7 empty] | #N/A | #N/A
COB_004 | [7 empty] | #N/A | #N/A
COB_005 | [7 empty] | #N/A | #N/A
COB_006 | [7 empty] | #N/A | #N/A
COB_007 | [7 empty] | #N/A | #N/A
COB_008 | [7 empty] | #N/A | #N/A
COB_009 | [7 empty] | #N/A | #N/A
COB_010 | [7 empty] | #N/A | #N/A
COB_011 | [7 empty] | #N/A | #N/A
COB_012 | [7 empty] | #N/A | #N/A
COB_013 | [7 empty] | #N/A | #N/A
COB_014 | [7 empty] | #N/A | #N/A
COB_015 | [7 empty] | #N/A | #N/A
COB_016 | [7 empty] | #N/A | #N/A
COB_017 | [7 empty] | #N/A | #N/A
COB_018 | [7 empty] | #N/A | #N/A
COB_019 | [7 empty] | #N/A | #N/A
COB_020 | [7 empty] | #N/A | #N/A
COB_021 | [7 empty] | #N/A | #N/A
COB_022 | [7 empty] | #N/A | #N/A
COB_023 | [7 empty] | #N/A | #N/A
COB_024 | [7 empty] | #N/A | #N/A
COB_025 | [7 empty] | #N/A | #N/A
COB_026 | [7 empty] | #N/A | #N/A
COB_027 | [7 empty] | #N/A | #N/A
COB_028 | [7 empty] | #N/A | #N/A
COB_029 | [7 empty] | #N/A | #N/A
COB_030 | [7 empty] | #N/A | #N/A
COB_031 | [7 empty] | #N/A | #N/A
COB_032 | [7 empty] | #N/A | #N/A
COB_033 | [7 empty] | #N/A | #N/A
COB_034 | [7 empty] | #N/A | #N/A
COB_035 | [7 empty] | #N/A | #N/A
COB_036 | [7 empty] | #N/A | #N/A
COB_037 | [7 empty] | #N/A | #N/A
COB_038 | [7 empty] | #N/A | #N/A
COB_039 | [7 empty] | #N/A | #N/A
COB_040 | [7 empty] | #N/A | #N/A
COB_041 | [7 empty] | #N/A | #N/A
COB_042 | [7 empty] | #N/A | #N/A
COB_043 | [7 empty] | #N/A | #N/A
COB_044 | [7 empty] | #N/A | #N/A
COB_045 | [7 empty] | #N/A | #N/A
COB_046 | [7 empty] | #N/A | #N/A
COB_047 | [7 empty] | #N/A | #N/A
COB_048 | [7 empty] | #N/A | #N/A
COB_049 | [7 empty] | #N/A | #N/A
COB_050 | [7 empty] | #N/A | #N/A
COB_051 | [7 empty] | #N/A | #N/A
COB_052 | [7 empty] | #N/A | #N/A
COB_053 | [7 empty] | #N/A | #N/A
COB_054 | [7 empty] | #N/A | #N/A
COB_055 | [7 empty] | #N/A | #N/A
COB_056 | [7 empty] | #N/A | #N/A
COB_057 | [7 empty] | #N/A | #N/A
COB_058 | [7 empty] | #N/A | #N/A
COB_059 | [7 empty] | #N/A | #N/A
COB_060 | [7 empty] | #N/A | #N/A
COB_061 | [7 empty] | #N/A | #N/A
COB_062 | [7 empty] | #N/A | #N/A
COB_063 | [7 empty] | #N/A | #N/A
COB_064 | [7 empty] | #N/A | #N/A
COB_065 | [7 empty] | #N/A | #N/A
COB_066 | [7 empty] | #N/A | #N/A
COB_067 | [7 empty] | #N/A | #N/A
COB_068 | [7 empty] | #N/A | #N/A
COB_069 | [7 empty] | #N/A | #N/A
COB_070 | [7 empty] | #N/A | #N/A
COB_071 | [7 empty] | #N/A | #N/A
COB_072 | [7 empty] | #N/A | #N/A
COB_073 | [7 empty] | #N/A | #N/A
COB_074 | [7 empty] | #N/A | #N/A
COB_075 | [7 empty] | #N/A | #N/A
COB_076 | [7 empty] | #N/A | #N/A
COB_077 | [7 empty] | #N/A | #N/A
COB_078 | [7 empty] | #N/A | #N/A
COB_079 | [7 empty] | #N/A | #N/A
COB_080 | [7 empty] | #N/A | #N/A
COB_081 | [7 empty] | #N/A | #N/A
COB_082 | [7 empty] | #N/A | #N/A
COB_083 | [7 empty] | #N/A | #N/A
COB_084 | [7 empty] | #N/A | #N/A
COB_085 | [7 empty] | #N/A | #N/A
COB_086 | [7 empty] | #N/A | #N/A
COB_087 | [7 empty] | #N/A | #N/A
COB_088 | [7 empty] | #N/A | #N/A
COB_089 | [7 empty] | #N/A | #N/A
COB_090 | [7 empty] | #N/A | #N/A
COB_091 | [7 empty] | #N/A | #N/A
COB_092 | [7 empty] | #N/A | #N/A
COB_093 | [7 empty] | #N/A | #N/A
COB_094 | [7 empty] | #N/A | #N/A
COB_095 | [7 empty] | #N/A | #N/A
COB_096 | [7 empty] | #N/A | #N/A
COB_097 | [7 empty] | #N/A | #N/A
COB_098 | [7 empty] | #N/A | #N/A
COB_099 | [7 empty] | #N/A | #N/A
COB_100 | [7 empty] | #N/A | #N/A

## Milestone Reporting
DRAFT DOCUMENT
Change Overview Board Milestone Reporting
Faster Switching
BaselineTarget Implementation Date
Forecast Target Implementation Date
Milestone | Analysis / High Level Design Baseline | Analysis / High Level Design Forecast / Actual | Detailed Design Baseline | Detailed Design Forecast / Actual | Build Baseline | Build Forecast / Actual | System Testing Baseline | System Testing Forecast / Actual | UAT Baseline | UAT Forecast / Actual | Market Trials Baseline | Market Trials Forecast Actual | Business Readiness & Training Baseline | Business Readiness & Training Forecast / Actual
Phase Dates
UK Link Programme
BaselineTarget Implementation Date
Forecast Target Implementation Date
Milestone | Analysis / High Level Design Baseline | Analysis / High Level Design Forecast / Actual | Detailed Design Baseline | Detailed Design Forecast / Actual | Build Baseline | Build Forecast / Actual | System Testing Baseline | System Testing Forecast / Actual | UAT Baseline | UAT Forecast / Actual | Market Trials Baseline | Market Trials Forecast Actual | Business Readiness & Training Baseline | Business Readiness & Training Forecast / Actual
Phase Dates
EU Reform
BaselineTarget Implementation Date
Forecast Target Implementation Date
Milestone | Analysis / High Level Design Baseline | Analysis / High Level Design Forecast / Actual | Detailed Design Baseline | Detailed Design Forecast / Actual | Build Baseline | Build Forecast / Actual | System Testing Baseline | System Testing Forecast / Actual | UAT Baseline | UAT Forecast / Actual | Market Trials Baseline | Market Trials Forecast Actual | Business Readiness & Training Baseline | Business Readiness & Training Forecast / Actual
Phase Dates
SMIP
BaselineTarget Implementation Date
Forecast Target Implementation Date
Milestone | Analysis / High Level Design Baseline | Analysis / High Level Design Forecast / Actual | Detailed Design Baseline | Detailed Design Forecast / Actual | Build Baseline | Build Forecast / Actual | System Testing Baseline | System Testing Forecast / Actual | UAT Baseline | UAT Forecast / Actual | Market Trials Baseline | Market Trials Forecast Actual | Business Readiness & Training Baseline | Business Readiness & Training Forecast / Actual
Phase Dates

## Milestone Reporting Graph (hidden)
Phase Dates
| HLD B | HLD F/A | DD B | DD F/A | Build B | Build F/A | ST B | ST F/A | UAT B | UAT F/A | MT B | MT F/A | BC B | BC F/A
Shipper 1 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Shipper 2 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Shipper 3 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Shipper 4 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Shipper 5 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Shipper 6 | 2014-04-01 | 2014-04-15 | 2014-08-01 | 2014-08-15 | 2014-10-01 | 2014-10-15 | 2014-12-01 | 2014-12-15 | 2015-05-01 | 2015-05-15 | 2015-08-29 | 2015-09-12 | 2015-08-29 | 2015-09-12
Example Risk Assessment Heat Map
Risk Parameter
Change Driver | System Readiness | Delivery Quality | Business Readiness
Change Driver XYZ | High | Low | High
Change Driver XYZ | Medium | Medium | Medium
Change Driver XYZ | Low | High | Medium
Change Driver XYZ | High | Medium | Low
Formulas:
HLD F/A = [HLD B]+14
DD F/A = [DD B]+14
Build F/A = [Build B]+14
ST F/A = [ST B]+14
UAT F/A = [UAT B]+14
MT F/A = [MT B]+14
BC F/A = [BC B]+14

## Inputs (hidden)
Risk Parameter Weightings |  | Risk Status | Change Programme | Risk Parameter | Probability | Impact | Date
System Readiness | 40% | Open | UK Link Programme | System Readiness | 1 | 1 | 2014-01-01
Delivery Quality | 30% | Closed | Faster Switching | Delivery Quality | 2 | 2 | 2014-02-01
Organisational Readiness | 30% |  | SMIP | Organisational Readiness | 3 | 3 | 2014-03-01
|  |  | EU Reform |  |  |  | 2014-04-01
2014-05-01
2014-06-01
2014-07-01
2014-08-01
2014-09-01
2014-10-01
2014-11-01
2014-12-01
2015-01-01
2015-02-01
2015-03-01
2015-04-01
2015-05-01
2015-06-01
2015-07-01
2015-08-01
2015-09-01
2015-10-01
2015-11-01
2015-12-01
2016-01-01
2016-02-01
2016-03-01
2016-04-01
2016-05-01
2016-06-01
2016-07-01
2016-08-01
2016-09-01
2016-10-01
2016-11-01
2016-12-01