## Version Control (hidden)
Version | Status | Comments
V0.1 | Initial Draft
V0.2 | 2nd draft | Change register updates
Tier 1 category updates
Tier 2 category updates
CR Business Priority review with ES & BV

## ChMC Change Demand Backlog
Serial No | Existing Change Proposal No | Xoserve Change Request No | Change Request Title | Drivers of Change | Benefit/Case for Change | Requirement(s) of Change Request/Proposal | Breach of Code | Related to MOD Ref | MOD Implementation Date | Comments | Proposed Status | High level view of impact to market participants | Service Area | Source | DSC Proposed Priority 10/05/2017
1 |  | UKLP060 | Read Validation Tolerances | Market Driven | New Requirement | A requirement to change the read validation tolerance from a % based test to a kWh test for a Supply Meter Point with an AQ less than [30,000 kWh] and to split the AQ band of less than 73,200 into 2 further AQ bands. | No |  |  |  | Proposed for Bubbling Under | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC
2 |  | UKLP065 | Correction Factor Application | Business Excellence | New Requirement | A requirement to ensure a facilitation is available to censor check the appropriate Correction Factor is being applied and thus consumption can be calculated. In addition, the Energy Thermal Regulations document state the requirements for what Correction Factor that must be applied. | No |  |  |  | Proposed for Bubbling Under | Shippers | Service Area 15: Demand Estimation | PNUNC |  | System/Process | Business Excellence | Internal
3 |  | UKLP071 | Provision of Formula Year AQ | Business Excellence | New Requirement | A requirement to add an optional field to the S75 which would provide visibility of provision year AQ data. The value would be populated where this had been derived for the forthcoming year, and had yet to become effective. | No |  |  | Not in UNC, users require this for quotes and transportation charges | Proposed for Bubbling Under | Shippers | To Be Determined | PNUNC |  | Report | Market Driven | External
4 |  | UKLP072 | Design Gaps - Ability To Provide Missing Class 3 Reads | Service Sustaining | Design Gap | A requirement to create notification to Shippers of any reads missing in a batch of reads for Class 3 SMP’s | No |  |  |  | Proposed for Bubbling Under | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC | Low |  | Service Introduction
5 |  | UKLP073 | Read Design Gaps - Missing Override Flags In RGMA and Retro Files | Business Excellence | Design Gap | A requirement to include read validation to the reads supplied by the Registered User in the RGMA and Retro update file flows. A read tolerance override flag will be required to be added to the relevant file formats and validation to consider when the tolerance override flag has been set the by User. | No |  |  | Discussed in DSC meeting 10/05/2017 The validation rules are contained in a supplementary guidance and not in UNC. Inner tolerance validation not applied. There should be 2 Change Proposals submitted for this change to cover RGMA and Retro. | CP Required (CDSP Proposed) | DNs Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC |  |  | Service Sustaining
6 |  | UKLP096 | IA for strategic solution options for the GDE Offline database | Business Excellence | Continuous Improvement | A requirement for solution options for a GDE solution to remove the offline solution. | No |  |  |  | Proposed for Bubbling Under | DNs Shippers |  | DN | Low
7 |  | UKLP109 | Capability to replace a sequence of readings | Service Sustaining | Design Gap | A Requirement to replace multiple readings in one file. A user can replace a sequence of readings but only 1 at a time and the chances of failure are high. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | Service Area 5: Metered Volume and Metered Quantity | PNUNC
8 |  | UKLP112 | Missing Key Data Item from iGTs to Shippers (Plot Number) | Service Sustaining | New Requirement | A requirement to include the Plot number within current Shippers File Formats. | No |  |  |  | Proposed for Bubbling Under | iGTs Shippers |  | PNUNC
9 |  | UKLP113 | Notification of Formula Year AQ & SOQ | Service Sustaining | Design Gap | A requirement to notify Users at Month -5 of changes to the Rolling and/or Formula year AQ/SOQ following the monthly calculation/update process. | Yes | 432 | 1st June 17 | MOD432 text - G1.6.6Code implies we will notify the user 'New formula year AQ & SOQ First notification due to be issued March 18 | CP Required (CDSP Proposed R1.1) | Shippers | Service Area 6: Annual Quantity, DM Supply Point and Offtake Rate Reviews | PNUNC
10 |  | UKLP122 | PAF Indicator field inclusion on VAD and ACR files | Service Sustaining | Service Sustaining | A requirement to include the PAF Indicator field on VAD and ACR file formats. | No |  |  |  | CP Required (CDSP Proposed) | DNs Shippers | Service Area 1: Manage Supply Point Registration | UKLP
11 |  | UKLP136 | Notification of Twin streams that have calculated an AQ or W/C ( T04, S91 & T50) | Service Sustaining | Design Gap | A requirement to support twin streams. The current NRL T04,S91 & T50 files does not support the communication of twin stream: these being SMP’S that have multiple asset and reads. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP
12 |  | UKLP140 | .DUP & .DUS file type registration in AMT | Service Sustaining | Design Gap | A requirement to support the duplicate invoice & supporting information from the new UK Link application | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 18 Provision of user reports and information | UKLP
13 | XRN3830 | UKLP142 | Change to DN files .DDU .DDS & .CPM | Business Excellence | New Requirement | A requirement for additional data items on Demand Derivation System to realise the benefits of the systems improvements. | No |  |  | CDSP has submitted a Change Order for this requirement in September 2015 which has the XRN 3830. | CP Available (CDSP Proposed R1.1) | DNs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | DN
14 |  | UKLP147 | DDS/DDU file amendment | Service Sustaining | New Requirement | A requirement for the following changes to the DN DDS and DDU files: 1. Twin stream meters - For DDS and DDU files to only contain the first asset for a twin stream meter i.e. suppress any instances where there is a second record for an MPRN. 2. Rolling AQ updates – For the DDU file to not include any records relating to rolling AQ updates. | No |  |  |  | CP Required (CDSP Proposed R1.1) | DNs | 21 Data flows and services to Network Operators 14 Provision of reporting services to Gas Transporters | DN
15 |  | UKLP152 | Change to processing ONJOB/ONUPD where existence of a Read marked Suspect as one of the latest activities | Market Driven | Retro | A requirement to amend the validation check framework (VCF) logic in current RGMA functionality in SAP-ISU to include an additional Read Type (suspect Reads) validation for checking suitability to process ONJOB/ONUPD across sites of all class types | No |  |  |  | Proposed for Bubbling Under | Shippers | 1 Manage supply point registration 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC
16 |  | UKLP154 | Retro Updates - Suspecting Reads following Asset Attribute Update | Market Driven | Retro | A requirement to have a consistent approach to the treatment of reads, being all reads recorded are marked ‘suspect’ and it will be Shippers responsibility to either replace reads or submit a latest reading to trigger reconciliation and generate the adjustment to charges. | No |  |  |  | Proposed for Bubbling Under | Shippers | 1 Manage supply point registration 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC
17 |  | UKLP155 | Retro Updates - Notifying of Suspect Reads | Market Driven | Retro | A requirement to issue notification of all reads (the Registered User only) marked ‘Suspect’ | No |  |  |  | Proposed for Bubbling Under | Shippers | 5 Metered volume and quantity 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence | PNUNC
18 |  | UKLP159 | Document Archival in ILM | Service Sustaining | Service Sustaining | A requirement to archive historical transactional (invoicing and supporting) files, dating back up to 7 years prior to Go-Live date. | No |  |  | CR prioritised at DSC Meeting 10/05/17 Score given = High | CP Required (CDSP Proposed R1.1) | Xoserve | To Be Determined | UKLP | High
19 |  | UKLP162 | Addition of Daily LDZ Unidentified Gas (UG) to National Grid Operational Data Services | Market Driven | New Requirement | A requirement to make daily Unidentified Gas (UG) as calculated during daily Nominations and Allocations at LDZ level available to Shippers on National Grid’s Operational Data service. | No |  |  |  | Proposed for Bubbling Under | NTS | 18 Provision of user reports and information | UKLP
20 |  | UKLP189 | Transfer reading following a Retro update | Market Driven | Retro | A requirement to review the current process as it has a huge customer satisfaction impact for end consumers as their ending with old and starting with new Supplier readings could be different. | No |  |  |  | Proposed for Bubbling Under | Shippers | 5 Metered volume and quantity | PNUNC
21 |  | UKLP192 | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of OFGEM RFI | Market Driven | New Requirement | A requirement for changes to the Market Intelligence report and Change of Supplier reporting suite. | No |  |  | OFGEM need to instruct the Networks to update a suite of reports after Xoserve provide the delivery timescales. | Proposed for Bubbling Under | Xoserve |  | OFGEM
22 |  | UKLP194 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | Market Driven | New Requirement | A requirement to create an enduring solution for National Grid to receive the billing history data to feed into the analysis, that will be conducted as part of the Phase 4 and Charging Review (Gas).The data is required from Nexus Implementation date on an enduring basis (annual and monthly basis which is dependant on that particular report) via report/s which should have the flexibility to be run by a number of users (within Market Change Gas). | No |  |  | New CO to support enduring solution is required | CP Required (CDSP Proposed) | DNs | 7 NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices 21 Data flows and services to Network Operators | DN
23 |  | UKLP197 | Addition of New fields from CMS being available in BW/IP reporting environment | Service Sustaining | Service Sustaining | Addition of new fields from CMS to Xoserve's SAP Business Warehouse to enable use in future reporting services. | No |  |  |  | CP Required (CDSP Proposed) | Xoserve | 18 Provision of user reports and information 21 Data flows and services to Network Operators | UKLP
24 |  | UKLP198 | Ability to submit a read taken at meter inspection with meter inspection update | Service Sustaining | Design Gap | A requirement to include the submission of the read along with the inspection date following a meter inspection. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 5 Metered volume and quantity | PNUNC
25 |  | UKLP202 | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | Service Sustaining | Design Gap | A requirement to have maximum reads loaded on the system, which results in more accurate AQ’s. | Yes | 432 | 1st June 17 | MOD 432 text - UNC G1.6.26 - No workaround this has been discussed with PNUNC and agreed can be resolved at a later date | CP Required (CDSP Proposed) | Shippers | 5 Metered volume and quantity 6 Annual quantity, DM Supply Point and Offtake Rate Reviews | PNUNC
26 |  | UKLP203 | Amendment to U82 record to include the revised NTS optional tariff rate | Service Sustaining | Design Gap | A requirement file format change required to add the NTS Optional Tariff Rate. | No |  |  | A current workaround exists | CP Required (CDSP Proposed) | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | PNUNC
27 | COR3995 | UKLP222 | Theft Risk Assessment Service Tip-off Hotline Data Provision – Enduring Solution | Business Excellence | New Requirement | A requirement for an enduring solution for the Energy Theft Tip-Off Services provider to identify an MPRN for an address where they receive a tip-off/notification of a suspected theft of gas situation. Xoserve would provide a monthly report to the Energy Theft Tip-Off Services provider via a .csv file. | No |  |  | COR 3995 was submitted to deliver the report. However, as part of this change order they have developed an interim solution to support the change till the enduring solution is delivered. | CP Available (CDSP Proposed) | DNs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP
28 |  | UKLP223 | Allow for a capacity revision on a Seasonally Large Supply Point | Service Sustaining | Design Gap | A requirement to support UNC code B4.9.2 - The current design does not allow for a capacity revision for a Seasonal Supply Point. | Yes | 432 | 1st June 17 | B4.9.5 (d) states a User can amend capacity at certain times via capacity revision. A User can submit a re-confirmation to revise capacity to fulfil the requirement. Extremely low volumes of MPRN's impacted. | CP Required (CDSP Proposed) | Shippers | 6 Annual quantity, DM Supply Point and Offtake Rate Reviews | PNUNC
29 |  | UKLP225 | Change number of occurrences in the K13 record for SSMP’s | Service Sustaining | Design Gap | A requirement to update supplier code to contain prospective Supplier and Shipper values(SUPPLIER SHORT CODE and SHIPPER SHORT CODE in K13 record (TRS/TRF file)). | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP
30 |  | UKLP226 | Provide the DMSP with the AQ in the O13 record on the GCC file | Business Excellence | New Requirement | Requirements: 1. Provide the DMSP with the site AQ value in order they can accurately validate class 1 readings prior to submission to Xoserve. 2. Trigger the GCC file following a ‘finalised ratchet’ to the DMSP. 3. Supply the MNEPOR value for any NTS data logged SMP’s | No |  |  |  | CP Required (CDSP Proposed) | DMSP | 21 Data flows and services to Network Operators | UKLP
31 |  | UKLP233 | Functional change to reflect data that has been nulled in output files provided to Shippers | Business Excellence | New Requirement | A requirement to support nullified data. Shippers will not know of contact titles that are nulled by Xoserve as the return file provided to Shippers will contain the original information supplied by Shippers. | No |  |  |  | Proposed for Bubbling Under | Shippers | 1 Manage supply point registration | UKLP
32 | COR4057 | UKLP244 | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | Market Driven | New Requirement | The changes include introduction of obligations on Distribution Networks (DNs) to supply specific information to NG Transmission in the event of a Gas Deficit Emergency (GDE). | No |  |  |  | CP Available (DSC Prioritised) | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | DN | Low
33 | COR4097 | UKLP249 | Addition of new Vulnerable Customer Needs codes | Market Driven | New Requirement | An OFGEM lead requirement, their final consultation requires the new needs codes to be in use from 1st June 2017, this will be reiterated through license condition changes to Gas Transporter licences. | No |  |  | CR prioritised at DSC Meeting 10/05/17 Score given = High | CP Required (CDSP Proposed R1.1) | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | OFGEM | High
34 |  | UKLP251 | Reports required under UNC TPD V16.1 in Nexus (reports required by MOD 520A) | Market Driven | New Requirement | A requirement for a number of reports. DNs are to provide a number of reports both to the industry in general and also to Performance Assurance Committee members. | No |  |  |  | CP Required (DSC Prioritised) | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | BAU Change | High
35 |  | UKLP256 | NDM Twin Stream Read Validation | Service Sustaining | Design Gap | A requirement to support NDM twin stream and automated read input validation process. | No |  |  | This is not breaching the code because we have a workaround in place, Xoserve will input the meter reads supplied by the registered User until such time as a fix is implemented. We are expecting extremely low volumes on this. | CP Required (CDSP Proposed) | Shippers | 5 Metered volume and quantity | UKLP
36 |  | UKLP257 | Class 1 validation errors (NTS/telemetered/CSO sites) | Service Sustaining | Service Sustaining | A requirement to support G1.5.2(a) that states what qualifies to be class 1. | No |  |  | This is not breaching the code because there is a workaround in place to ensure those impacted sites. | CP Required (CDSP Proposed) | Shippers | 1 Manage supply point registration | UKLP
37 |  | UKLP258 | Various File Format Changes identified in August 2016 | Service Sustaining | Service Sustaining | A requirement to change the structure and composition of the Unique Sites file format (e.g. additional field, optionality/allowable values etc.) to enable files to be issued and received. | No |  |  |  | CP Required (CDSP Proposed) | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP
38 |  | UKLP262 | Change to RGMA validations for LI confirmations | Business Excellence | New Requirement | A requirement to change Existing RGMA validation rules in legacy and new UK Link. | No |  |  |  | Proposed for Bubbling Under | Shippers | 1 Manage supply point registration | UKLP
39 |  | UKLP267 | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | Service Sustaining | Service Sustaining | A requirement to adjust file format that allows the User to set ‘n’ when providing site visit reads via the SFN file, this indicates that, following site visit, the reads taken have not fixed the fault. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP
40 |  | UKLP270 | Amend referral rules for class 2 smaller LSP’s | Service Sustaining | Design Gap | A requirement to accept Class 2 Meter Points and to be a configurable upper value with the ability to increase/decrease if required. There could be a significant number of Class 2 Meter Points, some of which will have lower AQ/SOQ value (LSP’s that still require nomination). | No |  |  |  | CP Required (CDSP Proposed) | DNs | 1 Manage supply point registration | UKLP
41 |  | UKLP271 | Work Items unique Task ID request | Service Sustaining | Service Sustaining | A requirement in SAP to generate unique Task ID. There are several types of Work Items have the same Task ID which makes it difficult to predict volumetric and ensure that they are completed in a timely and correct manner. | No |  |  |  | CP Required (CDSP Proposed) | Xoserve | To Be Determined | UKLP
42 |  | UKLP272 | Capacity referral raised in error following Nomination | Service Sustaining | Design Gap | A requirement to amend rules so NOT to issue a referral in the below scenario. SAP is referring a nomination to DN’s when the User has requested prevailing SOQ/SHQ values but the SOQ/SHQ is >16 /<24. In this scenario no referral is required and an offer should be issued to User (providing all other validations are passed). | No |  |  |  | CP Required (CDSP Proposed R1.1) | DNs Shippers | 1 Manage supply point registration | UKLP
43 |  | UKLP273 | PSR requirements – Vulnerable Customer data requirements | Market Driven | New Requirement | A requirements to be in place to assist customers in vulnerable situations; - Aligned vulnerable customer needs codes between Gas and electricity - Mapping of existing vulnerable customer needs code to new vulnerable customer needs code | No |  |  |  | Proposed for Bubbling Under | DNs iGTs Shippers | 9 User admission and termination | OFGEM
44 |  | UKLP276 | iGT IIL & IDL files splitting - manual workaround provided in Market Trials into Production post go live | Service Introduction | New Requirement | A requirement iGTs would like IIL & IDL files to split, the total file into its daily components. SAP produces a single “catch up” file covering all the “down” days. | No |  |  |  | Proposed for Bubbling Under | iGTs | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 18 Provision of user reports and information | UKLP
45 |  | UKLP277 | Treatment of values in the CDR | Service Sustaining | New Requirement | A requirement to define allowable values for the functional data items (lower level of detail) within the Connection and Disconnection Suite of jobs (this includes the CDN, CDR and CDJ (or CDJOB). | No |  |  |  | Proposed for Bubbling Under | Shippers | 1 Manage supply point registration | PNUNC
46 |  | UKLP279 | Pending capacity amendment with Ratchet | Service Sustaining | Design Gap | A requirement to for current functionality to take into consideration a pending capacity amendment when a ratchet occurs. The incorrect (lower value) could go live resulting in further ratchets that should not be applied. | Yes |  |  | The code reference is B4.7G5. There is no workaround in place therefore it is required to be implemented in release 1.1 as ratchets run from 1st October each year. | CP Required (CDSP Proposed R1.1) | Shippers | 1 Manage supply point registration | UKLP
47 |  | UKLP280 | Various File Format changes identified in December 2016 | Service Sustaining | New Requirement | A requirement for File Format description and system changes that have been identified and recorded to be reviewed post Go Live. | No |  |  |  | CP Required (CDSP Proposed) | DNs iGTs Shippers | 16 Provision of supply point information services and other services required to be provided under condition of the GT Licence 21 Data flows and services to Network Operators | UKLP
48 |  | UKLP281 | DN Sales (Outbound Services) Requirements for UKLP enduring solution | Market Driven | New Requirement | A requirement for an enduring solution to split invoicing automated without manual intervention is required by 1 year after UKLP Go Live. | No |  |  | There was a project COR4043 that delivered the interim solution however it was agreed that Beverly Viney will be raising a separate Change Proposal for the enduring solution. | Proposed for Bubbling Under | DNs Shippers NTS | 7 NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-hoc adjustment and balancing invoices | DN
49 |  | UKLP287 | Back billing for domestic (SSP) sites needs to be reflect the correct adjustment start date | Service Sustaining | Design Gap | A requirement to ensure correct adjustment period is billed for SSP sites as part of the back billing (GSR site visit) process. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | 7: NTS Capacity, LDZ Capacity, Commodity, Reconciliation, Ad-Hoc Adjustment and Energy Balancing Invoices | UKLP
50 |  | UKLP289 | Class 4 CSEPS Reconciliation Variance Identification | Service Sustaining | Design Gap | A requirement to ensure correct reconciliation billing following a CSEPs Project change. | Yes |  |  | Breach of UNC section S. this was deemed to be a low priority change as the likelihood of only a CSEPs grid change is low. | CP Required (CDSP Proposed) | iGTs Shippers | To Be Determined | UKLP
51 | COR2831.5 | UKLP292 | Changes to the upper parameter of the XDO partial refresh file | Business Excellence | New Requirement | A requirement to ensure that the obligations in the Smart Energy Code are fully met. At present a request greater than 30k MPRNs can not be met. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a partial request of any size up to a full portfolio. | No |  |  | As part of COR2831.5 this requirement was supposed to be delivered but it was deferred and it needs to be considered for the DSC prioritisation. | CP Available (CDSP Proposed) | DCC | To Be Determined | Smart
52 | COR2831.5 | UKLP293 | Splitting of the DXI inbound and DXR outbound file from the DCC. | Business Excellence | New Requirement | A requirement to ensure that the treatment of the DXI and DXR files meets the obligations in the Smart Energy Code. The SEC does not stipulate a size restriction and therefore the DCC / DSP can submit a file of any size. | No |  |  | As part of COR2831.5 this requirement was supposed to be delivered but it was deferred and it needs to be considered for the DSC prioritisation. | CP Available (CDSP Proposed) | DCC | To Be Determined | Smart
53 |  | UKLP300 | Unique Sites – Adding profiles | Business Excellence | Continuous Improvement | A requirement to enable the correct profiles to be added automatically and not manually. | No |  |  |  | CP Required (CDSP proposed) | Xoserve | To Be Determined | UKLP
54 |  | UKLP301 | Annual Production and notification of LIS 3 years read | Service Sustaining | Service Sustaining | A read requirement to be generated each year for any Meter Point that do not have a read recorded post LIS -3 years to be loaded by 1st April each year. This read is required to be issued to, and identifiable by, the registered User as it will be used for Reconciliation purposes. | No |  |  |  | CP Required (CDSP Proposed) | Shippers Xoserve | To Be Determined | UKLP
55 |  | UKLP305 | MOD 431 – Validations against file header and data within records | Service Sustaining | Design Gap | A requirement to validate that; the recipient within the file header is the same as the Shipper short code within records, where any discrepancies are found – these should be rejected. | Yes | 431 |  | We would be in breach of code until this is fixed. No identified workaround, required to issue out Nov 17 | CP Required (CDSP Proposed R1.1) | Shippers | To Be Determined | UKLP
56 |  | UKLP306 | Amend functionality to send GCC file to DMSP when Class 1 Confirmation Requests Lapse due to objection. | Service Sustaining | Design Gap | A Requirement for DMSP to be informed via GCC when the Class 1 confirmation request is cancelled | No |  |  |  | CP Required (CDSP Proposed) | DMSP | To Be Determined | UKLP
57 |  | UKLP307 | Proposal for process improvements for Supporting Information files (AML,COI and CZI) | Business Excellence | Continuous Improvement | A requirement to the supporting information program to enable the simulation of the supporting information files before the actual generation and submission of these supporting information files for delivery. | No |  |  |  | Proposed for Bubbling Under | Shippers | To Be Determined | UKLP
58 |  | UKLP309 | UMR Hierarchy Amendment in AMT | Service Sustaining | Service Sustaining | A requirement to change file format hierarchy. The UMR file U01 record is currently registered in AMT as having unlimited occurrences – this need to be changed to 300,000 occurrences as per the approved file format hierarchy. | No |  |  |  | CP Required (CDSP Proposed) | Shippers | To Be Determined | UKLP
59 | COR4186 |  | DES Access Restriction and Audit | Market Driven | New Requirement | A requirement to support the Competition and Markets Authority (CMA) order to provide data to Price comparison Websites (PCWs) to facilitate faster switching. | No |  |  |  | CP Available (DSC Prioritised) | Shippers | To Be Determined | BAU Change | High
60 | COR4248 |  | Quarterly smart metering reporting for HSE and DNs | Business Excellence | Continuous Improvement | A requirement to produce a quarterly report to be provided as a national report to the HS&E and as a DN level report to each network summarising meter exchanges and installations. | No |  |  |  | CP Available (DSC Prioritised) | DNs | To Be Determined | BAU Change | High
61 |  | UKLP317 | Sybase NLS Solution Design Gap | Service Sustaining | Service Sustaining | A requirement to support the Sybase solution and NLS data. The design of the Sybase solution based on the business requirements and the BW capability delivered, a solution design gap has been identified where the use of reports through the Universe reporting layer capability are unable to read NLS data. | No |  |  |  | CP Required (CDSP Proposed) | Xoserve | To Be Determined | UKLP
62 |  | UKLP132A | Delivery via Automated Integration Solution for all IP reports from SAP BW | Business Excellence | Continuous Improvement | A requirement that all external reports produced from the SAP BW solution would be submitted to Users via an automated delivery mechanism. | No |  |  |  | CP Required (CDSP Proposed) | Xoserve | To Be Determined | UKLP
63 |  | UKLP315 | Meter Point Details Report & Sector Breakdown Report | Service Sustaining | Design Gap | A requirement to develop two reports to validate the amendment invoices. 1. Meter Point Details Report 2. Sector Breakdown Report | No |  |  |  | CP Required (CDSP Proposed) | Xoserve | To Be Determined | UKLP
64 |  | UKLP319 | Delivery of Retro | Market Driven | Retro | A requirement to support the delivery of MOD 434 into the UK Link Solution Design. | No |  |  | MOD 573 - Sets implementation date 1st October 2017 | Proposed for Bubbling Under | All | To Be Determined | UKLP
65 | COR3283 |  | Recording DN Siteworks | Market Driven | New Requirement | A requirement to receive Network connection(s) reference numbers and the ability to store these reference numbers in a central system. | No |  |  |  | CP Available (DSC Prioritised) | DNs | To Be Determined | BAU Change | Low
66 | COR3386 |  | New DN role for CMS | Market Driven | New Requirement | A requirement to create a new role that includes all activities that can be undertaken within DNs to facilitate more efficient working practices. | No |  |  |  | CP Available (DSC Prioritised) | DNs | To Be Determined | BAU Change | Low
67 | COR3287 |  | MOD 455s - updating of Meter Asset information by the transporter | Market Driven | New Requirement | A requirement to develop a proposal to update Sites and Meters with Meter Asset details as per MOD455S. | No |  |  |  | CP Available (DSC Prioritised) | DNs | To Be Determined | BAU Change | Medium
68 |  | UKLP325 | Annual shrinkage submission (.ORD ) received from Networks is not getting apportioned correctly when the adjustment period is spanning across Nexus Go live date (01-June-2017) | Service Sustaining | Design Gap | A requirement to correct the smearing process for Annual shrinkage in SAP because the current design is considering the variance period as 6 months and this will not work as expected with the new Go live date as 01-June-2017. If the error persists it will result in incorrect charges present in the amendment invoice (AMS) and will have financial impacts to Networks revenue. | No |  |  |  | CP Required (CDSP Proposed) | DNs | To Be Determined | UKLP

## IA (hidden)
|  | RRC |  |  | Tier 1 | [7 empty] | Tier 2
Change Information |  | Business Area | Lower Level Process | System Impacted | Number of Rules (source) | Impact on current Processes | Data Structure (LDM ) | Application(s) Impacted | External(s) Impact | Interface Impact |  | T1 Impact Assessment Score | Design Impact H/M/L/N | Development timescale H/M/L/N | Testing Impact H/M/L/N | Impact on people H/M/L/N | T2 Impact Assessment Score | Total Impact Score (T1 + T2) | Interlinked with other CRS (CR No.)
Ref | Change Request Description | [8 empty] | Interface Impact | Comments
UKLP CRDBI060 | Read Validation Tolerances | 4. Settle meter point consumption | 4.01.01.06 Validate Meter Read Energy for the Period | SAP | 9 | 1 | 3 | 1 | 0 | 0 |  | 11 | [5 empty] | 2.5
UKLP CRDBI065 | Correction Factor Application | 2. Maintain Supply Meter Point Register 4. Settle meter point consumption | 2.02.02.01 Create Supply Meter Point 2.16.01.01 Identify Outstanding Obligations for SMP 2.16.01.02 Notify Stakeholders of Outstanding Obligations 2.04.02.01 Update Supply Meter Point Details 2.04.02.02 Notify Update of Supply Meter Point Details 4.03 Reconcile Supply Meter Point Energy | SAP | 3 | 1 | 0 | 1 | 0 | 0 | Clear seperation of change from context is needed | 5 | L | N |  |  |  | 0.6
UKLP CRDBI071 | Provision of Formula Year AQ | 2. Maintain Supply Meter Point Register | various SPA processes where S75 record is included in the output file | AMT SAP | 8 | 8 | 0 | 2 | 8 | 0 |  | 26
UKLP CRDBI072 | Design Gaps - Ability To Provide Missing Class 3 Reads | 4. Settle Meter Point Consumption | New Process | AMT SAP | 5 | 1 | 0 | 2 | 1 | 0 |  | 9
UKLP CRDBI073 | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files | 2. Maintain Supply Meter Point Register 4. Settle meter point consumption | 4.01.01.06 Validate Meter Read Energy for the Period 2.10.01.01 Validate Request to Update Asset 2.10.01.02 Validate Asset Update | AMT SAP | 8 | 2 | 3 | 2 | 8 | 0 |  | 20
UKLP CRDBI074 | Prime and Sub Read Requests | 2. Maintain Supply Meter Point Register 4. Settle Meter Point Consumption | 2.17.01.01 Identify Outstanding Meter Read 2.17.01.02 Issue MRA Visit Request 2.17.02.02 Validate Warrant Visit Response 5.01.04.07 Calculate Ancillary Financial Values 4.01.01.01 Validate Meter Read Submission Process that triggers ad-hoc P&S must read | SAP |  | 4 | 0
UKLP IADBI080 | Amendment to the AQ &SOQ File and Field Length | No process impact - Gemini field change required | see change comment | Gemini |  |  | 3
UKLP IADBI096 | IA for strategic solution options for the GDE Offline database | 2. Maintain Supply Meter Point Register 3. Predict, Allocate and Balance Daily Energy 4. Settle Meter Point Consumption 5. Invoice & Collect Charges | many | Gemini SAP SAP BW AMT |  |  | Not enough information
UKLP IADBI109 | Capability to replace a sequence of readings | 4. Settle Meter Point Consumption | 4.01.01.01 Validate Meter Read Submission 4.01.01.06 Validate Meter Read Energy for the Period | SAP |  | 1 | 0
UKLP IADBI112 | Missing Key Data Item from iGT’s to Shippers (Plot Number) | 2. Maintain Supply Meter Point Register | various SPA processes where address or S70 record is included in the output file | AMT SAP
UKLP IADBI113 | Notification of Formula Year AQ & SOQ | 4. Settle meter point consumption | 4.02.05.02 Notify impact of AQ calculation | SAP (+ AMT?)
UKLP IADBI122 | PAF Indicator field inclusion on VAD and ACR files | 2. Maintain Supply Meter Point Register | 2.04.02.01 Update Supply Meter Point Details 2.04.02.02 Notify Update of Supply Meter Point Details | SAP (+ AMT?) CMS Address validation tool |  | 2
UKLP IADBI129 | Meter Asset Provider Report | 2. Maintain Supply Meter Point Register | 2.15.01.01 Identify Relevant Supply Meter Point Information 2.15.01.02 Notify Stakeholders of Relevant Portfolio Data | SAP BW AMT EFT / IX |  | 2
UKLP IADBI134v2 | AQ Consumption history that holds a USRV period (old-world) & Consumption history that hold a faulty period (new world) | 2. Maintain Supply Meter Point Register ?? 4. Settle Meter Point Consumption | 4.02.07.01 Calculate SMP AQ 2.10.01.01 Validate Request to Update Asset 2.10.01.02 Validate Asset Update 4.01.01.01 Validate Meter Read Submission 4.01.05.01 Identify Suspended Reads within the Fault Period 4.01.05.02 Remove Suspended Status 4.04.02.01 Validate Consumption Adjustment Submission 4.04.02.02 Validate Energy for the Consumption Adjustment Period 4.04.02.03 Notify Volume Adjustment Outcome | SAP |  | 8
UKLP IADBI136 | Notification of Twin streams that have calculated an AQ or W/C ( T04, S91 & T50) | 4. Settle meter point consumption | 4.02.05.02 Notify impact of AQ calculation | SAP AMT
UKLP IADBI137 | CUN being issued downstream | 2. Maintain Supply Meter Point Register | 2.05.02.02 Notify Update of CSEP Details | SAP |  | 1
UKLP IADBI140 | .DUP & .DUS file type registration in AMT | External interface layer | AMT layer | AMT
UKLP IADBI142 | Change to NTS files .DDU .DDS & .CPM | 2. Maintain Supply Meter Point Register | 2.15.01.01 Identify Relevant Supply Meter Point Information 2.15.01.02 Notify Stakeholders of Relevant Portfolio Data | SAP or SAP BW |  | 2
UKLP IADBI147 | DDS/DDU file amendment | 2. Maintain Supply Meter Point Register | 2.15.01.01 Identify Relevant Supply Meter Point Information 2.15.01.02 Notify Stakeholders of Relevant Portfolio Data | SAP or SAP BW |  | 2
UKLP IADBI149 | Consumption adjustment flat profile process | 4. Settle meter point consumption | 4.01.08 Calculate Better Estimated DM Meter Reads | SAP
UKLP IADBI151 | The Winter consumption file is not populate the number of exchanges | 4. Settle meter point consumption | 4.02.05.02 Notify impact of AQ calculation | SAP
UKLP IADBI152 | Change to processing ONJOB/ONUPD where existence of a Read marked Suspect as one of the latest activities | 2. Maintain Supply Meter Point Register 4. Settle meter point consumption | 4.01.01.06 Validate Meter Read Energy for the Period 2.10.01.01 Validate Request to Update Asset 2.10.01.02 Validate Asset Update | SAP
UKLP IADBI154 | Retro Updates - Suspecting Reads following Asset Attribute Update | 2. Maintain Supply Meter Point Register | 2.10.03.01 Update Asset Information | SAP |  | 1
UKLP IADBI155 | Retro Updates - Notifying of Suspect Reads | 2. Maintain Supply Meter Point Register | 2.10.03.01 Update Asset Information | SAP |  | 1
UKLP IADBI157 | AMT Validation for No Such File Type | External interface layer | AMT layer | AMT
UKLP IADBI159 | Document Archival in ILM |  |  | SAP or SAP BW ILM
UKLP IADBI162 | Addition of Daily LDZ Unidentified Gas (UG) to National Grid Operational Data Services | 3. Predict, allocate and balance energy | new process to output calculated UIG | SAP AMT
UKLP IADBI168 | CMS Billing Template Class Change Adjsutment Crossover | 4. Settle meter point consumption | 4.03.01.02 Derive The Reconciliation Variance Periods 4.03.01.03 Calculate The Reconciliation Variance Energy | SAP
UKLP IADBI174 | MOD432 incorrectly removed M3.7.3 & M3.7.4 revised meter read to be re-instated in UNC and the associated process | 4. Settle meter point consumption | 4.01.01.01 Validate Meter Read Submission 4.01.01.06 Validate Meter Read Energy for the Period 4.03.01.02 Derive The Reconciliation Variance Periods 4.03.01.03 Calculate The Reconciliation Variance Energy | SAP
UKLP IADBI187 | Siemens Supplier ID Report | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI189 | Transfer reading following a Retro update | 2. Maintain Supply Meter Point Register 4. Settle meter point consumption | 4.01.01.06 Validate Meter Read Energy for the Period 2.10.01.01 Validate Request to Update Asset 2.10.01.02 Validate Asset Update 4.01.04.03 Calculate Estimated Read | SAP |  | 1
UKLP IADBI190 | MNO DVD Validation Tool | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | MNO DVD Validation Tool
UKLP IADBI194 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | Gemini or SAP BW
UKLP IADBI197 | Addition of New fields from CMS being available in BW/IP reporting environment | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | CMS SAP BW
UKLP IADBI198 | Ability to submit a read taken at meter inspection with meter inspection update | 2. Maintain Supply Meter Point Register | 2.04.01.01 Validate Supply Meter Point Change Request 2.04.02.01 Update Supply Meter Point Details | SAP AMT
UKLP IADBI202 | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | 4. Settle meter point consumption | 4.01.01.01 Validate Meter Read Submission 4.01.01.06 Validate Meter Read Energy for the Period | SAP
UKLP IADBI203 | Amendment to U82 record to include the revised NTS optional tariff rate | 2. Maintain Supply Meter Point Register | 2.09.01.02 Notify Acceptance of Contract Confirmation Request 2.09.03.02 Notify Contract Confirmation 2.13.02.02 Notify Supply Meter Point Details | SAP AMT
UKLP IADBI221 | SAP BW Report for Mod534 Offline Database | 5. Invoice & Collect Charges | 5.01.04.07 Calculate Ancillary Financial Values | SAP BW MOD 534 database
UKLP IADBI222v2 | TRAS Tip-off Hotline Data Provision – Enduring Solution | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI223 | Allow for a capacity revision on a Seasonally Large Supply Point | 2. Maintain Supply Meter Point Register | 2.11.01.01 Validate Request to Update Contract 2.11.01.02 Assess for Network Referral 2.11.01.03 Notify Network Referral 2.11.01.04 Issue Request to Network | SAP DN LINK
UKLP IADBI225 | Change number of occurances for K13 record for SSMP’s | See Comment | See Comment | See comment
UKLP IADBI226 | Provide the DMSP with the AQ in the O13 record on the GCC file | 2. Maintain Supply Meter Point Register | 2.09.03.04 Issue Contract Details | SAP AMT
UKLP IADBI233 | Contact Titles – Nullified data – functional change | 2. Maintain Supply Meter Point Register | 2.09.01.02 Notify Acceptance of Contract Confirmation Request 2.09.03.02 Notify Contract Confirmation 2.11.02.02 Notify Contract Change | SAP AMT
UKLP IADBI244 | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW Offline GDE tool
UKLP IADBI246 | Npower MPRN Information report | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI249 | New Vulnerable Customer Needs codes | 2. Maintain Supply Meter Point Register 7. Enable and Support Operational Processes | 2.04.02.01 Update Supply Meter Point Details 2.04.01.01 Validate Supply Meter Point Change Request 7.04 Master and Reference Data Management | SAP AMT SAP BW
UKLP IADBI251 | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI256 | NDM Twin Stream Read Validation | 4. Settle meter point consumption 2. Maintain Supply Meter Point Register | 4.01.01.01 Validate Meter Read Submission 2.10.01.01 Validate Request to Update Asset | SAP
UKLP IADBI257 | Class 1 validation errors (NTS/telemetered/CSO sites) | 2. Maintain Supply Meter Point Register | 2.11.01.01 Validate Request to Update Contract 2.07.01.01 Validate Contract Nomination Request 2.04.01.01 Validate Supply Meter Point Change Request | SAP
UKLP IADBI258 | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | ?? | Parts of System that process RCI and ANT files See change comment | SAP AMT SAP BW ?
UKLP IADBI262 | Change to RGMA validations for LI confirmations | 2. Maintain Supply Meter Point Register | 2.10.01.01 Validate Request to Update Asset 2.10.01.02 Validate Asset Update 2.10.01.03 Notify Rejection of Asset Update Request | SAP
UKLP IADBI267 | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | 2. Maintain Supply Meter Point Register | 2.04.01.01 Validate Supply Meter Point Change Request | AMT
UKLP IADBI268 | CNG Monthly Shipper Pack | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI270 | Amend referral rules for class 2 smaller LSP’s | 2. Maintain Supply Meter Point Register 7. Enable and Support Operational Processes | 7.04 Master and Reference Data Management 2.11.01.02 Assess for Network Referral 2.07.01.02 Assess Nomination Request for Network Referral | SAP SAP BW
UKLP IADBI271 | Work Items unique Task ID request
UKLP IADBI272 | Capacity referral raised in error following Nomination | 2. Maintain Supply Meter Point Register | 2.11.01.02 Assess for Network Referral 2.07.01.02 Assess Nomination Request for Network Referral | SAP
UKLP IADBI273 | PSR requirements – Vulnerable Customer data requirements | Duplicate of UKLP IADBI249 | Duplicate of UKLP IADBI250
UKLP IADBI276 | iGT IIL & IDL files splitting - manual workaround provided in Market Trials into Production post go live | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP
UKLP IADBI277 | Treatment of values in the CDR | 2. Maintain Supply Meter Point Register | 2.10.01.02 Validate Asset Update 2.10.01.01 Validate Request to Update Asset | SAP
UKLP IADBI279 | Pending capacity amendment with Ratchet | 4. Settle meter point consumption | 4.02.01.03 Revise The SOQ | SAP
UKLP IADBI280 | File Format Should Have Changes | most | many | SAP AMT SAP BW ?
UKLP IADBI281 | DN Sales (Outbound Services) Requirements for UKLP enduring solution | 5.02.02.03 Create Invoice | 5.01.05.01 Validate Calculated Charge Values 5.02.02.01 Calculate Invoice Items 5.02.02.03 Create Invoice | SAP AMT
UKLP IADBI282V2 | SAP BW Scope Changes – Descoped Reports | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI284v2 | Ability to reduce Capacity on DM Meter points outside on CRP (as per UNC G5.2) | 2. Maintain Supply Meter Point Register 5. Invoice & Collect Charges | 2.11.01.01 Validate Request to Update Contract 2.07.01.01 Validate Contract Nomination Request 5.01.04.03 Calculate Core Financial Values | SAP
UKLP IADBI285 | BUS Nomination Enquiry Report | 7. Enable and Support Operational Processes | 7.01 Provide Access to Data and Management Information | SAP BW
UKLP IADBI287 | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | 5. Invoice & Collect Charges | 5.01.04.03 Calculate Core Financial Values | SAP
UKLP IADBI289 | Class 4 CSEPS Reconciliation Variance Identification
UKLP IADBI291 | AMR report post Go Live
UKLP IADBI292 | Changes to the upper parameter of the XDO partial refresh file.
UKLP IADBI293 | Splitting of the DXI inbound and DXR outbound file from the DCC.
UKLP IADBI300 | Unique Sites – Adding profiles
UKLP IADBI301 | Annual Production and notification of LIS-3years read
UKLP IADBI305 | Mod431 – Validations against file header and data within records
UKLP IADBI306 | Amend functionality to send GCC file to DMSP when Class 1 Confirmation Requests Lapse due to objection.
UKLP IADBI307 | Proposal for the process improvement for SI files
UKLP IADBI309 | UMR Hierarchy Amendment in AMT
COR4186 | DES Access Restriction and Audit
COR4248 | Quarterly smart metering reporting for HS&E and GDNs
UKLP IADBI317 | Sybase NLS Solution Design Gap
UKLP IADBI132A | Delivery via Automated Integration Solution for all IP reports from SAP BW
UKLP IADBI315 | Meter Point Details Report & Sector Breakdown Report
Note on G3: National Grid: based on C,D,E
Note on G8: National Grid: Which L4 are impacted?

## Report CRs (hidden)
Source | CR Number | Internal or External | Change Driver | CR Title | Type of change | PCB Status | Date Raised | CR Originator | Value Chain Impact | RRC Ref | Process Impacted | Relates to Mod No. | Mod status | Mod Timescale | System Impacted | Owner | CR, SDG, DFT | Originator Priority | XRN | Reason For Rejection/Deferral | Work Around available | Work Around Comment | External Impact For Deferred Items | Required by date | Comments | WIPRO IA Completed | Links with CR | CR Document
UKLP deffered | UKLP IADBI129 | Internal | Market Driven | Meter Asset Provider Report | Report | On Hold - Deferred for future release | 2015-08-24 | Customer and Contracts team – Industry Engagement | 4.0 Settle meter point consumption |  |  | 432 | Final Modification Report | 1st June 17 | UKLink. | Fiona Mills | CR | 4 - Low | 3811 |  | No |  | Shippers and MAF Report | 2017-11-01
UKLP deffered | UKLP IADBI187 | Internal | Market Driven | Siemens Supplier ID Report | Report | On Hold - Deferred for future release | 2016-04-13 | Customer and Contracts team (commercial report) |  |  |  | 432 | Final Modification Report | 1st June 17 | UKLink. | Fiona Mills |  | blank |  |  | No |  | Shippers
UKLP deffered | UKLP IADBI194 | Internal | Application | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | Report | On Hold - Deferred for future release | 2016-04-28 | Beverley Viney (National Grid Tranmission Network) | 5. Invoice & Collect Charges |  |  | 432 | Final Modification Report | 1st June 17 | UKLink. | Lorraine Cave |  | 2 - High |  |  | No
UKLP deffered | UKLP IADBI221 | Internal | Application | SAP BW Report for Mod534 Offline Database | Report | On Hold - Deferred for future release | 2016-06-09 | [7 empty] | SAP BW – Universe Configuration Change and Report Build. | Darren Dredge |  | 2 - High |  |  | No |  |  |  |  | Yes
UKLP deffered | UKLP IADBI222v3 | Internal | Infrastructure | TRAS Tip-off Hotline Data Provision – Enduring Solution | Report | On Hold - Deferred for future release | 2016-06-10 | There are three industry changes supporting this:  UNC Modification 0584 and 0574  SPAA CP16/325  COR3995 |  |  |  | 432 | Final Modification Report | 1st June 17 | UKLink. | Lorraine Cave |  | 2 - High |  |  | No | No Workaround needed |  | Nov 16
UKLP deffered | UKLP IADBI226 | Internal | Business Excellence | Provide the DMSP with the AQ in the O13 record on the GCC file | Report | On Hold - Deferred for future release | 2016-06-24 | UKLP Tranche 1a | 5. Invoice & Collect Charges |  |  | n/a | [5 empty] | blank |  |  | Yes
UKLP deffered | UKLP IADBI268 | External | Business Excellence | CNG Monthly Shipper Pack | Report | On Hold - Deferred for future release | 2016-10-19 | Portfolio |  |  |  | 432 | Final Modification Report | 1st June 17 | IP and several offline databases (BICC Team) | Dave Turpin |  | 3 - Medium |  |  | No
UKLP deffered | UKLP IADBI285 | External | Application | BUS Nomination Enquiry Report | Report | On Hold - Deferred for future release | 2017-01-16 | Portfolio |  |  |  | 432 | Final Modification Report | 1st June 17 | Reporting | Dave Turpin |  | 3 - Medium |  |  | No
UKLP deffered | UKLP IADBI291 | Internal | Application | AMR report post Go Live | Report | On Hold - Deferred for future release | 2017-02-01 | [8 empty] | Darren Jackson |  | 4 - Low |  |  | No
Note on Y1: National Grid: Confirm what this is?

## R1.1 (hidden)
Source | CR Number | Internal or External | External Impacted Parties | Service Area | Service Line Reference | Drivers | CR Title | Type of change | Benefit/Case for Change | PCB Status | Date Raised | CR Originator | Value Chain Impact | RRC Ref | Process Impacted | Relates to Mod No. | Mod status | Mod Timescale | System Impacted | Owner | CR, SDG, DFT | Originator Priority | Purposed Priority | XRN | Reason For Rejection/Deferral | Workaround available | Workaround Frequency | Workaround Effort | Workaround Comments | Required by date (Original) | Purposed Date | Comments | WIPRO IA Completed | Links with CR | CR Document | CR IA Status | Share Externally
UKLP deffered | UKLP IADBI113 | External | Shippers | Service Area 6: Annual Quantity, DM Supply Point and Offtake Rate Reviews | DS-CS SA6 - 03 | Service Sustaining | Notification of Formula Year AQ & SOQ | System/Process | Sevice Agreement - Missed Req's | On Hold - Deferred for future release | 2015-07-07 | UKLP Tranche 1a | 5. Invoice & Collect Charges |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. | Emma Smith/Susan Prosser | SDG | 1 - Critical |  | 3747 |  | No |  |  |  | 2018-03-20 | 1st Nov | this change must be deliver ASAP after Go Live, Nov 17 - it was advised by Siva we implement this change prior to November when the jobs run for the formula year AQ/SOQ in order to ensure the data gets written to the right tables in order to notify in file. (ES) |  |  | IADBI113v2 | Release 1.1 | No
UKLP deffered | UKLP IADBI142 | External | NTS |  |  | Business Excellence | Change to NTS files .DDU .DDS & .CPM | System/Process | Continous Impovement | On Hold - Deferred for future release | 2015-10-05 | Dave Turpin |  |  |  | n/a | n/a | n/a | SAP | Dave Turpin | CR | 1 - Critical | ? | 3879 | New Req |  |  |  |  | 2017-06-01 | ? | Group with 147, high volume/performance |  |  | IADBI142 | Release 1.1 | No
UKLP deffered | UKLP IADBI147 | External | NTS and Shippers |  |  | Business Excellence | DDS/DDU file amendment | System/Process | Continous Impovement | On Hold - Deferred for future release | 2015-10-14 | Distribution Networks |  |  |  | n/a | n/a | n/a |  | Dave Turpin | CR | 1 - Critical | ? | 3887 |  | Yes |  |  |  | 2017-06-01 | ? | Group with 142 high volume/performance 12/04 - we have under increasing pressure from NTS to make the required changes to the DDU/DDS files (I think there is also a secondary change for DDS/DDU that we might want to consider at the same time) (ES). |  |  | IADBI147 | Release 1.1 | No
UKLP deffered | UKLP IADBI159 | Internal | Xoserve |  |  | Business Excellence | Document Archival in ILM | System/Process | Sevice Agreement - | On Hold - Deferred for future release | 2015-11-26 | Padmini Duvvuri |  |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. | Max Pemberton | CR | 1 - Critical |  | 3910 | [5 empty] | 2017-03-01 |  | Priority after go live |  |  | IADBI159 | Release 1.1 | No
UKLP deffered | UKLP IADBI249 | External | Shipper (Npower) |  |  | Market Driven | New Vulnerable Customer Needs codes | System/Process | New Requirment | On Hold - Deferred for future release | 2016-08-05 | External |  |  |  | 432 | Notice of Implementation | 1st June 17 | AMT, PO, SAP ISU | Steve Nunnington |  | 1 - Critical | [9 empty] | agreed to implement by November 17 |  |  | IADBI249v2 | Release 1.1 | No
UKLP deffered | UKLP IADBI272 | Internal | Networks & Shippers |  |  | Market Driven | Capacity referral raised in error following Nomination | System/Process | Sevice Agreement - Missed Req's | On Hold - Deferred for future release | 2016-11-09 | UKLP Tranche 1a |  |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. |  |  | 1 - Critical | [9 empty] | Before R2 |  |  | IADBI272 | Release 1.1 | Yes
UKLP deffered | UKLP IADBI279 | Internal | Shippers |  |  | Service Sustaining | Pending capacity amendment with Ratchet | System/Process | Sevice Agreement - Missed Req's | On Hold - Deferred for future release | 2016-12-06 | UKLP Tranche 1a |  |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. |  |  | 1 - Critical | [9 empty] | Ratchets commence from 1st October, there is no workaround to manage this, a new shipper could take on site at lower SOQ and thus ratchet again. |  |  | IADBI279v2 | Release 1.1 | No
UKLP deffered | UKLP IADBI132A | Internal | Xoserve |  |  | Service Sustaining | Delivery via Automated Integration Solution for all IP reports from SAP BW | System/Process | Continous Impovement | On Hold - Deferred for future release | 2015-07-01 | Lee Chambers | [6 empty] | SAP BI SAP AMT/PO SAP Basis Team | Lee Chambers | CR | 1 - Critical | [9 empty] | Orignally closed and now deferred | No |  |  | Release 1.1
UKLP deffered | UKLP IADBI315 | Internal | Xoserve |  |  | Service Sustaining | Meter Point Details Report & Sector Breakdown Report | Report | Continous Impovement | On Hold - Deferred for future release | 2017-03-28 | Simon Bissett/ Michelle Downes | [6 empty] | SAP-BW | Mark Cockayne | CR | 1 - Critical | [7 empty] | 2017-07-01 | [5 empty] | Release 1.1
UKLP deffered | UKLP IADBI192 | Internal | Xoserve |  |  | Market Driven | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | Report | Continous Impovement | On Hold - Deferred for future release | 2016-04-19 | Paul Orsler | [6 empty] | SAP-BW | Paul Orsler | CR | 1 - Critical
`
Note on AE1: National Grid: Confirm what this is?
Note on AL1: National Grid: ES View point
Note on W9: National Grid: Review priority
Note on W10: National Grid: Review priority

## UKLP Defect (HPQC) (hidden)
Source | Defect ID | Governance Progress | Status | Target Cycle | Detected in Cycle | Variant | Summary | Target Resolution Date | Process | Severity | Detected on Date | Test Phase | Non-Shippers | Shippers | Defect Detected Area
UKLP Defect (HPQC) | 13892 | PGL | Requires CR | Post Go Live | MT Regression |  | MTR - SSE_R401 - IT360 629691 - SAP ISU - MBR - Read reason Code in MBR M03 is invalid - 1528 |  | Reads- Read upload | 3-Moderate | 2017-04-11 | Regression Testing |  | Sse | SAP IS-U
UKLP Defect (HPQC) | 13861 | PGL | Requires CR | Post Go Live | Operational Readiness |  | DNs have requested that the SRL/ SRZ files are split by each DN so that they only recieve the data that is pertinent to them - this is not how legacy works and a change will need to be made POST GO LIVE |  | SPA - DN Interruptions | 4-Minor | 2017-04-04 | MarketTrials |  |  | SAP IS-U
UKLP Defect (HPQC) | 13823 | PGL | Requires CR | Post Go Live | MT Regression |  | MTR - N/A - N/A - SAP ISU - ORD Submission - incorrect smearing done in Feb Reconciliation. Resulted in wrong invoice value |  | Billing & Invoicing - reconciliation | 3-Moderate | 2017-03-27 | Regression Testing |  |  | SAP IS-U
UKLP Defect (HPQC) | 13836 | PGL | Requires CR | Post Go Live | MT Regression |  | MTR - N/A - N/A - SAP ISU - CGI - File failure as decimal point issue for the fields PER_BREACH_CON_MAX_AQ_SMP and PER_BREACH_IGT_SYSTEM_MAX_AQ in multiple segments. |  | AMT functional rejection | 3-Moderate | 2017-03-08 | MarketTrials |  |  | SAP IS-U
UKLP Defect (HPQC) | 13481 | PGL | Requires CR | Post Go Live | Operational Readiness |  | BB_REG_01: Incorrect start date determination for Capacity adjustments |  | RGMA - Asset Install | 3-Moderate | 2017-03-06 | MarketTrials |  |  | SAP IS-U
UKLP Defect (HPQC) | 13468 | PGL | Requires CR | Post Go Live | MT Regression |  | MTR - CNG_R007/3.8 - IT360 *613414* - AMT MF - CNF - No CFR response |  | SPA - Registration | 3-Moderate | 2017-03-01 | MarketTrials |  | CNG | AMT Market Flow
UKLP Defect (HPQC) | 13352 | PGL | Requires CR | Post Go Live | Operational Readiness |  | On shipper confirmation going to Lapsed status GCC is not generated to DMSP THIS IS DESIGN GAP raised for Change request - |  | SPA - Registration | 4-Minor | 2017-02-17 | MarketTrials |  |  | SAP IS-U
UKLP Defect (HPQC) | 13309 | PGL | Requires CR | Post Go Live | MT Regression |  | WORKAROUND: MTR - RWE_R071/15.2, GAZ_R021/15.2, - IT360 *606114*, *608258*, *610613* - AQI - AQ Correction functionality not working as per BRD - 2362, MT_RG_00230 |  | AQ/CWV - Functional rejection | 3-Moderate | 2017-02-15 | MarketTrials |  | Gazprom;nPower;Winchester | SAP IS-U
UKLP Defect (HPQC) | 13087 | PGL | Requires CR | Post Go Live | MT Regression |  | CR 298 : MTR - N/A - N/A - SAP ISU - CAP,COM, REC - Wrong CAP, COM and REC billing done for CSEP installations with Max AQ/SOQ change |  | Reconciliation Variances | 3-Moderate | 2017-01-18 | MarketTrials |  |  | SAP IS-U
UKLP Defect (HPQC) | 12902 | PGL | Requires CR | Post Go Live | Operational Readiness | WORKAROUND | WORKAROUND - Following the Xoserve auto/manual asset attach process there is no notification to the Shipper to provide the asset details and installation read for Class 1 and 2 site |  | RGMA - Asset Install | 3-Moderate | 2016-12-20 | Backbilling UAT |  |  | SAP IS-U
UKLP Defect (HPQC) | 12867 | PGL | Requires CR | Post Go Live | Operational Readiness |  | BB: GSR02 - Charges calculated incorrectly for pre go live period |  | Billing & Invoicing - reconciliation | 2-Major | 2016-12-14 | Backbilling UAT |  |  | SAP IS-U
UKLP Defect (HPQC) | 12870 | PGL | Requires CR | Post Go Live | Operational Readiness | WORKAROUND | CR289 : BB: GSR_TC_06 - CSEP Grid change is not considered for Rec billing correctly |  | Reconciliation Variances | 3-Moderate | 2016-12-14 | Backbilling UAT |  |  | SAP IS-U
UKLP Defect (HPQC) | 6476 | PGL | Requires CR | Post Go Live | AMT Testing |  | CR128 v 2 : ONJOB_AMT_REJECTIONS_issue with FUTURE DATE header |  | RGMA - Validation Testing | 3-Moderate | 2015-12-28 | UAT |  |  | AMT Market Flow

## External XRN's (hidden)
XRN Number | Title | Area | Date Submitted | Authorising Manager | Submitted By | Customer Target Delivery Date | System Affected | Request Type | Status | ClearQuest Ref | Allocated To | Associated References | HLE Submitted Date | Number of Days Effort - Off Shore | Number of Days Effort - On Shore | Comments | HLE Approved By | Category | Approved By | HLE Cost | HLE Approved Date | Category Change Date | Complexity | Pot Number | UKLP XRN | UKLP Type | UKLP ID | UKLP STATUS | UKLP Title | UKLP Date Raised | UKLP Associated References | UKLP Fast Track | UKLP Raised by | UKLP Source of Change | UKLP Authorising XM1 Manager | UKLP Date Approval Required | UKLP Portfolio Impact | UKLP Required in Legacy | UKLP Portfolio Impact Details | UKLP Priority | UKLP Requested Implementation Date | UKLP Impacted System(s) | UKLP Driver | UKLP Reason / Justification
4010 | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) |  | 2016-04-12 | Dave Turpin | Beverly Viney |  |  | Change Order | Deffered |  | Deffered until Future relase UKL |  |  |  |  | 04.05.16: Cm Flash assement came back as deferred until a furure release into UK Link Phase 2. Cm has written to Beverly to advise her of this, 27/04/16CM has raised the UKL CR and sent to emma Smith 21/04/16: This CO has been deferred in ICAF today to be |  | XRN - Live | Deferred ICAf 20.04.016 | [5 empty] | FALSE | [6 empty] | FALSE |  |  |  |  | FALSE | FALSE
4057 | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | ASA | 2016-06-23 |  | Richard Pomroy | 2016-10-01 |  | Change Order | Deferred until Future Release Uk Link |  | TBC | COR3745 |  |  |  | 12/07/16: The CO has been discussed with RP & DD. Cm has sent the acknowlegment to RP confirming that this will be completed in a future release of UK Link 06/07/16: This CO has been redrafted by Darran Dredge and aent onto Richard Pomroy, Change acknowle |  | XRN - Live | ICAF-29/06/16 | [5 empty] | FALSE | [6 empty] | FALSE |  |  |  |  | FALSE | FALSE
4067 | ETTOS Data Provision – Phase 2 (Post Nexus) |  | 2016-07-15 | Jane Rocky | Alex Ross |  |  | Change order | Long term Defferal |  | TBC | COR3995 |  |  |  | 20/07/16; CM This CO will be approved for future release of UK Link Programme. The CO is the 2nd part to COR3995 and will be the reporting element. Crime Stoppers are aware that there will be a break in service when go live happens. Charlie Haley to raise |  | XRN - Live | ICAf - 20/07/16- Long Term defferal | [5 empty] | FALSE | [6 empty] | FALSE |  |  |  |  | FALSE | FALSE
4080 | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) |  | 2016-07-28 | Lorraine Cave | Richard Pomroy |  |  | Change Order | Deferred | [6 empty] | 12.09.16- CM has sent acknowledgment to networks today to advise deffered into future release of UK Link programme. Update from UK Link PMO - 12.09.16 - CR251 - Deferred at flash meeting on 06.09.16, this will now be put into future release plan of UK Lin |  | XRN - Live | ICAF - Long term defferal for UK Link | [5 empty] | FALSE | [6 empty] | FALSE |  |  |  |  | FALSE | FALSE
4097 | Changes to the Vulnerable Customer codes |  | 2016-09-07 |  | Jo Fergusson | 2017-06-01 |  | Change order | Long Term Deffered | [6 empty] | 14/09/16: This Change Order will be placed on long term deferred for future release of UK Link. This change is already with UK Link and discussions have taken place between Tahera and Emma Smith. Emma has said this will be a simple change but a large amou |  | XRN - Live | ICAF Long Term Deffered - 14/09/16 | [5 empty] | FALSE | [6 empty] | FALSE |  |  |  |  | FALSE | FALSE

## Closed CR (hidden)
Source | CR Number | CP/CO Number | Next Action | Breach of Mod | CR Title | Internal or External | External Impacted Parties | Service Area | Service Line Reference | Drivers | Type of change | Benefit/Case for Change | PCB Status | Date Raised | CR Originator | Value Chain Impact | RRC Ref | Process Impacted | Relates to Mod No. | Mod status | Mod Timescale | System Impacted | Owner | CR, SDG, DFT | Originator Priority | Purposed Priority | XRN | Reason For Rejection/Deferral | Workaround available | Workaround Frequency | Workaround Effort | Workaround Comments | Required by date (Original) | Purposed Date | Comments | WIPRO IA Completed | Links with CR | CR Document | CR IA Status | Shared with DSC ChC | Data shared with DSC | T2 SME Support Required | DSC Priority 10/05/2017
UKLP deffered | UKLP IADBI282V2 |  |  |  | SAP BW Scope Changes – Descoped Reports | Internal | ? |  |  | Business Excellence | System/Process | Continous Impovement | On Hold - Deferred for future release | 2016-12-19 | Lee Chambers |  |  |  | 432 | Notice of Implementation | 1st June 17 | SAP BW | Lee Chambers |  | 3 - Medium | [9 empty] | check with LC This CR was raised for information and lessons learned from the programme. |  |  | IADBI282 | Progress to T1 |  |  | Emma Smith
Note on AH1: National Grid: Confirm what this is?

## Summary (hidden)
All CR Sources
Sources | Total
UKLP Defect (HPQC) | 22
Grand Total | 22
Row Labels | Count of Source
UKLP deffered | 66
Grand Total | 66
Total | 88
Below sources to be reviewed:
Business & Technical Debt | 0
Change Backlog | 4 | These are have been confirm and already form part of UKLP deffered figures
New market Requests | 4
Xoserve Roadmaps | 0
CR Priority
UKLP Defect |  | UKLP Deffered
Row Labels | Count of Priority | Row Labels | Count of Originator Priority
2-High | 2 | 1 - Critical | 9
3-Moderate | 20 | 2 - High | 25
Grand Total | 22 | 3 - Medium | 30
|  | 4 - Low | 10
|  | Not Provided | 1
|  | Grand Total | 75

## Sheet5 (hidden)
Count of Source |  |  |  |  | Dimension | Application
75 |  |  | Dimension | Application | Type of change | System
Row Labels | Count of Dimension |  | Row Labels | Count of Type of change | Row Labels | Count of Originator Priority
Application | 30 |  | Report | 3 | 1 - Critical | 6
Business Excellence | 21 |  | System | 27 | 2 - High | 7
Infrastructure | 10 |  | Grand Total | 30 | 3 - Medium | 9
Market Driven | 14 |  |  |  | 4 - Low | 5
Grand Total | 75 |  |  |  | Grand Total | 27
|  |  | Dimension | Business Excellence | Dimension | Business Excellence
[5 empty] | Type of change | System
|  |  | Row Labels | Count of Type of change
|  |  | Report | 2 | Row Labels | Count of Originator Priority
|  |  | System | 19 | 1 - Critical | 2
|  |  | Grand Total | 21 | 2 - High | 7
[5 empty] | 3 - Medium | 9
Row Labels | Count of Type of change |  |  |  | 4 - Low | 1
Report | 9 |  |  |  | Grand Total | 19
System | 66 |  | Dimension | Infrastructure | Dimension | Infrastructure
Grand Total | 75 |  |  |  | Type of change | System
|  |  | Row Labels | Count of Type of change
|  |  | Report | 1 | Row Labels | Count of Originator Priority
|  |  | System | 9 | 2 - High | 3
|  |  | Grand Total | 10 | 3 - Medium | 6
[5 empty] | Grand Total | 9
Row Labels | Count of Originator Priority |  | Dimension | Market Driven
1 - Critical | 9 |  |  |  | Dimension | Market Driven
2 - High | 25 |  | Row Labels | Count of Type of change | Type of change | System
3 - Medium | 30 |  | Report | 3
4 - Low | 10 |  | System | 11 | Row Labels | Count of Originator Priority
Not Provided | 1 |  | Grand Total | 14 | 1 - Critical | 1
Grand Total | 75 |  |  |  | 2 - High | 4
[5 empty] | 3 - Medium | 4
Dimension | Business Excellence |  |  |  | 4 - Low | 2
[5 empty] | Grand Total | 11
Count of Originator Priority | Column Labels
type of Change | External | Internal | Grand Total
Report
2 - High | 1 | 3 | 4
3 - Medium | 2 |  | 2
4 - Low |  | 2 | 2
Not Provided |  | 1 | 1
System
1 - Critical |  | 9 | 9
2 - High | 4 | 17 | 21
3 - Medium | 4 | 24 | 28
4 - Low | 3 | 5 | 8
Grand Total | 14 | 61 | 75

## Sheet1 (hidden)
Row Labels | Count of Drivers
Business Excellence | 35
Market Driven | 14
Service Introduction | 1
Service Sustaining | 27
Grand Total | 77
Drivers | Market Driven
Row Labels | Count of Drivers
1 - Critical | 3
2 - High | 3
3 - Medium | 1
4 - Low | 6
Not Provided | 1
Grand Total | 14
Drivers | Market Driven
Row Labels | Count of Drivers
1 - Critical | 3
2 - High | 3
3 - Medium | 1
4 - Low | 6
Not Provided | 1
Grand Total | 14

## Sheet2 (hidden)
XRN
3656
3661
3667
3668
3669
3670
3676
3699
3732
3477
3747
3764
3811
3866
3868
3869
3877
3879
3887
3889
3892
3872
3873
3889
3910
0

## Sheet7 (hidden)
Source | CR Number | CP/CO Number | Next Action | Breach of Mod | CR Title | Internal or External | External Impacted Parties | Service Area | Service Line Reference | Drivers | Type of change | Benefit/Case for Change | PCB Status | Date Raised | CR Originator | Value Chain Impact | RRC Ref | Process Impacted | Relates to Mod No. | Mod status | Mod Timescale | System Impacted | Owner | CR, SDG, DFT | Originator Priority | Purposed Priority | XRN | Reason For Rejection/Deferral | Workaround available | Workaround Frequency | Workaround Effort | Workaround Comments | Required by date (Original) | Purposed Date | Comments | WIPRO IA Completed | Links with CR | CR Document | CR IA Status | Shared with DSC ChC | Data shared with DSC | T2 SME Support Required | DSC Priority 10/05/2017
| UKLP IADBI194 | 4040 | Emailed for update COR |  | Billing History by all NTS capacity / commodity related charges (from Nexus implementation onwards) | External | DN |  |  | Market Driven | Report | Service Sustaining | On Hold - Deferred for future release | 2016-04-28 | Beverley Viney (National Grid Tranmission Network) | 5. Invoice & Collect Charges |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. | Darran Dresge |  | 2 - High | [7 empty] | 2018-05-01 |  | The first extract of this was delivered by Gemini/ME team. The data is from Gemini source system, the same extract will need to be run for this, Darran Dredge will have more information on this |  |  | IADBI194 | Progress to T1 |  |  | Emma Smith
| UKLP IADBI142 |  | Emailed for update COR |  | Change to NTS files .DDU .DDS & .CPM | External | NTS |  |  | Business Excellence | System/Process | New Requirment | On Hold - Deferred for future release | 2015-10-05 | Dave Turpin |  |  |  | n/a | n/a | n/a | SAP | Dave Turpin | CR | 1 - Critical | ? | 3879 | New Req |  |  |  |  | 2017-06-01 | ? | Group with 147, high volume/performance |  |  | IADBI142 | Release 1.1 |  |  | Emma Smith
| UKLP IADBI096 | 3699 | Emailed for update COR |  | IA for strategic solution options for the GDE Offline database | Internal | DN & Shippers |  |  | Business Excellence | System/Process | Continous Impovement | On Hold - Deferred for future release | 2015-05-15 | SAP BW (IP & DES) | 4.0 Settle meter point consumption |  |  |  | Notice of Implementation | 1st June 17 | UKLink. | Lee Chambers | CR | 2 - High | 4 - Low | 3699 | [7 empty] | Still needed in addition to CR012 11/04 - Down Graded priority to low |  |  | IADBI096 | Progress to T1 |  |  | Lee Chambers | L
PNUNC | UKLP IADBI112 | No COR required | Emailed for update COR |  | Missing Key Data Item from iGT’s to Shippers (Plot Number) | External | IGT |  |  | Business Excellence | System/Process | New Requirment | On Hold - Deferred for future release | 2015-07-07 | IE | 6. Develop & Deliver Industry Change |  |  | 440 |  |  |  | Lee Chambers | SDG | 2 - High | ? | 3477 |  | No |  |  |  | 2017-11-01 |  | SN to confirm whether this CR is still required in repect to cost may require a new CO 28/04 - SN confirm this is still required |  |  | IADBI112 | Progress to T1 |  |  | Emma Smith
| UKLP IADBI273 |  | Emailed for update COR |  | PSR requirements – Vulnerable Customer data requirements | External | Shippers |  |  | Market Driven | System/Process | New Requirment | On Hold - Deferred for future release | 2016-11-11 | OFGEM |  |  |  | Confirm MOD Number with SN | Final Modification Report | 1st June 17 | UKLink. | Steve Nunnington |  | 2 - High | 1. Critical | [8 empty] | 25/04 - ES to coonfirm this is not a duplicate |  |  | IADBI273 | Progress to T1 |  |  | Emma Smith | H
| UKLP IADBI222 | COR3995 - this is inflight. | Emailed for update COR |  | TRAS Tip-off Hotline Data Provision – Enduring Solution | Internal |  |  |  | Business Excellence | Report | New Requirment | On Hold - Deferred for future release | 2016-06-10 | There are three industry changes supporting this:  UNC Modification 0584 and 0574  SPAA CP16/325  COR3995 |  |  |  | 432 | Notice of Implementation | 1st June 17 | UKLink. | Lorraine Cave |  | 2 - High | [6 empty] | No Workaround needed | Nov 16 |  |  |  |  | IADBI222v3 | Progress to T1 |  |  | Emma Smith
| UKLP IADBI277 |  | Emailed for update COR |  | Treatment of values in the CDR | External | Shippers |  |  | Business Excellence | System/Process | Design Gap | On Hold - Deferred for future release | 2016-12-05 | Work Stream / Delivery Tower / Portfolio |  |  |  | 432 | Notice of Implementation | 1st June 17 |  | David Addison |  | 4 - Low | [12 empty] | IADBI277 | Progress to T1 |  |  | Emma Smith

## Sheet3 (hidden)
Drivers | (All)
CR IA Status | (Multiple Items)
Internal or External | (All)
. | Next Actions
Case for Change | Bubbling under | CO/CP Required | DSC to prioritise | Emailed for update COR | Grand Total
Continous Impovement | 3 |  | 2 | 1 | 6
Design Gap | 9 | 11 |  | 1 | 21
New Requirment | 12 |  | 8 | 4 | 24
Retro |  | 6 |  |  | 6
Service Sustaining |  | 13 |  | 1 | 14
Grand Total | 24 | 30 | 10 | 7 | 71