## Introduction
Forward Work Plan
Background
Ofgem published its final proposals for the Code Governance Review Phase 3 (CGR3) in March 2016. One of the proposals makes recommendations for Code Administrators to develop a forward work plan, to enable code administrators to manage change at a strategic level.
Objective
The objective of this Forward Work is to coordinate the project management of ‘major’ industry change, through on-going oversight of the end-to-end delivery of significant programmes and central systems changes.
Scope
The scope of the Forward Work Plan is based on the annually agreed workstreams. The workstreams for 2017 are listed below: * Smart metering * Half Hourly settlement * European harmonisation * Faster and more reliable switching * Other code specific considerations
Need more information?
For more information regarding a specific programme or change, please contact the responsible Code Administrator:
Code Administrator | Code
ElectraLink Ltd | Distribution Connection Use of System Agreement (DCUSA)
Supply Point Administrator Agreement (SPAA)
ELEXON | Balancing and Settlement Code (BSC)
Energy Networks Assocation | Distribution Code
Gemserv | iGT Uniform Network Code (IGT UNC)
Master Registration Agreement (MRA)
Smart Energy Code (SEC)
Joint Office of Gas Transporters | Uniform Network Code (UNC)
National Grid | Connection and Use of System Code (CUSC)
Grid Code
System Operator – Transmission Owner Code (STC)

## Headlines
Headlines
The Forward Work Plan headlines provide an overview of the key updates around the priority areas. The headlines are provided when and as they arise.
Workstream 1. Smart Metering
* DCC Go-Live extended to 30 September 2016 * Potential impoct on UEPT R1.3 start date, due to DCC Go-Live delay
Workstream 2. Half Hourly Settlement
* Example * Example
Workstream 3. European Harmonisation
* Example * Example
Workstream 4. Faster Switching
* Example * Example
Workstream 5. Code Specific Consideratiions
* Example * Example

## Horizon (All)
Horizon Scanning
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation. Key (I) - Industry impact (L) Legislative impact (R) Regulatory impact
Lead Code Admin is ELEXON, Contact 020 7090 7755
Headlines - (18/08/16) DCC Go-Live, previously expected to be delivered in Summar 2016, has been extended to 30 September 2016
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
DCC Go-Live
(L) (High)
BREXIT
(L) (Medium)
UK General Election (2020)
(L) (Medium)
Smart meter roll out complete
(I) (Medium)
Faster Switching and Centralised Registration
(I) (High)
NEXUS
(I) (High)
RAASP
(I) (High)
NEXUS Ph2
(I) (High)
FGO Ph2 Imp. (Q2 17)
(I) (Medium)
EU CAM (Am & Inc)
(R) (Medium)
Priority Svs Register
(R) (Medium)
EU Tariff Code
(R) (High)
Alternative Sources of Gas
(I) (Low)
Gemini Rewrite
(I) (High)
Gas Settlement Evolution
(R) (High)
EU Reform
(R) (High)
COLOUR KEY
Industry-wide change
Electricity
Gas

## Commentary 2+ yrs
This sheet sets out the changes identified in the 2-5 years timescale on the Horizon
Horizon item | What is it? | Which Codes might be affected? | What happens next? | For more information
Nexus Phase 2 | During specification and build of the new UK Link systems under Project Nexus, a number of 'further requirements' were identified by the UNC Workgroup that participants believed would add value if made available. These were too late to be included in the inital release and were therefore compiled into a Requirements Log that was to be subject to more detailed assessment in due course. | UNC iGT UNC | It is anticipated that further UNC modifications would be required to enable the changes identified. No work is anticipated on this until after the current Nexus deliverables - Phase 1 and RAASP - are more certain in H1 2017. | The Requirements Log can be viewed here: http://www.gasgovernance.co.uk/nexus/090816 A diagram showing how the various UNC modifications interact to form Project Nexus is available here: http://www.gasgovernance.co.uk/sites/default/files/Nexus%20Modification%20interactions%20v2.0_0.pdf
Alternative Sources of Gas | This is an early-planning placeholder to focus some thinking about how the various future sources - e.g. shale, LNG, biomethane - might impact on the operation of GB's gas networks. | UNC iGT UNC | tbc | http://www2.nationalgrid.com/UK/Industry-information/Future-of-Energy/Gas/
Gemini Rewrite | Gemini provides GB's gas nominations, trades, energy balancing and entry/exit capacity processes and invoicing. The operating system behind the central Gemini system (operated by Xoserve on behalf of National Grid Gas) has been in use since 2005 and will require replacement or refreshing. | UNC | tbc | http://www.xoserve.com/index.php/our-systems/gemini/
UK General Election 2020 | Potential change of emphasis in Energy Policy leading to strengthening of Retail reform, acceleration of alternative sources of energy, penetration of electric vehicles etc | ALL | tbc
Brexit | UK exit from the EU is not currently expected to have a significant impact on GB Codes. Working assumption for the industry is that GB will continue to access the Single Energy Market, meaning that existing interconnection point arrangements will remain. In the near term, GB is legally obliged to comply with EU Regulations and subsequent Codes and work to adapt GB Codes continues. | ALL | Awaiting clear direction from central government via BEIS and Ofgem. | tbc
Smart Meter Roll-out complete | As roll-out of Smart meters approaches completion, the availability of reliable and frequent data items should permit the industry to improve many processes, such as Settlement, Forecasting, Balancing and capacity management | ALL | Ofgem are leading work under the "Future Energy Insights" banner that should inform direction on these matters. | https://www.ofgem.gov.uk/publications-and-updates/ofgem-s-future-insights-series-overview-paper
Gas Settlement Evolution | Currently a placeholder for a piece of work that is only just starting - essentially to think about how Settlement could be further improved. | UNC iGT UNC | Initial discussions are taking place at the Change Overview Board | http://www.gasgovernance.co.uk/COB

## Horizon (Elec)
Horizon Scanning
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation. Key (I) - Industry impact (L) Legislative impact (R) Regulatory impact
Lead Code Admin is ELEXON, Contact 020 7090 7755
Headlines - (18/08/16) DCC Go-Live, previously expected to be delivered in Summar 2016, has been extended to 30 September 2016
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
DCC Go-Live
(L) (High)
EU REform
(R) (High)
UK membership in the EU
(L) (Medium)
CMA
(R) (High)
UK General Election (2020)(L) (Medium)
Faster switching programme published
(I) (Medium)
Faster Switching and Centralised Registration
(I) (High)
Pan-EU harmonisation complete
(I) (Medium)

## Horizon (Gas)
Horizon Scanning
Horizon scanning provides provides a high level snap shot of the key legislative and regulatory changes expected to impact the industry. The changes are represented in terms of impact, certainty and anticipated implementation. Key (I) - Industry impact (L) Legislative impact (R) Regulatory impact
Lead Code Admin is ELEXON, Contact 020 7090 7755
Headlines - (18/08/16) DCC Go-Live, previously expected to be delivered in Summar 2016, has been extended to 30 September 2016
1 -2 years
2- 5 years
5 years +
Firm deliverables
Deliverables in definitition
Deliverables undefined
Policy undefined
Ones to watch
RAASP
(I) (High)
EU CAM (Am & Inc)
(R) (Medium)
NEXUS
(I) (High)
Gemini Rewrite
(I) (High)
EU Tariff Code
(R) (High)
Alternative Sources of Gas
(I) (Low)
FGO Ph2 Imp. (Q2 17)
(I) (Medium)
Gas Settlement Evolution
(R) (High)
Priority Svs Register
(R) (Medium)
NEXUS Ph2
(I) (High)

## 1. Cross-Industry
Workstream 1. Cross-industry change
Lead Code Admin is xxxx, contact 0xxx
Headlines
Code | Area | Mod Ref | Title | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary
ALL | DCC Go-live | n/a | None Required | ALL-n/a | C | n/a | E | tbc | E | tbc | n/a | n/a | Pending Implementation | On Track
UNC | DCC Go-live | n/a | None Required | UNC-n/a | C | n/a | E | tbc | E | tbc | n/a | n/a | Pending Implementation | On Track
BSC | DCC Go-live | n/a | None Required | BSC-n/a | C | n/a | E | tbc | E | tbc | n/a | n/a | Pending Implementation | On Track
ALL | Priority Services Register | n/a | None Required | ALL-n/a | C | n/a | E | tbc | E | tbc | n/a | n/a | Pending Implementation | On Track
UNC | Priority Services Register | XXXX | None Required | UNC-XXXX | C |  | E |  | E |  |  |  |  | At Rick
BSC | Priority Services Register | XXXX | None Required | BSC-XXXX | C |  | E |  | E |  |  |  |  | On Track
ALL | Faster Switching and Centralised Registration | XXXX | Modification Title | ALL-XXXX | C |  | C |  | C |  |  |  |  | On Hold
UNC | Faster Switching and Centralised Registration | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | At Rick
BSC | Faster Switching and Centralised Registration | XXXX | Modification Title | BSC-XXXX | C |  | E |  | C |  |  |  |  | On Track
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | C |  | C |  |  |  |  | On Hold
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | C |  | C |  |  |  |  | At Rick
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | E |  | C |  |  |  |  | On Track
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | C |  | C |  |  |  |  | On Hold
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | E |  | E |  |  |  |  | At Rick
ALL |  | XXXX | Modification Title | ALL-XXXX | C |  | E |  | E |  |  |  |  | On Track

## 5. UNC
Workstream 5. Code-Specific (UNC)
For more information, please visit the UNC website.
Lead Code Admin is Joint Office, contact 0121 288 2107
Headlines All UNC modifications dependent on Project Nexus are to be deferred to 01 June 2016, however Ofgem planning is ongoing and reference should be made to Project Nexus Steering Group documentation and the central plan (on Ofgem's website) New modifications relating to CAM changes for 2017 are expected at the October UNC Panel
Code | Area | Mod Ref | Title | Timeline Ref | S | Raised | S | Imp Decision | S | Imp Date | Assessment Duration | Implementation Duration | Progression State | RAG Status | Commentary
UNC | NEXUS | 432 | Project Nexus - Gas Demand Estimation, Allocation, Settlement and Reconciliation reform | UNC-432 | C | 2012-09-07 | C | 2014-02-21 | C | 2017-06-01 | 532 | 1196 | Systems Delivery | At Risk | For current progress, please refer to Project Nexus Steering Group papers on Ofgem's website.
UNC | NEXUS | 440 | Project Nexus - iGT Single Service Provision | UNC-440 | C | 2012-12-07 | C | 2015-01-14 | C | 2017-06-01 | 768 | 869 | Systems Delivery | At Risk | For current progress, please refer to Project Nexus Steering Group papers on Ofgem's website.
UNC | NEXUS | 473 | Project Nexus – Allocation of Unidentified Gas | UNC-473 | C | 2013-11-18 | C | 2015-04-09 | C | 2017-06-01 | 507 | 784 | Pending Implementation | On Track | Post-Nexus implementation
UNC | NEXUS | 583S | Requiring an Opening Meter Reading at same User Confirmation | UNC-583S | C | 2016-05-10 | C | 2016-08-15 | C | 2017-06-01 | 97 | 290 | Pending Implementation | On Track | Post-Nexus implementation
UNC | NEXUS | 586FT | Resolution of minor legal text drafting conflicts arising from UNC Modification 0432 | UNC-586FT | C | 2016-06-06 | C | 2016-06-16 | C | 2017-06-01 | 10 | 350 | Pending Implementation | On Track | Post-Nexus implementation
UNC | NEXUS | 589S | Inclusion of CSEP Supply Meter Points within NDM Sampling Arrangements | UNC-589S | C | 2016-06-27 | C | 2016-09-15 | C | 2017-06-01 | 80 | 259 | Pending Implementation | On Track | Post-Nexus implementation
UNC | RAASP | 434 | Project Nexus - Retrospective Adjustment | UNC-434 | C | 2012-09-24 | C | 2014-02-21 | E | 2018-06-01 | 515 | 1561 | Systems Delivery | On Hold | Currently on hold until implementation of the main Nexus system.
UNC | FGO Ph2 | 565 | Common Data Service Provider - General framework and obligations | UNC-565 | C | 2015-09-04 | E | 2017-01-27 | C | 2017-04-01 | 511 | 64 | Assessment | On Track | UNC modification and Data Services Contract scheduled for consultation in November 2016
UNC | EU CAM Incremental | 597 | Rules for the release of incremental capacity at Interconnection Points | UNC-597 | C | 2016-10-07 | E | 2017-03-30 | E | 2017-04-01 | 174 | 2 | New Proposal | On Track
UNC | EU CAM Amendment | 598 | Amendments to Capacity Allocations Mechanisms to comply with EU Capacity Regulations | UNC-598 | C | 2016-10-07 | E | 2017-03-30 | E | 2017-07-01 | 174 | 93 | New Proposal | On Track
UNC | EU Tariff Code | XXXX | tbc | UNC-XXXX | E | 2017-04-01 | E | 2018-12-31 | E | 2019-03-01 | 639 | 60 | Pre-Modification stage | On Track | Consideration as part of Transmission Charging Review at NTSCMF. See http://www.gasgovernance.co.uk/ntscmf
UNC | Miscellaneous Change | 516S | Information provision by large Customers to aid understanding of site characteristics | UNC-516S | C | 2014-09-16 | C | 2015-05-21 | C | 2017-06-01 | 247 | 742 | Pending Implementation | On Track | Nexus system dependent
UNC | Miscellaneous Change | 518S | Shipper Verification of meter and address details following system meter removals. | UNC-518S | C | 2014-10-31 | C | 2015-10-15 | C | 2017-06-01 | 349 | 595 | Pending Implementation | On Track | Nexus system dependent
UNC | Miscellaneous Change | 520A | Performance Assurance Reporting | UNC-520A | C | 2015-10-02 | C | 2016-04-25 | C | 2017-06-01 | 206 | 402 | Pending Implementation | On Track | Nexus system dependent
UNC | Miscellaneous Change | 523S | Supply Point Registration – Facilitation of ‘faster switching’ for Shared Supply Meter Points | UNC-523S | C | 2015-01-07 | C | 2015-07-16 | C | 2017-06-01 | 190 | 686 | Pending Implementation | On Track | Nexus system dependent
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | E |  |  |  |  | On Hold
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | E |  |  |  |  | At Rick
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | E |  |  |  |  | On Track
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | On Hold
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | At Rick
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | C |  |  |  |  | On Track
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | On Hold
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | At Rick
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | C |  |  |  |  | On Track
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | C |  | C |  |  |  |  | On Hold
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | E |  |  |  |  | At Rick
UNC |  | XXXX | Modification Title | UNC-XXXX | C |  | E |  | E |  |  |  |  | On Track