## Slide 1: PNISG Update
June 2015

## Slide 2: Xoserve’s UKLP Assessment Principles
Maintain current delivery plans where possible and appropriate e.g. don’t just push all dates out – use additional time to focus on areas that would benefit from it.
Re-plan where there was constraint earlier and where it will benefit the Programme and the industry. e.g. UAT schedule dictated by maintaining Market Trials length and approach.
Reinforce confidence in the solution e.g. visibility of testing progress.

## Slide 3: Assumptions
Assumption
1. L2/3 MT will be deferred.
2. The industry would prefer a single UKLP implementation a. Delivery approach options for US/Retro should be reassessed.
3. Go-Live will not be 1st October a. New go-live date is still TBC following engagement with the PNISG.
4 High level Xoserve programme strategy is to progress with current plans where possible. a. Where necessary and possible, certain activities will be lifted and shifted later (e.g. business change, transition) b. Significant risk/quality impact areas could be re-planned where useful (e.g. data, performance test)
5. Market Trials approach (sequencing of functionality, Xoserve support) is assumed to remain as-is with no new requirements being added except for longer duration (to be determined by Industry) or as a result of 2.a above
6. There will be impacts to Xoserve existing portfolio plan – e.g. evaluate change congestion through 2016.
7. Any future releases will not be delivered before 2017
8. The current UKL systems will need to operate for longer – sustainability/EOL impacts need to be reviewed covering performance, support, budgets

## Slide 4: Re-Plan Progress
All phases of the UKLP in scope; all activities completed.
Focussed re-planning activities concluded.
  Project and SME resource during this period caused impact on UAT progress; recovery plan now in flight.

## Slide 5: Design
What elements should hold the current plan? | What elements could benefit from being deferred
Close out in-flight Change Requests. Maintain the current scope – i.e. no other changes to come in now as a result of the change in dates. | Understand Retro and Unique Sites designs and, working with wider Programme, understand impact on their delivery/test plans.

## Slide 6: UAT
What elements should hold the current plan? | What elements could benefit from being deferred
Continue to drive for current targeted testing plans based on accurate forecasts. Continue to share weekly updates to improve confidence of progress being made. | UAT progress being impacted by re-planning exercise Once the current targeted test plans are completed, explore opportunities to complete additional testing to further enhance confidence in the quality of the solution

## Slide 7: Data
What elements should hold the current plan? | What elements could benefit from being deferred
Delta and IGT data cleansing should continue to operate at current pace. | Work with the industry to further clean data prior to (revised) load dates. Particularly iGT data. Re-plan to determine when the best time is to undertake MT load and DMTC2, such that defects can be more fully resolved in these cycles, improving confidence and associated functional tests. Consider new load requirements UAT MT

## Slide 8: Performance Test
What elements should hold the current plan? | What elements could benefit from being deferred
Current plan impacted by time constrained PT window | PT window constraint removed so re-plan being undertaken Re-plan: determine (a) when the infrastructure is built and pen tested, and (b) when the right point is to take functional tested application and (c) defect corrected data. The PT phase should then be at the appropriate point in the overall plan to provide confidence in the solution.

## Slide 9: CMS
What elements should hold the current plan? | What elements could benefit from being deferred
SIT phase of CMS is progressing at amber status and should continue as per plan and continue mitigating actions to complete as planned. | Need to re-plan Retro associated changes. Retro re-planning will follow the same timelines and principles as US and Retro delivery. Plan to do integrated testing with UAT environment

## Slide 10: Reporting
What elements should hold the current plan? | What elements could benefit from being deferred
Continue with the SIT of reports as per existing plan. Continue with DES build and test as per the existing plan. | Unique Site reporting and DES to be worked upon as per the timelines of US delivery plan

## Slide 11: Gemini
What elements should hold the current plan? | What elements could benefit from being deferred
On plan and should stay at current pace. Will be implemented with EU Phase 2 as planned in September 2015 with GCC code changes dormant in the system. | Need to monitor changes in Gemini Standalone UAT to be carried out in Gemini to ensure the functionality is not impacted due to introduction of parameters in code.

## Slide 12: Market Trials
What elements should hold the current plan? | What elements could benefit from being deferred
L1 completed on 15th May L2/L3/L4 deferred | Detailed work with Data and UAT streams to determine the point Xoserve will be able to release a fully UAT’d solution to the industry; Working with PwC to determine appropriate timeline for the industry to enter Market Trials Detailed planning on appropriate length of Market Trials for each functional area

## Slide 13: Business Change
What elements should hold the current plan? | What elements could benefit from being deferred
Continue current pace and plans. Change Impact Readiness continues to plan. Continue with training content development and review the timing of delivery. | US and Retro training content development to be included but at a later point

## Slide 14: Technical Transition
What elements should hold the current plan? | What elements could benefit from being deferred
Scope of the transition stream will remain the same Delivery of high level implementation plan complete but will be revised due to date change Medium & low level implementation plan on hold until revised date is known | Move implementation date and all IDRs to revised implementation date.

## Slide 15: Next Steps
Continue to share and evolve our thinking.
Revise delivery plans once PNISG has recommended revised plan (meeting 15th June).
Communicate revised plans, updated dashboards, risks (July).