## Sheet1
Unregistered Sites No Assets No Activity Project Timeline
Week Commencing
| Task | Approximate No of MPRNs | Date | Duration (business days) | time axis 2007-10-01 to 2008-10-27
| Total original pot | 47850
1 | High level analysis |  | 2007-10-15 | bar: 2007-10-01; 2008-01-14
2 | Database development |  | 2007-10-15 | bar: 2007-10-01
3 | D8ta centre LWIs |  | 2007-11-01 | bar: 2007-10-29
4 | Training |  | 2007-11-05 | bar: 2007-11-05
5 | Detailed project plan |  | 2007-11-05 | bar: 2007-10-01 to 2007-11-19
6 | Potential Duplicates |  | 2007-11-05 | 30 | bar: 2007-10-22 to 2007-11-12
7 | D8ta centre workshop |  | 2007-11-20
8 | End user letter strategy agreed |  | 2007-11-20
9 | D8tacentre Training |  | 2007-11-26
10 | End user letter 1 dispatched |  | 2007-12-03 | bar: 2007-12-03
11 | Phase 1 | 3000 | 2007-11-19 | 13.986
12 | USNANA MI distributed |  | 2007-12-03
13 | Unregistered workgroup |  | 2007-12-11
14 | Phase 2 | 4250 | 2007-12-10 | 19.8135
15 | USNANA MI distributed |  | 2008-01-11
16 | Phase 3 | 5400 | 2008-01-07 | 25.1748
17 | End user letter 2 commence |  | 2008-01-28 | bar: 2008-01-28
18 | USNANA MI distributed |  | 2008-02-12
19 | Phase 4 | 4250 | 2008-02-11 | 19.8135
20 | Unregistered workgroup |  | 2008-03-11
21 | USNANA MI distributed |  | 2008-03-12
22 | Phase 5 | 4250 | 2008-03-10 | 19.8135
23 | USNANA MI distributed |  | 2008-04-10
24 | Phase 6 | 4250 | 2008-04-07 | 19.8135
25 | USNANA MI distributed |  | 2008-05-13
26 | Phase 7 | 4250 | 2008-05-12 | 19.8135
27 | USNANA MI distributed |  | 2008-06-11
28 | Phase 8 | 4250 | 2008-06-09 | 19.8135
29 | USNANA MI distributed |  | 2008-07-10
30 | Phase 9 | 5450 | 2008-07-07 | 25.4079
31 | USNANA MI distributed |  | 2008-08-12
32 | Phase 9 | 4250 | 2008-08-11 | 19.8135
33 | USNANA MI distributed |  | 2008-09-10
34 | Phase 9 | 4250 | 2008-09-08 | 19.8135
35 | USNANA MI distributed |  | 2008-10-10
36 | Documentation and Presentation |  | 2008-10-21 | 5 | bar: 2008-10-20