## CMC_Summary
Totals by Budget Area (£,000's) | [9 empty] | Current Year Actual Spend By Customer Class
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Total Cost of Project | Previous Year Actuals | Current Year Actuals | Current Year Forecast | Future Financial Years Forecast | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 146.989 | 83.189 | 80.291 | 2.898 | 0 | 0 | 0 | 2.9 | 0 | 0 | 0
|  | Internal |  | 127.307 | 107.946 | 76.864 | 31.082 | 0 | 0
|  | Total |  | 274.296 | 191.135 | 157.155 | 33.98 | 0 | 0
RAG status: | [9 empty] | 0 | 0 | 0 | 0 | 0
Cost/forecast within approved value & budget
Cost/forecast over approved value, but total spend within budget
Total cost/forecast over budget | [9 empty] | 0 | 2.9 | 0 | 0 | 0
Note that project expenditure & budget values shown do not include margin
Internal costs are not deducted from budget (unless otherwise notified)
Details of Changes (£,000's) Negative red value indicate increase of costs
Project Line Level Changes | Sum of Change in Total Approved Value | Sum of Change in Estimated Total Cost of Project | Sum of Change in Previous Year Actuals | Sum of Change in Current Year Actuals | Sum of Change in Current Year Forecast | Sum of Change in Future Financial Years Forecast | Commentary
No changes from last month

## CMC_Current
[25 empty] | SORT FIELD 2 | [11 empty] | SORT FIELD 1
[13 empty] | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [12 empty] | Y | Y | Y | Y | Y | Y |  | Formulas do not delete |  |  | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Next Contractual Step | Next Step Date | Expenditure Type | Total Approved Value | Estimated Total Cost of Project | Previous Year Actuals | Current Year Actuals | Current Year Forecast | Future Financial Years Forecast | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Line Sequence Sort (THEN BY THIS) | PM | Line Check NOT FOR FILTER | Show Approved Money? | Show Reported Money? | Auto Assess of CMC Friendly? | Manual CMC Flag | ng-t | ng-d | sgn | wwu | ngn | Progress Sort (SORT BY THIS) | Matcher | Project Line | CBP Flag | High Level Process Stage | Next Contractual Step | Next Step Date | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Actuals | Change in Current Year Forecast | Change in Future Financial Years Forecast | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | External | 33.273 | 11.23 | 9.032 | 2.198 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 11.23 | 0 | 0 |  | CCR to be issued, project is in closure. | 53 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | Internal | 25.714 | 22.721 | 22.684 | 0.037 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 22.721 | 0 | 0 |  |  | 54 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | Total | 58.987 | 33.951 | 31.716 | 2.235 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 33.951 | 0 | 0 |  |  | 55 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | External | 9.7 | 9.655 | 8.955 | 0.7 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 9.655 | 0 | 0 | Sent | CCR has been issued, awaiting approval | 98 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 3995External | 3995 TRAS Tip-off Hotline Data Provision - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | Internal | 3.12 | 2.3 | 2.3 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.3 | 0 | 0 | Sent |  | 99 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 3995Internal | 3995 TRAS Tip-off Hotline Data Provision - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | Total | 12.82 | 11.955 | 11.255 | 0.7 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 11.955 | 0 | 0 | Sent |  | 100 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 3995Total | 3995 TRAS Tip-off Hotline Data Provision - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-09-15 | External | 15.016 | 2.016 | 2.016 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.016 | 0 | 0 |  | CCR to be issued, project is in closure. | 107 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | Y | SAME | SAME | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-09-15 | Internal | 57.5 | 43.1 | 22.7 | 20.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 43.1 | 0 | 0 |  |  | 108 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | Y | SAME | SAME | DIFF | 0 | 0 | 0 | -3.1 | 3.1 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-09-15 | Total | 72.516 | 45.116 | 24.716 | 20.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 45.116 | 0 | 0 |  |  | 109 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | Y | SAME | SAME | DIFF | 0 | 0 | 0 | -3.1 | 3.1 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | External | 89 | 60.288 | 60.288 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 60.288 | 0 | 0 |  | CCR approved, project now closed. | 143 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | Internal | 31.05 | 36.444 | 24.18 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 36.444 | 0 | 0 |  |  | 144 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | Total | 120.05 | 96.732 | 84.468 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 96.732 | 0 | 0 |  |  | 145 | Mark Pollard | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5 | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved | CCR approved, project now closed. | 161 | Lorraine Cave | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - External | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Internal | 9.923 | 3.381 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 3.381 | 0 | 0 | Approved |  | 162 | Lorraine Cave | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Internal | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Total | 9.923 | 3.381 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 3.381 | 0 | 0 | Approved |  | 163 | Lorraine Cave | TRUE | SHOW | SHOW | Y | Y | N | N | N | N | N | 5.5 | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Total | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 164 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | N | N | N | N | 0 | 4160External | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 165 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | N | N | N | N | 0 | 4160Internal | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 166 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | N | N | N | N | 0 | 4160Total | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | Zero costs being done as BAU | 188 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | Y | Y | Y | Y | 1 | 4242External | 4242 Monthly provision of national S&U statistics - External | Y | SAME | SAME | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 189 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | Y | Y | Y | Y | 1 | 4242Internal | 4242 Monthly provision of national S&U statistics - Internal | Y | SAME | SAME | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 190 | Lorraine Cave | TRUE | NO | NO | Y | Y | N | Y | Y | Y | Y | 1 | 4242Total | 4242 Monthly provision of national S&U statistics - Total | Y | SAME | SAME | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | Zero costs being done as BAU | 191 | Lorraine Cave | FALSE | SHOW | SHOW | Y | Y | N | Y | Y | Y | Y | 6 | 4248External | 4248 Quarterly smart metering reporting for HS&E and GDNs - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 192 | Lorraine Cave | FALSE | SHOW | SHOW | Y | Y | N | Y | Y | Y | Y | 6 | 4248Internal | 4248 Quarterly smart metering reporting for HS&E and GDNs - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 193 | Lorraine Cave | FALSE | SHOW | SHOW | Y | Y | N | Y | Y | Y | Y | 6 | 4248Total | 4248 Quarterly smart metering reporting for HS&E and GDNs - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 2
Note on BA3: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual