## Read Me First
PAF Risk Register
The PAF Risk Register sets out all operational and financial risk to gas settlement. The PAF and subsequently the PAF Risk Register is limited to energy and supply points within local distribution zones. It does not extend to energy transported through the National Transmission System and supply meter points connected to it.
The PAF Risk Register contains 15 risks and is currently baselined using theoretical a view of the risks identified from the initial work completed by Engage.
Further refinement of the PAF Risk Register will be completed following industry consultation and once further information is forthcoming.
Risks within the register are valid for the PAF year, 1 October 2017 to 30 September 2018 (2017/18).
Throughout the PAF year risks may remain in the same banding. Progress on those risks would still be made and captured within the Controls and Action of the risk.
This document will include within-period revisions made at PAC meetings from 1 October 2017 to 30 September 2018.
Additional information on how risk scores are calculated and on how to raise a risk, please see the Risk Register Approach document (link below).
https://www.gasgovernance.co.uk/sites/default/files/ggf/page/2017-10/PAC%20Document%203%20Risk%20Register%20Approach%20v2.0.pdf
Publication Date | 2017-10-13
Date Range | 2017-10-01 | to | 2018-09-30
Update History:
This version of the Risk Register reflects the contents of the latest approved Risk Register (13/10/2017) by the PAC.

## Risk Summary
PAC Risk | Risk Title | Current Throughput (1-5) | Current Probability (1-5) | Current Control (Not Effective, Partially Effective, Effective) | Current Gross Risk Score | Current Net Risk Score | Current Allocation (£ '000) | Current Reconciliation (£ '000) | Current Allocation (GWh) | Current Reconciliation (GWh) | Target Throughput (1-5) | Target Probability (1-5) | Target Control (Not Effective, Partially Effective, Effective) | Target Gross Risk Score | Target Net Risk Score | Associated Risk
PACR0001 | Theft of Gas | 5 | 5 | Not Effective (x1) | 25 | 25 | 42218 | 43046 | 2483 | 2532 | 5 | 4 | Partially Effective (x0.8) | 20 | 16 | -
PACR0002 | Use of the AQ Correction Process | 5 | 5 | Not Effective (x1) | 25 | 25 | 32218 | 32286 | 1895 | 1899 | 3 | 5 | Partially Effective (x0.8) | 15 | 12 | -
PACR0003 | Estimated reads used for daily metered sites (Product Classes 1 and 2) | 5 | 4 | Not Effective (x1) | 20 | 20 | 23555 | 47 | 1386 | 3 | 5 | 3 | Partially Effective (x0.8) | 15 | 12 | -
PACR0004 | Identified LDZ Offtake Measurement Errors | 5 | 3 | Partially Effective (x0.8) | 15 | 12 | 21152 | - | 1244 | - | 4 | 3 | Partially Effective (x0.8) | 12 | 9.6 | PACR0007
PACR0005 | Incorrect or missing asset data on the Supply Point Register | 4 | 4 | Not Effective (x1) | 16 | 16 | 13987 | 14073 | 823 | 828 | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8 | -
PACR0006 | Use of Winter Annual Ratio (WAR) for End User Category (EUC) 03-08 | 4 | 4 | Not Effective (x1) | 16 | 16 | 8908 | - | 524 | - | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8 | -
PACR0007 | Undetected LDZ Offtake Measurement Errors | 3 | 2 | Not Effective (x1) | 6 | 6 | 7051 | 7051 | 415 | 415 | 3 | 2 | Partially Effective (x0.8) | 6 | 4.8 | PACR0004
PACR0008 | Unregistered Sites | 2 | 4 | Not Effective (x1) | 8 | 8 | 2326 | - | 137 | - | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8 | -
PACR0009 | Shipperless Sites | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8 | 2481 | 621 | 146 | 37 | 2 | 2 | Partially Effective (x0.8) | 4 | 3.2 | -
PACR0010 | Meter readings fail validation | 2 | 4 | Not Effective (x1) | 8 | 8 | 1439 | - | 85 | - | 2 | 3 | Effective (x0.6) | 6 | 3.6 | -
PACR0011 | Late check reads on meters that derive a read | 2 | 4 | Not Effective (x1) | 8 | 8 | 1437 | 467 | 85 | 27 | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8 | -
PACR0012 | Meter read submission frequency for Product Class 4 meter points | 2 | 4 | Not Effective (x1) | 8 | 8 | 1350 | - | 79 | - | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8 | -
PACR0013 | Estimated reads at Change of Shipper | 1 | 3 | Not Effective (x1) | 3 | 3 | 408 | 410 | 24 | 24 | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6 | -
PACR0014 | Failure to obtain a meter reading within the settlement window | 1 | 3 | Not Effective (x1) | 3 | 3 | 79 | 79 | 5 | 5 | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6 | -
PACR0015 | Consistent approach to retrospective updates | 1 | 3 | Not Effective (x1) | 3 | 3 | - | 5 | - | 0 | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6 | -
[7 empty] | Cost at average SAP 1.7p for higher threshold (Oct 2012 – Nov 2016) |  |  |  | Target figures are for the PAF year 2017-18

## Risk Scores
Rating | Energy Throughput | Cost (£) | Likelihood
1 | 0 – 49 GWh | 850000 | Description – Remote Probability – <10% chance
2 | 50 – 249 GWH | 4250000 | Description – Less Likely Probability – >=10% and < 40% chance
3 | 250 – 499 GWh | 8500000 | Description – Equally unlikely as likely Probability – >=40% and < 60% chance
4 | 500 – 999 GWh | 17000000 | Description – More likely Probability – >=60% and < 90% chance
5 | > 1,000 GWh | 42,500,000 (no upper limit) | Description – Almost certain Probability – >=90% chance
Cost at average SAP 1.7p for higher threshold (Oct 2012 – Nov 2016)

## 001-Theft of Gas
Risk Number | PACR0001 | Risk Description / Title: | Theft of Gas
|  | There is a risk that… | The energy consumed at a Shipper's site will not be accounted for and be incorporated into unidentified gas
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 2483 | Allocation (£ '000) | 42218
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 2532 | Reconciliation (£ '000) | 43046
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 5 | Not Effective (x1) | 25 | 25 | Reviewed on 10/10/17
|  | Target | 5 | 4 | Partially Effective (x0.8) | 20 | 16
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Failure to identify consumers and customers who conduct theft of gas. |  | The sites and quantity of gas stolen cannot be identified, gas cannot be allocated and reconciled correctly |  | Detective: Shipper performance report to be produced in the future. Preventative: The TRAS framework. Above controls that have been put in place (obligations, TRAS etc.) have yet to be considered or reviewed by PAC, and until they are reviewed, an assumption that the controls are not effective has been made. | Action 0801: TRAS representative to attend the November PAC meeting to provide an update of activities. Investigate data provided from AUGE Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 002 - Use of the AQ Corrections
Risk Number | PACR0002 | Risk Description / Title: | Use of the AQ Correction Process
|  | There is a risk that… | Inaccurately calculated AQs will cause a misallocation of energy and the AQ correction process will not be used in a fair and consistent way.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 1895 | Allocation (£ '000) | 32218
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 1899 | Reconciliation (£ '000) | 32286
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 5 | Not Effective (x1) | 25 | 25 | Reviewed on 10/10/17
|  | Target | 3 | 5 | Partially Effective (x0.8) | 15 | 12
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Misunderstanding as well as misuse of how and when to use the AQ correction process. Also Erroneous reads, significant changes in consumption and sites with AQ incorrectly calculated of 1. The misuse and misunderstanding (not actioning) can lead to deflated AQs as a result, e.g. lowered erroneous consumption due to tampered reads means AQs should potentially be increased once theft is discovered. |  | The AQ allocated does not provide an accurate reflection of gas consumption; impacts allocation to the shipper and unidentified gas. The misallocation will not be corrected until Meter Point Reconciliation takes place. |  | To be Agreed. Reporting to monitor use of the corrections process and provide assurance that corrections are submitted in a fair and consistent manner. Production of shipper performance report 2A.8 and 2B.8 | Monitoring of Report 2A.8 to help show the use of the AQ correction process. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 003 - Estimated readings
Risk Number | PACR0003 | Risk Description / Title: | Estimated reads used for daily metered sites (Product Classes 1 and 2)
|  | There is a risk that… | Where estimated reads are used in Product Classes 1 and 2 after D+5, gas is allocated and reconciled incorrectly.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 1386 | Allocation (£ '000) | 23555
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 3 | Reconciliation (£ '000) | 47
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 4 | Not Effective (x1) | 20 | 20 | Reviewed on 10/10/17
|  | Target | 5 | 3 | Partially Effective (x0.8) | 15 | 12
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
The current cause of this risk is thought to be that the estimated read issue causes incorrect reconciliation at D+5. This risk should be considered as a risk to allocation, rather than a risk to reconciliation. |  | Estimated daily readings being used rather than actuals; allocation and reconciliation will be impacted. Use of estimated reads for these meters can affect unidentified gas volumes. Ultimately the meter point reconciliation corrects the position, though settlement remains inaccurate until then. |  | To be Agreed. Manage and monitor the number of estimates used for MPRNs in PC2. Transporters to follow process in TPD M7.2 which are reviewed to ensure they are proportionate and mitigate the settlement risk for MPRNs in PC1. Targets to be investigated to ensure check read obligations are met. Production of shipper performance report 2A.1 and 2B.1 | Xoserve currently working with Shippers, the DMSP (Daily Metered Service Provider) and the GTs to resolve sites with this issue Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 004 - LDZ Offtake measure error
Risk Number | PACR0004 | Risk Description / Title: | Identified LDZ Offtake Measurement Errors
|  | There is a risk that… | Offtake meters develop errors and produces inaccurate readings.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 1244 | Allocation (£ '000) | 21152
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | - | Reconciliation (£ '000) | -
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 5 | 3 | Partially Effective (x0.8) | 15 | 12 | Reviewed on 10/10/17
|  | Target | 4 | 3 | Partially Effective (x0.8) | 12 | 9.6
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | PACR0007 |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Inadequate management and monitoring of offtake meters. Meter inaccuracies and equipment faults. |  | Gas incorrectly allocated to meter points within the LDZ. No back-up or check meters in place. Also misallocation of NTS shrinkage leading to increased unidentified gas allocation |  | Manage and monitor LDZ Offtake meters to mitigate risk and implement a set of Transporter principles to provide assurance that the UNC Offtake arrangements are being followed. Performance report to be produced in the future. | 4 Transporters have published their quarterly Offtake Meter Performance reports outlining maintenance regime, meter error reports and copy of RRP report Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 005 - Incorrect asset data
Risk Number | PACR0005 | Risk Description / Title: | Incorrect or missing asset data on the Supply Point Register
|  | There is a risk that… | The billing attributes of a meter and gas consumption are incorrectly recorded or missing
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 823 | Allocation (£ '000) | 13987
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 828 | Reconciliation (£ '000) | 14073
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 4 | 4 | Not Effective (x1) | 16 | 16 | Reviewed on 10/10/17
|  | Target | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8
|  | Inherent | 5 | 5 | Not Effective (x1) | 25 | 25
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Insufficient validation and/or assurance of information provided by Shippers (ultimately provided by Suppliers and MAMs) |  | Meter reads failing validation resulting in delays and/or missing reconciliation. For Class 1 & 2 (DM) the impact is at the point of allocation and persists in reconciliation unless spotted and corrected. For Class 3 & 4, allocation will be correct but the asset error will cause incorrect (or missing) reconciliation. |  | To be Agreed. A principle of good behaviour to be introduced where Shippers are measured for updating incorrect asset data. Production of Shipper performance report for the following: 2A.9, 2B.9, 2A.2, 2B.2, 2A.3, 2A.3. PAC to investigate, attaining MDD validation data and information from Electralink. | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 006 - Site WAR for EUC 3-8
Risk Number | PACR0006 | Risk Description / Title: | Use of Winter Annual Ratio (WAR) for End User Category (EUC) 03-08
|  | There is a risk that… | Accurate daily settlement of meter points that do not have a site specific WAR; it will not reflect accurate consumption.
Date | 2017-09-25 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 524 | Allocation (£ '000) | 8908
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | - | Reconciliation (£ '000) | -
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 4 | 4 | Not Effective (x1) | 16 | 16 | Reviewed on 10/10/17
|  | Target | 4 | 4 | Partially Effective (x0.8) | 16 | 12.8
|  | Inherent | 4 | 4 | Not Effective (x1) | 16 | 16
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Lack of meter read history means the WAR has not been populated or an estimated profile has been applied. |  | Allocated energy is not reflective of accurate consumption if timing for WAR bands are missed and thus daily allocations could be impacted and incorrect AQ values derived. However, reconciliation might be impacted as it might put energy into the wrong times of year. |  | To be Agreed: Shippers to manage and monitor, on a monthly basis, the percentage of their MPRNs with a site specific WAR. Production of shipper performance report 2A.5 and 2B.5 | Xoserve currently investigating what the take up of WAR bands is. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 007 - Undetected LDZ errors
Risk Number | PACR0007 | Risk Description / Title: | Undetected LDZ Offtake Measurement Errors
|  | There is a risk that… | LDZ offtake meters develop an error and remains undetected, which causes the readings to be inaccurate.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 415 | Allocation (£ '000) | 7051
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 415 | Reconciliation (£ '000) | 7051
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 3 | 2 | Not Effective (x1) | 6 | 6 | Reviewed on 10/10/17
|  | Target | 3 | 2 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 4 | 4 | Not Effective (x1) | 16 | 16
Associated Risk | PACR0004 |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Offtake errors from LDZ's are occurring but are not being identified and corrected. Inadequate management and monitoring of LDZ offtake meters. Also there are no back-up or check meters in place. Meter inaccuracies and equipment faults remain undetected until reconciliation takes place |  | The incorrect LDZ offtake measurements leads to gas being wrongly allocated. Misallocation of NTS shrinkage leading to increased Unidentified Gas allocation. |  | To be agreed: Transporters manage and monitor LDZ offtake meters in mitigating risk. Frequent auditing and investigation into LDZ offtake measurement errors. Use the Transporter performance to provide industry assurance that UNC Offtake Arrangements are met. Performance report to be produced in the future | 4 Transporters have published their quarterly Offtake Meter Performance reports outlining maintenance regime, meter error reports and copy of RRP report. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 008 - Unregistered Sites
Risk Number | PACR0008 | Risk Description / Title: | Unregistered Sites
|  | There is a risk that… | An unregistered meter begins consuming gas and adversely impacts the accuracy to Settlement
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 137 | Allocation (£ '000) | 2326
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | - | Reconciliation (£ '000) | -
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Reviewed on 10/10/17
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 3 | 4 | Not Effective (x1) | 12 | 12
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Following a new connection, meters are fitted and gas is allowed to flow without a valid supply contract being in place (where they have an MPRN) Also incorrectly identifying customer owned meters as primary meters. |  | Shipper fails to register a site. The consumption at those sites is not measured and falls in to unidentified gas. |  | To be Agreed. Manage and monitor the performance and ensure that the intentions of UNC MOD 410A are achieved. | PAC to obtain reports around unregistered sites for PAC consideration PAC to ensure there is a clear demarcation between themselves and the Shipperless and Unregistered Sites working group. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 009 - Shipperless Sites
Risk Number | PACR0009 | Risk Description / Title: | Shipperless Sites
|  | There is a risk that… | The accuracy of settlement where a Shipperless site is either still consuming gas, or begins to consume at a future date without the Supply Point being reregistered.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 146 | Allocation (£ '000) | 2481
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 37 | Reconciliation (£ '000) | 621
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8 | Reviewed on 10/10/17
|  | Target | 2 | 2 | Partially Effective (x0.8) | 4 | 3.2
|  | Inherent | 2 | 3 | Not Effective (x1) | 6 | 6
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers are withdrawing from sites that still have meters attached. The site then starts and/or continues to consume gas |  | The gas consumed is not measured and falls into unidentified gas. This also impacts accuracy of settlement |  | To be Agreed. Shippers to manage and monitor that UNC MODs 0424 and 0425 are met. MOD 0469S details Transporter performance. Also monitoring Shippers follow the correct withdrawal process and Transporters to ensure that GSR visits are completed on time. Monitor site re-registrations to ensure energy allocation is corrected. Production of shipper performance report | PAC members to understand issues in the performance reports, should there be any once reports are received. PAC to ensure there is a clear demarcation between themselves and the Shipperless and Unregistered Sites working group. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 010 - Readings fail validation
Risk Number | PACR0010 | Risk Description / Title: | Meter readings fail validation
|  | There is a risk that… | Meter readings are submitted and fail validation, and subsequent reads fail validation; the AQ will become less accurate impacting the timeliness of reconciliation.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 85 | Allocation (£ '000) | 1439
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | - | Reconciliation (£ '000) | -
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Reviewed on 10/10/17
|  | Target | 2 | 3 | Effective (x0.6) | 6 | 3.6
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers are not managing the validation errors identified and therefore not remedying the issue. Also causes for rejected reads not investigated which reflects in inaccurate consumption. |  | Because of a poor and/or diminishing meter reading history, reconciliation will not be possible and the derived AQ is more likely to be inaccurate. |  | To be agreed: Manage and monitor the use of data set tolerance readings and focus on where there are persistent read fail validations. Production of shipper performance report 2A.6, 2B.6. Monitor number of failed reads per shipper (this is dependent on what above shipper performance reports cover). | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 011 - Late Check Reads
Risk Number | PACR0011 | Risk Description / Title: | Late check reads on meters that derive a read
|  | There is a risk that… | Where check reads are not completed, there is a risk that meters are under or over reading for an extended period of time which will impact allocation accuracy
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 85 | Allocation (£ '000) | 1437
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 27 | Reconciliation (£ '000) | 467
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Reviewed on 10/10/17
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers failing to provide timely check reads and providing late reads. Shippers not checking converters at the same time as the main meters. |  | Late check readings impact accurate allocation and extend drift periods. Derived readings cannot be verified as being accurate leading to potential consumption inaccuracies. |  | To be agreed: Ensure obligation for shippers to check converters at the same time as the main meter is met. Production of shipper performance report 2A.1, 2B.1 | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 012 - Meter read submission PC4
Risk Number | PACR0012 | Risk Description / Title: | Meter read submission frequency for Product Class 4 meter points
|  | There is a risk that… | The frequency of submission of meter readings for Product Class 4 meter points could adversely impact the accuracy of the derived AQ and consumption
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 79 | Allocation (£ '000) | 1350
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | - | Reconciliation (£ '000) | -
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 2 | 4 | Not Effective (x1) | 8 | 8 | Reviewed on 10/10/17
|  | Target | 2 | 3 | Partially Effective (x0.8) | 6 | 4.8
|  | Inherent | 2 | 4 | Not Effective (x1) | 8 | 8
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Shippers submitting meter readings infrequently |  | Timing differences in submission will create a risk of misallocation among shippers. The AQ will not be recalculated frequently from a good meter reading history leading to potential inaccuracies. |  | Obligations recently introduced following CMA order (annual read submission obligation and monthly read submission for smart). Manage and monitor frequency of read submissions. Production of shipper performance report 2A.5, 2B.5 Individual meter point reconciliation should correct this miscalculation. | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 013 - Est. Reads Change Shipper
Risk Number | PACR0013 | Risk Description / Title: | Estimated reads at Change of Shipper
|  | There is a risk that… | Estimated readings provided by the Transporter are used and not replaced with an actual reading are inaccurate and will create incorrect periods of reconciliation.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 24 | Allocation (£ '000) | 408
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 24 | Reconciliation (£ '000) | 410
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Reviewed on 10/10/17
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 3 | 3 | Not Effective (x1) | 9 | 9
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
No reading obtained within the change of transfer window and/or rejected by initial validation due to incorrect AQ. Shippers do not have an actual reading to replace the estimate following transfer |  | Estimated opening meter read used during the reconciliation between the two shippers will be inaccurate. This will result in an incorrect final allocation for the transferring parties; accuracy of the whole market will not be accurate. This can be described as a temporary UIG and can be updated once reads are submitted |  | UNC, SPAA and supply license rules and regulations. SARs process to correct change of supplier reads. Production of shipper performance report 2A.4, 2B.4 | PAC to review Shipper agreed reads process to see if there are any issues. Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/17

## 014 - Failure to obtain read
Risk Number | PACR0014 | Risk Description / Title: | Failure to obtain a meter reading within the settlement window
|  | There is a risk that… | Some meter points do not obtain a read within the settlement window and reconciliation periods will crystallise not reflecting true consumption
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | 5 | Allocation (£ '000) | 79
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 5 | Reconciliation (£ '000) | 79
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Reviewed on 10/10/17
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 2 | 3 | Not Effective (x1) | 6 | 6
Associated Risk | n/a |  |  |  | Category |  | Allocation & Settlement
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Meter readings are not being obtained within the settlements window. Also read validation errors not being corrected by shippers. |  | Incorrect consumption being crystallised due to lack of meter reads |  | To be agreed: Principle of logic checks to approve consumption adjustments. Production of shipper performance report 2A.7, 2B.7 | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/2017

## 015 - Retrospective updates
Risk Number | PACR0015 | Risk Description / Title: | Consistent approach to retrospective updates
|  | There is a risk that… | The approach taken by shippers to retrospective updates increases the risk of inaccurate reconciliation periods.
Date | 2017-07-11 | Raised by | Performance Assurance Committee (PAC) | Risk Energy and Financial Estimate | Allocation (GWh) | - | Allocation (£ '000) | -
Risk Status (Active / Inactive) | Active |  |  |  | Reconciliation (GWh) | 0 | Reconciliation (£ '000) | 5
Risk Scores |  |  | Throughput | Probability | Control | Gross Risk | Net Risk | Risk Review Date
|  | Current | 1 | 3 | Not Effective (x1) | 3 | 3 | Reviewed on 10/10/17
|  | Target | 1 | 2 | Partially Effective (x0.8) | 2 | 1.6
|  | Inherent | 1 | 3 | Not Effective (x1) | 3 | 3
Associated Risk | n/a |  |  |  | Category |  | Allocation
Potential Causes of the risk |  | Potential Consequences of the Risk Event Occurring (e.g.. Because of …) |  | Controls | Actions |  | Owner and Target Completion Date
Commercial drivers and incentives on shippers do not promote a fair and balanced approach to use retrospective updates. |  | An unfair and unbalanced approach to retrospective updates, allocation could be skewed and distorted overall towards greater unidentified gas. |  | To be agreed: Monitoring the use of the retrospective updates process, by measuring update requests. Full set of retrospective adjustment update requirements not fully delivered at initial Nexus implementation, work is being done to refine requirements and agree future delivery Shipper performance report to be produced in the future. | Consultation to commence 13/10/17 |  | PAC review meeting on 10/10/2017