## Slide 1: Release 3 Scope Selection and Plans
10/01/2018

## Slide 2: Summary
UK Link Release 3 has been initialised with a target implementation window of November 2018
We will share today an indicative delivery plan, a scoping and funding approval plan, and Xoserve’s approach to prioritisation
What we’re seeking from ChMC today:
Direction on scope to be considered for R3: ChMC members to provide direction on scope items they would like included
Approval of the approach to gain scope approval: ChCM members to approve approach to engage SDG to review scope in detail and return to ChMC for ratification
Acceptance of the funding plan: ChMC accept the plan required to achieve funding and also the assumed commencement and target implementation date
Direction on the prioritisation method: ChMC members to provide direction on the prioritisation method Xoserve have proposed and approval to engage SDG to review method in detail and return to ChMC for ratification

## Slide 3: Release 3 High Level Delivery timelines
2018 |  |  |  |  |  |  |  |  |  |  | 
January | February | March | April | May | June | July | August | September | October | November | December
Scope
Prioritisation
Scope
Defined
Funding
Design
Build
Imp.
PIS
Scoping
Initiation
Delivery
Realisation
Baselined
Scope
Locked
Scope
Analysis, IA & HL Design
System Test
SIT
UAT
Market Trials

## Slide 4: Release 3 Scoping and Funding Approach
Following previous release practice, an Initiation phase (Scope & Design) followed by Delivery phase (Build, Test & Implement) is proposed for R3.
The Plan for achieving Scoping and Initiation inc. Design is described below:
# | Decision Step | Reviewer/Approver | Timescales
1 | Scope Prioritisation | (ChMC/delegated authority) | January 2018
2 | Scope Endorsement | (ChMC) | End January 2018
3 | EQR Approval (Design funding) | (ChMC) | February 2018
4 | BER Approval (Full delivery funding) | (ChMC) | March 2018
5 | Design Commencement | (Xoserve R3 team) | Mid March 2018

## Slide 5
Proposed Release 3 Scope & Funding Plan
The Plan for achieving steps of Scoping and Initiation is described below for this group’s review:

## Slide 6: Scope Considerations
Release 3 Release change item prioritisation proposal includes previously requested high priority items such as Cadent Billing, NTS tariff Billing Rate
RAASP has been excluded from Release 3 following advice from this committee due to the ongoing industry discussions.
Initial examination of Meter Read Sequencing (XRN 3732) requires further clarification of requirements. It is also believed to have large congruence of ‘solution fit’ to RAASP functionality, therefore inclusion within R3 is not advised
Delivery capacity verification needs to be carried out to ensure the final proposed scope of a release can be accommodated within the planned delivery timeframe
Xoserve are also proposing service sustaining changes into release scope
Non-functional and potential market trials implications will be considered and reviewed with SDG when defining the scope of the release

## Slide 7: Release 3 Scope – initial view
Level-1
Level-2
Level-3
No customer impact, purely internal change
No impacts to customer interfaces, but impacts to customer business processes
Impacts to customer interfaces Inc. customer file formats*
Notes:
This classification is an early view only, with the expectation that scope, impacts and benefits will be fully ratified by SDG as per the planned activities described in slide 5.
Any change impacting an external file format is classified as ‘Level 3’ by default.
Delivery capacity verification needs to be carried out to ensure the proposed scope of a release can be accommodated within the planned delivery timeframe
Delivery Mechanism
Perceived Benefit
Low
Medium
High
4454 – DN Sales/ Cadent Billing
4273 – Introducing In –Home Display
4443 – File Format Change (Unique Sites)
4436 – Changes to K13 Records (SSMPs)
4534 – RGMA Validation Rules
4480 – CAP Recon charge
4484 – Restriction on SOQs
4421 – Daily LDZ UG to NG
4559 – Meter Asset Reporting
4431 – AQ corrections: Market Breaker
4458 – CSEP Variance
4375 – NTS Gemini Data Import
4477 – AIR Response File Change
4426 – IA on ‘Changes to Market Intelligence Report’
4432 – NTS Optional Tariff Rate
4503 – Late Meter Attach Resolution
4496 – IGT Address Amendments