## 3. Requires Sponsorship
XRN Ref | Change Title | Comments | Change Type | Origination Date | Previous UK Link CR Ref
4499 | CDN/CDR File record Occurence Change | propose to move to minor release 27/02 - will be closed if no sponsorshiped received by 7th March ChMC meeting | CR (internal) | 2017-07-11 | UKLP IADBI365
4451 | Treatment of values in the CDR | 27/02 - will be closed if no sponsorshiped received by 7th March ChMC meeting | CR (internal) | 2016-12-05 | UKLP IADBI277
4345 | File format changes to the CGI file | 27/02 - will be closed if no sponsorshiped received by 7th March ChMC meeting | CR (internal) | 2017-09-12 | UKLP IADBI379
3667 | Provision of Formula Year AQ | Sponsored / CP to be Submitted 27/02 - currently in R3, potential to de-scope if no sponsorship received | CR (internal) | 2015-02-06 | UKLP IADBI071
4526 | removal of UNC Section M7.3.7 during MOD432 development | 27/02 - will be closed if no sponsorshiped received by 7th March ChMC meeting | CR (internal) | 2016-02-10 | UKLP IADBI174
4421 | Addition of Daily LDZ unidenitified gas (UG) to National Grid Operational Services | 27/02 - will be closed if no sponsorshiped received by 7th March ChMC meeting | CR (internal) |  | UKLP162
New Change requiring sponsorship
4621 | Suspension of the Validation between Meter Index and Uncoverted Converter Index | 28/02 - added to request sponsorship A change was implemented during Project Nexus to amend the validations for meter reads/Corrected/uncorrected reads due to issues raised at the time, however was stated the validations should be assessed post implementation. | N/A
4622 | Incrementing Reads on Isolation Supply Meter Points | 28/02 - added to request sponsorship the issue was raised post implementation, request to re-raise to assess if change required | N/A