## Issue Tracking List
ISSUE TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Issue Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ISSUE NO. / TITLE | DATE CREATED | DESCRIPTION | ASSOCIATED ACTION | STATUS | WITHIN 0849R SCOPE? | COMPLETION DATE | Transmission and Distribution? | COMMENTS | OUTCOME (So what) | CLOSE
1a- Deblending | 2023-06-19 | Do we need to consider de-blending commercial framework as part of this workgroup? If not who will be looking at this and when? | Action 11 | Under Review | Potentially if required |  |  | Issue's list for commercial framework changes to support deblending created. Agree if these issues should be included in 0849R scope or kept separate. Distribution level- Hydeploy study to include outputs on connected consumers acceptability and requirements. (outputs early next year). Transmission level- FutureGrid/ H2 Acceptability study/ site specific assessments. Strategic and economic case for blending to be explored and approach outlined. Clarity on requirement for de-blending technology once safety case review is complete. | Assess the need for deblending following safety evidence submission for both GDN and NTS level, engage with HSE on this.
1b- User acceptability of a hydrogen blend | 2023-06-19 | There may be safety, operational or commerical impacts to end user acceptability when receiving a hydrogen blend. (Power Generation, CNG stations, Storage ect). For example CCGT’s operation can only burn up to 2-5% H2 blend. Beyond this they are not covered by OEM warranties. | Action 1 | Under Review | No (safety/ technical) |  |  | As above. Further work required on site specific assessments on costing and time constraints. OEM resource needs to be considered (could have bottleneck of assessment requests). Mitigation solutions may be necessary (i.e. de-blending) to manage this. This could be reliant on volume percent of blended gas being received and compostition variance. | Assess learnings from Hydeploy and NTS acceptability study as well as similar studies completed in EU on industrial acceptability of hydrogen. Consider learnings from site specific assessments completed to review costings and timing for any required modifications. Also consider the need for deblending following HSE review of safety evidence.
1c- Blend variability | 2023-07-20 | Blending strategic role as reserve offtaker and strategic enabler (electrolytic only), blend % variability will be likely. How will this impact Industrial end users and what mitigation techniques will be required? | Action 1 | Under Review | No (safety / technical) |  |  | Progressive Energy blend acceptability study has completed initial review for this for Transmission direct connects, Hydeploy project for Distribution. However overarching approach for blending as reserve offtaker- requires clarification from Government as to whether a variable or fixed blended gas quality based approach will be implemented, this has been enquired within consultation. | Site specific assessments will need to be completed to explore impacts of variable blend on end user equipment and operability. These assessments will require resource from OEM, risk of bottleneck if all end users request assessments in similar timeframe.
2- CCUS | 2023-06-19 | DESNZ want CCUS networks to be fully utilised, with possibility of penalties if they are not. |  | Closed in 849R | No (commercial) |  |  | Issue where CCUS projects connected to network may receive a blend, which will impact maximum production optimisation. | To be considered as part of industrial end user impacts by HSE- May lead to requirement for de-blending equipment
3- Connection Agreements | 2023-06-19 | Industrial users that have connection agreements in place have to warrant that site is safe for offtake of gas, this is specifically around Methane, therefore adaptation will be required, this will need to be reviewed by HSE? | Action 4 | Closed in 849R | No (HSE) |  |  | NExA points to standard offtake requirements in code | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
4- Control of Major Accidents Hazard (COMAH) | 2023-06-19 | Timeline for HSE to review Control of major accident hazards (COMAH) safety approvals would need to be considered within roll out plan |  | Closed in 849R | Consideration for Implementation timeline. Within HSE safety case scope. |  |  | This point impacts timescales for the roll out of blending but does not need to be considered within the scope for 849R | This will sit under the HSE Safety case remit and therefore does not require further review under 0849R
5a) GCOTER | 2023-06-19 | Other aspects of GCOTER include gas temperature, pressure correction and compressibility factor. Has this been covered adequately within Hydeploy programme, does it need to be further considered within 849R? | Action 2 | Closed in 849R | Hydeploy report. HSE safety case scope. |  |  | This will be considered within the HSE safety case review, report covering this has been covered within Hydeploy project, Cadent to share once complete. Also work completed by Dave Lander looks at this, Dave has offered to present this data to the group in September. | Outputs from Dave Lander are explained below. Hydeploy report is yet to be published.
5b) GCOTER | 2023-10-04 | GCOTER includes gas temperature, pressure correction and compressibility factor.Check whether this will need to be reviewed and changed. |  | Closed in 849R | No- IGEM |  |  | Changing fixed factor in GCOTER isn't likely to be cost effective. However for large, high-pressure installations relevant upgrades to gas chromatograph may be required to account for H2. Solutions required and sufficient time to upgrade. | To be reviewed via IGEM. Time and cost considerations for updating chromatograph where necessary to factor into blending implementation roadmap.
5c) GCOTER | 2023-10-04 | GCOTER includes gas temperature, pressure correction and compressibility factor.Check whether this will need to be reviewed and changed. |  | Closed in 849R | No- IGEM |  |  | Intermediate-pressure installations are less straightforward, therefore guidance in IGEM/GM/5 for volume conversion devices needs updating | Volume conversion devices to be reviewed by IGEM, again time and cost considerations for developing and isntalling needs to be factored into blending implementation roadmap.
5d) GCOTER | 2024-02-28 | Will climate change have an impact on the temperature factor included in GCOTER? |  | Closed in 849R | Future Billing Methodology |  |  | Increase in UK temperatures are likely to lead to a small net under-billing to a similar net over-billing over the next 30-40 years. GB level of granularity wa assessed – more work required for localised impacts. Will future consumer billing arrangements (such as Future Billing Methodology) obviate the need for consumer billing based on a single, fixed, volume conversion factor? • If yes, then no need to consider amendment of fixed factor • If no, then may need to consider amendment | Monitor progress with Real Time Settlement Methodology and whether this will obviate the need for consumer billing based on a single, fixed , volume conversion. If no, this may require further consideration as a separate piece of work.
6)- Limitation to blend volume percentages | 2023-06-19 | Consideration as to how lower limits of blend volume percentage for initial injections coud be outlined? Through code or agreed within Connection Agreements? |  | Created | HSE |  |  | This will be considered within the HSE safety case review and a steer provided as to whether this sits within code or elsewhere. | Engage with HSE on this topic once safety case evidence is submitted and review UNC accordingly based on feedback.
7)- Site Safety Case/ Data Sheets | 2023-07-18 | Direct connect sites safety case/ data sheets for NExA's may refer to Methane, therefore these will need to be reviewed to include a blended gas. | Action 4 | Closed in 849R | No- HSE (safety/ technical) |  |  | This will require review under safety case workstream.
8)- Delivery Facility Operators | 2023-06-19 | Review who DFO’s would be for injecting H2 blend, particularly for entry points with multiple connections. |  | Resolved | Outlined in Functional Specifications Project. |  |  | F.Specs report outlines this, to be reviewed in August review group. National Gas also completing project looking at blend connection designs. | F.specs project considering Transmission also in flight. Review once outputs are finalised.
Direct Modification Requirement
9a)- Interconnectors | 2023-06-19 | EU blending strategy could differ from UK, therefore, require solution for H2 blend volumes across IP’s in order to continue trading |  | Monitor / under review | Yes |  |  | NG are scoping EU-UK Strategy paper to review the certainties and unknowns for EU strategy and where alignments and interjurisdictional coordination with UK strategy is required. | Reccomendations to be explored and developed within scope of this work. Any UNC/EID impacts to be reviewed.
9b)- European Interconnector Document | 2023-07-18 | Any changes made to UNC may impact EID, or may require changes in EID. | Action 6 | In-progress | Yes |  |  | Depending on EU blend strategy and decision on capacity allocation method there may be changes required to EID Section B-Capacity, C-Nominations and D-Allocation to reflect approach for capacity allocation across the networks. | NG to engage with interconnected TSO's and arrange internal workgroup to review the processes and relevant changes required to UNC. Then engage with relevant stakeholders to agree on provisions.
10)- Reverse Compression | 2023-06-19 | Reverse compression derogation 808 , concerns over impacts to a blended gas being transported. |  | Monitor | Yes potentially |  | Both | Derogation currently in discussion looking at Reverse compression between Tx and Dx networks which could impact blend cap management. This will need to be monitored and considered if implemented.
11)- Buffer Service | 2023-06-19 | Buffer service ( linepack) provided by TSO’s, could this be outlined in code/ agreed within connection agreement as a service to support maximisation of H2 production? |  | Resolved | Yes |  |  | This would impact blend cap, and would be restricted making it difficult to offer as a service.
12a)- Changes to Existing NEA's to enable blending (Gas Quality Data Provision) | 2023-06-19 | More transparency required on changes to existing NEA’s for Distribution Networks as current framework requires no MOD or industry consultation for this. Information such as agreed maximum blend volume to be shared with those impacted further downstream. | Action 10 | Created | Yes - UNC |  | DN's | Whats important to end users here, what information could be useful and what is appropriate to share? Review work currently being completed on Gas Quality. Blend points likely to be new NEA's. Refer to actions 9 an 10. | Further work required to review Gas Quality Data Provision and how this could be managed before UNC changes agreed (likely to impact-TPD Section I- ENTRY REQUIREMENTS) This work also links to a Capacity Allocation Mechanism for managing blends as geographical impacts (including downstream connections) could be reviewed to shape allocation of capacity. Alternatively additional pre-connection assessments/ network coordination provisions could be added.
12b)- New NEA's for blending (Gas Quality Data Provision) | 2023-06-19 | Currently no MOD or industry consultation required for new NEA's (Tx & Dx). More transparency required to include agreed maximum blend percentages and impacts on parties downstream. | Action 9 & 10 | Created | Yes - UNC |  | Both | Considerations for this have been explored in Future Billing Methodology. Also review any considerations within RIIO3 team. Refer to Actions 9 and 10. | Further work required to review Gas Quality Data Provision and how this could be managed before UNC changes agreed. This work also links to a Capacity Allocation Mechanism for managing blends as geographical impacts (including downstream connections) could be reviewed to shape allocation of capacity. (Potential impacts to TPD Section I- ENTRY REQUIREMENTS)
12c)- Hydrogen content in combined entry/exit agreements (IEA/CSEP) | 2023-09-28 | NTS standard storage connection agreement includes reference to 0.1% H2 content within Annex C - GAS ENTRY & QUALITY PROVISIONS. Interconnector Agreements are more bespoke bi-lateral agreements, however likely also include specific H2 content with entry provisions which will need to be changed to implement blending. | Action 3c | Created | Yes |  |  |  | These willl need to be reviewed and agreed through enabling modification process before hydrogen content can be updated accordingly. IEA's may need the involvement of different parliamentary authorities during modification process.
13)- Blend Cap Management | 2023-06-19 | Existing constraint management tools are mainly for turning down flows, do we require additional tools for when flows need to be increased to manage H2 blending? | Action 7a & 7b | Under Review | Yes |  | Both | Non-fault curtailement mechanism captured within phase 2 plan.
14)- Command and Control | 2023-06-19 | Technical solution required within NEA to ensure maximum H2 blend rates are not exceeded. Require a tool to guarantee a change in flow before emergency phase is reached. Could onsite storage be solution for this? | Action 7b | Under Review | Yes |  | Both | Agree, this needs to be called out in NEA. Transportation Flow Advice (TFA) can be issued to reduce or stop flows where gas quality parameters are at risk prior to injection, however blend will also be reliant on sufficient NG flows to blend. | Potential ammendments required in TPD Section I- ENTRY REQUIREMENTS, Control parametres to be set out in Network Entry Agreement (maximum blend % / CV target)
15)- H2 energy to volume difference | 2023-08-02 | Hydrogen has a lower energy to volume ratio than natural gas. |  | Monitor | Future Consideration- to be monitored |  | Both | For initial H2 blend injections this difference will not be materialistic, therefore a H2 blend can be traded as energy at the NBP, however if H2 blend injections are to increase in the future this difference in energy vs volume will need to be considered and reviewed. | Continue to monitor as blends increase, potential changes to TPD Scetion D and E may be necessary in the future.
16) - Offtake Profile Notices for H2 blend | 2023-09-28 | For blending it may be necessary to move to forecast in energy rather than volume, which could lead to required changes within OAD if new processes are relevant. |  | Resolved | Yes |  | Both | Initial discussions on potential solution options are being explored with NCC any impacts to OAD to then be reviewed and shared. (Likely ammendments to OAD Section I- NTS OPERATIONAL FLOWS and/or Section J- LDZ/LDZ OFFTAKES – PLANNING AND OPERATIONAL FLOWS) | No change- Continue providing OPN's in volumes by assuming the instantaneous CV at the offtake. Current OAD arrangements allows for tolerances with OPN and they are revised throughout the day to align better with changes in CV, therefore potential inaccuracy resulting from changes in the CV from the NTS wouldn’t be material enough to warrant the additional work that would be required for NG to provide GDNs with forecasts for it.
17) Free market appraoch with capacity protection (first come first serve) | 2023-09-29 | H2 producers will require protection when connecting to network to prevent later producers from connecting upstream and sterilising their blend capacity. |  | Under Review | Yes |  | Both | This may require additional provisions within gas transporter licence Condition 4B Connection Charging Methodology to provide blend capacity protection on a first come first serve basis and ammendment to Standard Special Condition D12 Requirement to offer terms for the provision of gas entry points to reject connections where protection is in place. | This will be subject to a decision on capacity allocation mechanism. Blend deliverable principles to be deveopled with Ofgem and workgroup to explore suitable capacity approach to be progressed early next year.
18a) - Free market approach with Capacity Allocation Mechanism (optimised approach) | 2023-09-28 | Development of a centrally orgainsed capacity allocation mechanism to manage blend capacity to create locational signals in a free market aproach. |  | Under Review | Yes |  | Both | Further work required to develop a suitable capacity allocation mechanism. (Likely ammendments to TPD Section B- SYSTEM USE and CAPACITY & Section Y - Charging Methodologies) if new blend capacity product and auction is created, along with Gemini system updates. | Once mechanism has been developed review where this will need to be incorporated into UNC.
18b) - Nominations | 2023-10-04 | Ability to raise Input nominations for hydrogen to blend may be necessary if a mechanism to optimise blend capacity is progressed but also if hydrogen is booked through existing capacity products as SO would need to know physical input of hydrogen into the network. (Transmission only) |  | Under Review | Yes |  | Transmission (if minimal change approach) | Nominations may be required to differentiate between hydrogen and natural gas physical inputs, therefore chnages to TPD Section C- Nominations | This ammendment only required for Transmission level blending in both a minimal change approach and optimised (capacity allocation mechanism)
18c) - Hydrogen blend capacity auction | 2023-10-04 | Where new H2 blend capacity product is created for capacity allocation mechanism- additional auction will need to be created for blend capacity product. |  | Under Review | Yes |  | Both | Hydrogen blend capacity auction to be added. Transmission (TPD Section Y Charging Methodologies A-I-2 Table 2.2.1) | To be reviewed following decsion on capacity allocation approach.
19) Net entry charge for commingling facility | 2023-10-04 | NTS Commingling facility defintion allows for net entry to be calculated for the purpose of taking NG off the network to commingle with other gas and re-inject as blended gas. Could this definition be expanded to cover LDZ commingling facility as well? |  | Under Review | Yes |  | Distribution | Potential change to (GT C1 & TPD Section E- Daily Quantities, Imbalances and Reconciliation NTS 1.10) to expand the definition or add in new definition to apply to LDZ Commingling facility as well. | Further work required to develop solution for LDZ net entry concept (whether this is an expansion of 'NTS Commingling Facility' or a separate concept). Currently no entry charge into LDZ so may require changes to Section B as well.
20) GS(M)R Hydrogen limits may vary between Distribution and Transmission | 2023-11-22 | Requirement to review how this could be managed and whether any impacts to UNC provisions or NEA's/ NExA's. |  | Created | Yes |  |  | How this will be managed from a regulatory point of view will need to be considered. (TPD Section J- Strandard Offtake Requirements) refers to GS(M)R. NExA's point to GS(M)R, if GS(M)R is varied between specific locations NExA's may need to be reviewed to ensure the correct GS(M)R limit is applied.
21) Slugging | 2023-11-22 | Is slugging being considered within the safety case review? |  | Under Review | Yes |  |  | Slugging and techniques to manage this is being considered at FutureGrid test facility. Blend testing for 2% 5% and 20% now complete, 100% to commence imminently, outputs due to be written up by Q2 this year.

## Actions Tracking List
ACTIONS TRACKING LIST
WORKGROUP | 0849R
PROJECT NAME | Commercial Framework Review to Enable Hydrogen Blending
Actions Tracker Owner | Megan Bray - megan.bray@nationalgas.co.uk
ACTION NO. / TITLE | DATE CREATED | DESCRIPTION | ASSIGNEE | STATUS | PRIORITY | RAISED BY | COMMENTS | OUTCOME (so what) | CLOSE
1- CCGT's | 2023-06-19 | Check CCGT’s are included in Progressive Energy study looking at Hydrogen Acceptability. | Megan Bray | Completed |  |  | All gas handling technology archetypes will be considered within the PE Accessibility Study, these have been agregated from a list of direct connected sites to the NTS and will cover CCGT equipment. Interviews will then be conducted with relevant industrial customers regarding each archetype and their compatibility with a Hydrogen blend of up to 20% including variability. | Megan and Julie Cox to discuss archetype and survey methodology for H2 acceptability study offline. The outputs of this work to be shared with industry upon completion and any issues identified to be considered for framework changes. | Yes
2- GCOTER | 2023-06-19 | GCOTER includes gas temperature, pressure correction and compressibility factor. Check this is adequately covered within Hydeploy (DN's). Confirm when report will be completed and share with group. | DN'S | Completed | IGEM/GM/5 |  | Report covering additional specifications such as gas temperature, pressure correction and compressibility factor is being completed within the Hydeploy programme and will be submitted to HSE as part of the safety case evidence. Report is still being developed, Cadent to share once complete. - Dave Lander has offered to present on findings from previous consumer billing report on this and update group. - Eric Fowler also raised enquiry with IGEM gas measurement committee- it was suggested for 5% blend in pressures upto 2bar effects would be immaterial, however this may need to be considered in higher pressures as well as effects of variability. | Domestic, small commercial, low-pressure installations • no change in fixed factor suggested Large commercial installations • probably no change in Schedule suggested Large, high-pressure installations • upgrade of gas chromatograph required to account for hydrogen in blend Intermediate-pressure installations are less straightforward • guidance in IGEM/GM/5 for volume conversion devices needs updating | Yes
2b- GCOTER | 2023-11-22 | Will climate change have an impact on the temperature factor included in GCOTER? Follow up with D.Lander to see if this needs to be a consideration. |  | Completed |  |  | Increase in UK temperatures are likely to lead to a small net under-billing to a similar net over-billing over the next 30-40 years. GB level of granularity wa assessed – more work required for localised impacts. Will future consumer billing arrangements (such as Future Billing Methodology) obviate the need for consumer billing based on a single, fixed, volume conversion factor? • If yes, then no need to consider amendment of fixed factor • If no, then may need to consider amendment | Monitor progress with Real Time Settlement Methodology and whether this will obviate the need for consumer billing based on a single, fixed , volume conversion. If no, this may require further consideration as a separate piece of work.
3a- Existing NExA gas specifications | 2023-06-19 | Check there are no direct gas specifications included in existing exit agreements. If 0.1% Hydrogen content is specifically referenced, this will need to be changed through appropriate method developed and agreed within this review group. | DN's Megan Bray | Completed |  |  | DN's and Transmssion currently checking NExA's for specific Hydrogen content reference. | National Gas, SGN, WWU and Cadent completed check and identified no direct H2 content reference. No change required
3b- Existing NExA (reference to GS(M)R) | 2023-06-19 | Alternatively existing NExA's may point to GS(M)R (likely to change to 20% H2 content) check if this is the case where specific H2 contents is not referenced. | DN's Megan Bray | Completed |  |  | If yes, this leads into deblending issues list and the requirement for an application process for customers to request specific gas quality from network operators and the relevant evidence to justify this requirement. | No change required
3c- Hydrogen content in combined entry/exit agreements (IEA/CSEP) | 2023-08-02 | Check whether specific H2 content is referenced within IEA's/ CSEP and consider aspects / interactions with the Offtake Arrangements Document (OAD) and Independent Gas Transporter Arrangements Document (IGTAD). | Megan Bray | Under Review |  |  | NTS standard storage connection agreement includes reference to 0.1% H2 content within Annex C - GAS ENTRY & QUALITY PROVISIONS. Interconnector Agreements are more bespoke bi-lateral agreements, however likely also include specific H2 content with entry provisions which will need to be changed to implement blending. | All exisiting combined connection agreements will need to be reviewed and will most likely require an ammendment within the Gas entry provisions section for H2 content. This will need to be reviewed on a case by case basis including engagement with necessary parliamentary authorities prior to a blend being recieved/ injected.
4- Safety case/ data sheets | 2023-07-18 | Check whether direct connect sites safety case and data sheets reference Methane / natural gas specifically. | DN's Megan Bray | Completed |  |  | If these include specific reference to Methane they would need to be updated to cover a blended gas. Would this sit with HSE Safety case review instead? | the HSE would need to consult on GS(M)R changes which would provide end consumers with an opportunity to comment / feedback on the H2 20% aspects. HSE would then need to make a decision on how to best manage the safety risk. Although the UNC has a valuable role in educating industry parties, the earlier any issues are highlighted the better (i.e. not awaiting HSE Safety Case related decisions). Therefore earlier industry enagaement on this matter is crucial.
5a- GT License exemption for Hydrogen DFO (NTS) | 2023-06-19 | Check if DFO injecting Hydrogen into NTS as a pre-blend would require a GT License exemption. Liase with Ofgem for clarification and refer to consultation (Gas Transporter Licence Exemption for Onshore Production of Gas) Exemption appies for pipeline up to 16.093km. | Megan Bray | Completed |  |  | https://www.legislation.gov.uk/uksi/2013/1726/made | Ofgem suggested exemption would need to be reviewed on a case by case basis considering the exemption conditions.
5b-GT License exemption for Hydrogen DFO (DN) | 2023-06-19 | Check if DFO injecting Hydrogen into Distribution Network as a pre blend, would require a GT License exemption. (refer to arrangements for Bio Methane plants) | DN's | Completed |  |  | Conditions on Exemption: a) "A does not convey the gas mentioned in article 3 to any premises; and b) the length of pipeline through which the gas mentioned in article 3 is conveyed does not exceed 16.043km between- i) the onshore gas processing facility at which gas processing operations are first carried out on that gas, and ii)the place at which the gas in introduced into a pipeline system operated by a gas transporter." | Ofgem suggested exemption would need to be reviewed on a case by case basis considering the exemption conditions.
6- European Interconnection Document | 2023-06-19 | Review EID to check if/where there may be cross over and requirement for amendments to manage both imports from and exports to interconnected TSO's. | Megan Bray | In- Progress |  |  | Interconnection Nomination, if blended gas is imported and exported across the interconnector, could that then sterilise connectioms from blending dwnstream of the IP, who would have the right to blend? | NG to arrange internal workgroup to review the processes and relevant changes required to UNC. Then engage with relevant stakeholders to agree on provisions.
7a- Managing the H2 blend cap (decrease in H2 availability) | 2023-07-18 | If H2 blend percentage needs to remain consistent, how could a loss in H2 supply be managed? | Networks | Closed |  |  | This issue would only arise if a fixed H2 blend model is implemented whereby injections would need to remain conistsent (fixed volumes). Storage could be a viable technical solution however may not be economical.. | Government role for blending as reserve offtaker would lead to variable blend, as hydrogen availability would vary.
7b- Managing the H2 blend cap (when limited NG to blend) | 2023-07-18 | Review potential mechanism to manage blend cap where constraint on the network limits natural gas flow to blend. | Networks | In-progress |  |  | In terms of gas quality safety a Terminal Flow Advisory can be submitted to stop injection, however where a network constraint reduces availability of N.gas to blend, is there a mechanism that could guarantee an increase in flow of N.gas before capacity buy-back is utilised.. | Review with capacity team and any lessons learnt from Lupton blend connection. Links to Nominations process and how this could be managed for blended gas? Non-fault curtailment process to be reviewed in phase 2 work.
8a- Clarification on the role of H2 Blending into networks (reserve offtaker or maximised production) | 2023-06-19 | Clarify with DESNZ whether H2 blending producers will be incentivised to maximise H2 production for blending or whether it will only be used as a reserve offtaker. If only reserve offtaker, does that H2 producer have the right to inject all of H2 reserve into networks, or is it down to network discretion/ capability? | DN's | Complete |  |  | Likely initial blending connections will be those with a HBM. DESNZ plan to run case by case assessment for HBM funding and forsee that blending will be utilised as reserve offtaker where Hydrogen Producers main demand is 100% H2 consumer, or blending may be utilised as an interim solution where production goes live before the demand is connected and ready. HBM's are still being considered in terms of roll out and assessment criteria. (Links with Action 13). H2 blending consultation due to be published in Sept, this may also give steer on the govt's perceived role for blending. | For distribution level blending - Reserve offtaker for electrolytic and CCUS projects to manage 'volume risk'. Blending may also have value in strategically enabling electrolytic hydrogen producers to support the wider energy system, beneficial for electrolytic hydrogen producers located behind electricity network constraints using excess renewable electricity that would otherwise have been curtailed. Potential role of blending into Tx network yet to be outlined.
8b-Reserve offtaker role provisions | 2023-11-22 | If only reserve offtaker, does that H2 producer have the right to inject all of H2 reserve into networks, or is it down to network discretion/ capability? |  | Created |  |  | Links to capacity allocation and right to connect anywhere on network. | To be further explored in phase 2 (development of blending delivery model) non-fault curtailment
9- Gas Quality changes in existing and new NTS NEA's | 2023-06-19 | Review previous ‘Implementing the Proposed Gas Quality Standards’ work programme and assess if outputs from this work can give guidance on how a gas quality change within existing and new NEA’s could be manged for a blended gas. | Megan Bray | In- Progress |  |  | Further work required to establish how blend capacity will be allocated and exploration into appropriate gas quality data provision for hydrogen blends. | Separate work programme to review gas quality data provision for hydrogen blend required? To be further explored in phase 2 under information flows. | Check this is captured in phase 2 plan
10- Gas Quality changes in existing and new DN NEA's | 2023-06-19 | Review GGG work looking at Gas Quality Data Provision and the recommendations from this to assess how we can enhance gas quality changes within existing and new Distribution NEA’s for blending. | DN's | In- Progress |  |  | Further work required to establish how blend capacity will be allocated and exploration into appropriate gas quality data provision for hydrogen blends. | Separate work programme to review gas quality data provision for hydrogen blend required? To be further explored in phase 2 under information flows. | Check this ic captured on phase 2 plan
11- De-blending | 2023-07-18 | Frontier Economics paper outlines high-level commercial framework changes to enable de-blending. Liase with Ofgem/DESNZ/HSE whether this should be considered alongside blending. If so who would be responsible for ownership of the de-blending facilities. | Megan Bray | In-progress |  |  | Clarity on requirement for de-blending technology to be available following govt response to blend consultation. Links to action 13 | Requirement for de-blending technology will be clearer following submission of safety case evidence and once decision has been made for Transmission blending (volume % cap).
12- Assumptions | 2023-07-18 | Review updated assumptions during each session | Megan Bray | Complete
13- Blend variability | 2023-08-02 | Potential impacts to connected end users may be worsened by variability, therefore understanding who this could impact, why and the costs and times for necessary mitigating solutions required need to be considered. | Industry / Networks | In- Progress |  |  | Blending consultation request's feedback from end consumers on H2 acceptability and specifically calls out variability. Also networks conducting studies to assess end user acceptability | Further site specific assessments are required to assess the impacts of blend variability, before necessary mitigation modification costs and timelines are concluded. Links to action 11.
14- H2 blend purchased on OCM | 2023-08-02 | Would SO need to know when they are purchasing H2 on OCM? Check with NCC. | Megan Bray | In-progress |  |  | Gas traded on OCM in energy therefore are updates to Gemini required so that Network operator was aware when they were purchasing H2 for shrinkage / own use gas. | Traded as kwh of energy, no need to differentiate between natural gas/ hydrogen unless any operational implications.
15- UNC Related Documents | 2023-11-22 | Changes to UNC document may impact the 'UNC related documents'. Therefore these will also require review once final UNC changes have been agreed. | Networks | Created |  |  | To be reviewed once final changes to UNC have been agreed.