## Sheet1
Distribution Network Charging Methodology Forum
Live Topic Tracker
TOPIC NO | TOPIC NAME | DESCRIPTION | TOPIC RAISED BY | TOPIC LEAD | STATUS | UPDATE | COMMENTS
1 | GB ENERGY SUPPLIER OF LAST RESORT | IN NOVEMBER 2016, GB ENERGY CEASED TRADING, WITH CO-OPERATIVE ENERGY APPOINTED OF SUPPLIER OF LAST RESORT. STANDARD SPECIAL CONDITION OF THE GAS TRANSPORTER LICENCE PROVIDES PROVISION FOR LAST RESORT SUPPLY PAYMENTS. LICENCEE MUST RECEIVE A VALID CLAIM BEFORE PAYMENT MADE TO CLAIMANT AND TRANSPORTATION PRICES ADJUSTED TO RECOVER. OVER OR UNDER RECOVER OF CLAIM IS ADJUSTED IN THE FOLLOWING YEAR. LICENCEE PROVIDES A STATEMENT TO OFGEM FOR ANY YEAR THAT CHARGES ARE ADJUSTED. RAISED AS AN OPEN TOPIC FOR UNCLEAR VALUE AND TIMING OF ANY ADJUSTMENT TO TRANSPORTATION CHARGES | CRAIG NEILSON, CADENT | CRAIG NEILSON, CADENT | OPEN | 2017-01-01 | WATCHING BRIEF ON TOPIC, AND ESTABLISH POINT OF CONTACT AT OFGEM
[6 empty] | 2017-03-01 | CLARIFICATION THAT ASSOCIATED LICENCE CONDITIONS PRECLUDE THE POSSIBILITY OF IN YEAR PRICE CHANGES
[6 empty] | 2017-06-01 | RESPONSE FROM LESLEY NUGENT AT OFGEM. NO UPDATE TO REPORT AT THIS STAGE, BUT ADDITIONAL POC AT OFGEM IS JEREMY ADAMS-STRUMP
[6 empty] | 2017-09-01 | EMAIL TO LESLEY NUGENT AND JEREMY ADAMS-STRUMP AT OFGEM FOR ANY UPDATE ON POTENTIAL FOR CLAIM AHEAD OF 2018/19 PRICE SETTING. NO RESPONSE AS AT 14/09/17
[6 empty] | 2017-09-01 | OFGEM CONFIRMED THAT THEY EXPECT TO DIRECT ON A CLAIM IMMINENTLY AND TO ADVISE NETWORKS IN LINE WITH INDICATIVE AND FINAL CHARGE SETTING PROCESS
2 | REVIEW OF DN CHARGING METHODOLOGY | THE CURRENT GAS DISTRIBUTION TRANSPORTATION CHARGING METHODOLOGY PROVIDES TARGETED LEVEL OF REVENUE COLLECTION BETWEEN SYSTEM CHARGES (CAPACITY / COMMODITY) AND CUSTOMER CHARGES (CAPACITY / FIXED). THESE SPLITS ARE BASED ON THE EXPECTED COST BASE OF GDNs. AS THESE HAVE NOT BEEN REVIEWED FOR SOME TIME, AND THE RIIO GD-1 FRAMEWORK MIGHT PROVIDE REFRESHED INTELLIGENCE ON GDN COST BASE, THE CHARGING METHODOLGY SHOULD BE REVIEWED ACCORDINGLY GOING INTO THE NEXT PRICE CONTROL PERIOD COMMENCING APRIL 2021. | CRAIG NEILSON, CADENT |  | OPEN | 2017-09-01 | INITIALLY RAISED AT DNCMF
3 | IMPACT OF DN ENTRY GROWTH ON GDN CHARGING METHODOLOGY | EXAMINATION AS TO WHETHER GROWTH IN DN ENTRY ACROSS THE NEXT PRICE CONTROL WARRANTS AMENDMENT TO THE GDN CHARGING METHODOLOGY. AS ENTRY FLOWS INCREASE, THE MORE DN ENTRY CREDIT WILL PROVIDED, OFFSET BY INCREASES TO EXIT CHARGES. IF NETWORK INVESTMENT IS REQUIRED TO FACILITATE MORE ENTRY FLOWS, WHO SHOULD PAY FOR THIS? CONTINUATION OF CURRENT REGIME WOULD CREATE LARGER CREDITS FOR ENTRY FLOWS SUBSIDISED BY EXIT. | CRAIG NEILSON, CADENT | CRAIG NEILSON, CADENT | OPEN | 2017-09-01 | INITIALLY RAISED AT DNCMF. ENGAGEMENT SESSION WITH OFGEM PLANNED FOR 25/09/17
4 | IMPACT OF NTS CHARGING METHODOLOGY REVIEW ON GDN REVENUE AND PRICES | NTS WILL BE IMPLEMENTING A NEW CHARGING METHODOLOGY FROM OCT-19, COMPLIANT WITH EU TARIFF CODE. PROPOSED CHANGE IS TO A CAPACITY WEIGHTED DISTANCE MODEL. IT IS HOPED THAT IN THE MEDIUM TERM THIS APPROACH WILL DRIVE INCREASED PREDICTABILTY AND STABILITY OF CHARGES. GIVEN CURRENT STAGE OF DEVELOPMENT OF MODEL AND UNC MODIFICATION, IMPACT TO GDN CHARGES IS NOT CURRENTLY CLEAR. GDNS EXAMINIE ISSUE AT A NATIONAL LEVEL WITH A VIEW TO SIGNPOSTING IMPACTS VIA NTSCMF | BRIDGET HILL, EON |  | OPEN | 2017-09-01 | SUGGESTED BY BRIDGET HILL OF EON THAT TOPIC IS ADDED TO THE REGISTER