## CMC_Summary
Totals by Budget Area (£,000's) | [9 empty] | Current Year Actual Spend By Customer Class
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Total Cost of Project | Previous Year Actuals | Current Year Actuals | Current Year Forecast | Future Financial Years Forecast | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 146.989 | 196.758 | 80.291 | 4.467 | 112 | 0 | 0 | 4.467 | 0 | 0 | 0
|  | Internal |  | 127.307 | 107.913 | 76.864 | 31.049 | 0 | 0
|  | Total |  | 274.296 | 304.671 | 157.155 | 35.516 | 112 | 0
RAG status: | [9 empty] | 0 | 0 | 0 | 0 | 0
Cost/forecast within approved value & budget
Cost/forecast over approved value, but total spend within budget
Total cost/forecast over budget | [9 empty] | 0 | 4.467 | 0 | 0 | 0
Note that project expenditure & budget values shown do not include margin
Internal costs are not deducted from budget (unless otherwise notified)
Details of Changes (£,000's)
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Actuals | Change in Current Year Forecast | Change in Future Financial Years Forecast | Commentary
UK Link Future Release 1.1 (DSC Change Budget) | 0 | 112 | 0 | 0 | 112 | 0 | Amber status of Release 1.1 is due to the 'Approved Value' being zero. Once the BER is approved this will be populated and the status will return to Green
UK Link Future Release 1.1 (DSC Change Budget) | 0 | 112 | 0 | 0 | 112 | 0
3995 TRAS Tip-off Hotline Data Provision - External | 0 | 0.6 | 0 | 0.6 | 0 | 0 | Small adjustment has been put in to match actual spend with invoice received.
3995 TRAS Tip-off Hotline Data Provision - Total | 0 | 0.5 | 0 | 0.5 | 0 | 0
3991 Pafa Administrator Role [Usr Pys] - External | 0 | 1 | 0 | 1 | 0 | 0 | Small adjustment has been put in to match actual spend with invoice received.
3991 Pafa Administrator Role [Usr Pys] - Total | 0 | 1 | 0 | 1 | 0 | 0
Grand Total | 0 | 227.1 | 0 | 3.1 | 224 | 0

## CMC_Current
[25 empty] | SORT FIELD 2 | [11 empty] | SORT FIELD 1
[13 empty] | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [12 empty] | Y | Y | Y | Y | Y | Y |  | Formulas do not delete |  |  | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Next Contractual Step | Next Step Date | Expenditure Type | Total Approved Value | Estimated Total Cost of Project | Previous Year Actuals | Current Year Actuals | Current Year Forecast | Future Financial Years Forecast | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Line Sequence Sort (THEN BY THIS) | PM | Line Check NOT FOR FILTER | Show Approved Money? | Show Reported Money? | Auto Assess of CMC Friendly? | Manual CMC Flag | ng-t | ng-d | sgn | wwu | ngn | Progress Sort (SORT BY THIS) | Matcher | Project Line | CBP Flag | High Level Process Stage | Next Contractual Step | Next Step Date | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Actuals | Change in Current Year Forecast | Change in Future Financial Years Forecast | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 0 | 4160External | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 0 | 4160Internal | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4160 | Provision of data for TRAS relating to permission provided in UNC0574 | On Hold (Delivery Stage) | On Hold | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 0 | 4160Total | 4160 Provision of data for TRAS relating to permission provided in UNC0574 - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | BER Stage | [CMC] Approve BER | N/A | External | 0 | 112 | 0 | 0 | 112 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4340External | 4340 UK Link Future Release 1.1 (DSC Change Budget) - External | 0 | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | BER Stage | [CMC] Approve BER | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4340Internal | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal | 0 | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | BER Stage | [CMC] Approve BER | N/A | Total | 0 | 112 | 0 | 0 | 112 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 0 | 0 | [15 empty] | 4340Total | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Total | 0 | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | External | 33.273 | 11.23 | 9.032 | 2.198 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 11.23 | 0 | 0 |  | CCR to be issued, project is in closure. | [5 empty] | Y | Y | N | N | N | N | N | 5 | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | Internal | 25.714 | 22.721 | 22.684 | 0.037 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 22.721 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Delivery Stage | [XOS] Issue CCN | 2017-07-31 | Total | 58.987 | 33.951 | 31.716 | 2.235 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 33.951 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-10-06 | External | 15.016 | 3.016 | 2.016 | 1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 3.016 | 0 | 0 |  | CCR to be issued, project is in closure. | [5 empty] | Y | Y | N | N | N | N | N | 5 | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | Y | SAME | SAME | DIFF | 0 | -1 | 0 | -1 | 0 | 0 | SAME | YES | -1 | TRUE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-10-06 | Internal | 57.5 | 43.1 | 22.7 | 20.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 43.1 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | Y | SAME | SAME | DIFF | 0 | 0 | 0 | -3.1 | 3.1 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Delivery Stage | [XOS] Issue CCN | 2017-10-06 | Total | 72.516 | 46.116 | 24.716 | 21.4 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 46.116 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | Y | SAME | SAME | DIFF | 0 | -1 | 0 | -4.1 | 3.1 | 0 | SAME | YES | -1 | TRUE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | External | 89 | 60.288 | 60.288 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 60.288 | 0 | 0 |  | CCR to be issued, project is in closure. | [5 empty] | Y | Y | N | N | N | N | N | 5 | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | Internal | 31.05 | 36.444 | 24.18 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 36.444 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s | Delivery Stage | [XOS] Issue CCN | 2017-08-31 | Total | 120.05 | 96.732 | 84.468 | 12.264 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 96.732 | 0 | 0 | [7 empty] | Y | Y | N | N | N | N | N | 5 | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | External | 9.7 | 10.224 | 8.955 | 1.269 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 10.224 | 0 | 0 | Sent | CCR has been issued, awaiting approval | [5 empty] | Y | Y | N | N | N | N | N | 5.5 | 3995External | 3995 TRAS Tip-off Hotline Data Provision - External | Y | SAME | SAME | SAME | 0 | -0.6 | 0 | -0.6 | 0 | 0 | SAME | YES | -0.6 | TRUE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | Internal | 3.12 | 2.267 | 2.3 | -0.033 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.267 | 0 | 0 | Sent | [6 empty] | Y | Y | N | N | N | N | N | 5.5 | 3995Internal | 3995 TRAS Tip-off Hotline Data Provision - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
MKT_1718_01 | 3995 | TRAS Tip-off Hotline Data Provision | Closedown Stage | [CMC] Approve CCN | N/A | Total | 12.82 | 12.491 | 11.255 | 1.236 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 12.491 | 0 | 0 | Sent | [6 empty] | Y | Y | N | N | N | N | N | 5.5 | 3995Total | 3995 TRAS Tip-off Hotline Data Provision - Total | Y | SAME | SAME | SAME | 0 | -0.5 | 0 | -0.5 | 0 | 0 | SAME | YES | -0.5 | TRUE |  | 0
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved | CCR approved, project now closed. | [5 empty] | Y | Y | N | N | N | N | N | 5.5 | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - External | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Internal | 9.923 | 3.381 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 3.381 | 0 | 0 | Approved | [6 empty] | Y | Y | N | N | N | N | N | 5.5 | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Internal | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] | Closed | N/A - Closed | N/A | Total | 9.923 | 3.381 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 3.381 | 0 | 0 | Approved | [6 empty] | Y | Y | N | N | N | N | N | 5.5 | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DES) [Usr Pys] - Total | Y | DIFF | DIFF | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | TBC | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | Zero costs being done as BAU | [5 empty] | Y | Y | N | Y | Y | Y | Y | 1 | 4242External | 4242 Monthly provision of national S&U statistics - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | TBC | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | Y | Y | Y | Y | 1 | 4242Internal | 4242 Monthly provision of national S&U statistics - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4242 | Monthly provision of national S&U statistics | Closed | N/A - Closed | TBC | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | Y | Y | Y | Y | 1 | 4242Total | 4242 Monthly provision of national S&U statistics - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | External | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  | Zero costs being done as BAU | [5 empty] | Y | Y | N | Y | Y | Y | Y | 6 | 4248External | 4248 Quarterly smart metering reporting for HS&E and GDNs - External | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | Y | Y | Y | Y | 6 | 4248Internal | 4248 Quarterly smart metering reporting for HS&E and GDNs - Internal | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4248 | Quarterly smart metering reporting for HS&E and GDNs | Closed | N/A - Closed | N/A | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | [7 empty] | Y | Y | N | Y | Y | Y | Y | 6 | 4248Total | 4248 Quarterly smart metering reporting for HS&E and GDNs - Total | Y | SAME | SAME | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 2
Note on BA3: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual