## Summary
Data Request ID | Contributor | Data Item | Data Item Description | Priority Rating | Source | Request Date | Expected Date | Status | Received | Validated | Comments
1 | Theft | Shipper Theft Data | Details of theft provided to Xoserve within CMS | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-07 | 2021-07-26
2 | Theft | TRAS Outcome File Data | The data outcome from TRAS | H | Xoserve (TRAS) | 2021-06-08 | 2021-07-07
3 | Theft | Current AMR Snapshot | A report of all of the current sites with an AMR fitted | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-23 | 2021-07-26
4 | Theft | Historical AMR Report | A historical report of the AMR installation and removal date | H | Xoserve | 2021-06-08 | 2021-07-07
5 | Theft | Telemetered Sites Report | A report of all the sites that are telemetered or have a datalogger fitted | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-23 | 2021-07-26
6 | Theft | Smart Meter Data | The forecast of smart meter installation | M | Public domain | n/a
7 | Theft | Retail Theft Data | Organised crime theft percentage | M | Public domain | n/a
8 | Unregistered and Shipperless | Snapshot Files (including MPR details) | Monthly Snapshot files | L | Xoserve | 2021-06-08 | 2021-07-26
9 | Shipperless | Gas Safety Regulations visit data | Details of Gas Safety Regulation Visits | L | Xoserve | 2021-06-08 | 2021-07-26
10 | Shipperless | Connection Details for Shipperless Sites | Details of connections for shipperless sites | L | Xoserve | 2021-06-08 | 2021-07-26
11 | Shipperless | Shipperless AQ report | A report of the AQ changes for shipperless sites that are now connected | L | Xoserve | 2021-06-08 | 2021-07-26
12 | Unregistered | Connection Details for Orphaned Sites | Details of connections for Orphaned sites | L | Xoserve | 2021-06-08 | 2021-07-26
13 | Unregistered | Unregistered AQ report | A report of the AQ changes for Unregistered sites that are now connected | L | Xoserve | 2021-06-08 | 2021-07-26
14 | Consumption Meter Errors - Inherent Bias | Meter Type and Age report | Meter Type by EUC, Class and installation year | M | Xoserve | 2021-06-08 | 2021-07-14
15 | Consumption Meter Errors - Inherent Bias | Annual in-service Testing | In service testing of domestic sized meters | M | BEIS - Office for Product Safety and Standard | 2021-06-09 | 2021-06-16 |  |  |  | Further report expected September 2021
16 | Consumption Meter Errors - Faulty Meter | Faulty Meter Portfolio | Details of all the supply meter points that currently have a fault set | M | Xoserve | 2021-06-08 | 2021-07-14
17 | Consumption Meter Errors - Extremes of Use | Within Day Use | Within day reads | L | Shippers | TBC |  |  |  |  | We are not planning on requesting this data this AUG year
18 | Meter Errors at LDZ input | Measurement Error Register | The register of the Measurement Errors held on the Joint Office Website | L | Joint Office website | n/a
19 | IGT Shrinkage | Main Length | Details of the length of main and the total number of end users | L | IGTs | 2021-06-09 | TBC |  | 2021-07-09 | 2021-07-09
20 | IGT Shrinkage | Leakage Rates | Leakage rates from the NLT | L | Public Domain | n/a
21 | IGT Shrinkage | IGT Sites | Number and associated AQ of sites on IGTs | M | Xoserve | 2021-06-08 | 2021-07-14 |  | 2021-07-23 | 2021-07-26
22 | Average Pressure Assumption | Sites with Volume Conversion Equipment Fitted | A report providing information for sites that have volume conversion equipment fitted | L | Xoserve | 2021-06-08 | 2021-07-26 |  | 2021-07-28 | 2021-07-28
23 | Average Temperature Assumption | Meter Location | Snapshot of the meter location split by EUC band | L | Xoserve | 2021-06-08 | 2021-07-26 |  | 2021-07-26 | 2021-07-26
24 | No read at the line in the sand | Sites with No Reads after April 2019 | Details of the sites with no actual read after April 2018 | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-06-25 | 2021-06-25
25 | No read at the line in the sand | AQ Corrections | Details of the AQ Corrections carried out on sites without reads | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-07 | 2021-07-07
26 | No read at the line in the sand | Read Rejections | Details of the read rejections carried out on sites without reads | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-29 | 2021-07-30
27 | No read at the line in the sand | Reconciliation | Monthly report of the reconciliations since Nexus go live | H | Public Domain (Xoserve) | n/a
28 | No read at the line in the sand | Additional Reconciliation Information | Percentage of NDM allocation that has been reconciled per month since June 2017 | H | Xoserve | 2021-06-08 | 2021-07-07
29 | Incorrect Correction Factors | Site Details | Correction factors for all sites in EUC04 and above | M | Xoserve | 2021-06-08 | 2021-07-14
30 | General Industry Information | AQ Change Report | The summary of the AQ changes by month | M | Xoserve | 2021-06-08 | 2021-07-14
31 | General Industry Information | Throughput | Daily Total throughput, DM allocation, NDM allocation and UIG by EUC | M | Xoserve | 2021-06-08 | 2021-07-14
32 | General Industry Information | Daily Allocation Factor | The daily Allocation factors applied to NDM sites | M | Xoserve | 2021-06-08 | 2021-07-14
33 | General Industry Information | Offline Adjustments | A report of all the offline adjustments that have taken place since the previous snapshot | M | Xoserve | 2021-06-08 | 2021-07-14
34 | Consumption Adjustments | Previous Consumption Adjustments | Valid consumption adjustments submitted from January 2018 onwards | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-07-29 |  | A partial file has been provided which has been queried
35 | Meters with a By-Pass Fitted | Meter By-Pass Portfolio | Details of all the Supply Meter Points with a By-Pass fitted | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-06-24 | 2021-07-07
36 | Meters with a By-Pass Fitted | Historical By-Pass view | Report of any changes to the open and closed status since June 2017 | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-06-29 | 2021-07-07
37 | Meters with a By-Pass Fitted | Accepted Read Report | A report of all the accepted reads for sites with a meter By-Pass fitted | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-06-24 | 2021-07-07
38 | Meters with a By-Pass Fitted | Rejected Reads Report | A report of all the rejected reads for sites with a meter By-Pass fitted | H | Xoserve | 2021-06-08 | 2021-07-07 |  | 2021-06-24 | 2021-07-07
39 | Meterless Sites | Meterless Sites Portfolio | A snapshot of all Meterless Supply Meter Points | L | Xoserve | 2021-06-08 | 2021-07-26
40 | Meterless Sites | Rejected Reads | A report of all the rejected reads for Meterless sites | L | Xoserve | 2021-06-08 | 2021-07-26
41 | Isolated Sites | Isolated Sites Portfolio | A snapshot of all Isolated Supply Meter Points | H | Xoserve | 2021-06-08 | 2021-07-14 |  | 2021-07-16 | 2021-07-22
42 | Isolated Sites | Accepted Reads | A report of all the accepted reads for Isolated Sites | H | Xoserve | 2021-06-08 | 2021-07-14 |  | 2021-07-21 | 2021-07-22
43 | Isolated Sites | Rejected Reads | A report of all the rejected reads for Isolated Sites | H | Xoserve | 2021-06-08 | 2021-07-14 |  | 2021-07-16 | 2021-07-22
44 | Isolated Sites | Connection Details for Isolated Sites | Connection Details for Isolated Sites | H | Xoserve | 2021-06-08 | 2021-07-14