## Slide 1: Change Management Committee
13th October 2021

## Slide 2: Section 2: DSC Change Budget & Horizon Planning

## Slide 3: DSC Change Budget 21/22 YTD

## Slide 4: Budget v Committed Spend BP21/22
Full finance tracker can be found here with commentary on monthly variance
Chart: NTS Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 54600 | 10542.1687 | 0 | 4216.8675 | 4216.8675
Spend | 0 | 0 | 0 | 0 | 0
Chart: Total Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 2589600 | 500000 | 100000 | 200000 | 200000
Spend | 1888242 | 0 | 99998.6366 | 0 | 0
Chart: Variance
| Shipper | DN | IGT | NTS
 | -70000 | -100000 | 0 | 0
Chart: Shipper Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 1495000 | 288654.6185 | 58434 | 115461.8474 | 115461.8474
Spend | 1316447.75 | 0 | 58972.7823 | 0 | 0
Chart: DN Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 900000 | 173772.0111 | 35457 | 69508.8044 | 69508.8044
Spend | 543442.45 | 0 | 35503.3915 | 0 | 0
Chart: IGT Committed Spend v Approved Budget
| Change Budget | Split of Contingency | PAC Funding | Xoserve Change Fund | Market Trials
Budget | 140000 | 27031.2017 | 6109 | 10812.4807 | 10812.4807
Spend | 28351.8 | 0 | 5522.4628 | 0 | 0

## Slide 5: Change Pipeline

## Slide 7
2020-2022 DSC Change / MiR Pipeline
 | 2021 |  |  |  |  |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  | 
 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Minor Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Major Releases |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSSC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Standalone Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
June 2021 (DBTI + PIS/Closedown)
Nov 2021 Analysis / Design
November 2021 Build/Test Implement/PIS
MiR 9
MiR 10
Regression
PIS
Retro (MOD 0651)
Key:
On Track
Potential Activity
Nov 21 IA
November 2022 Build/Test/Implement/PIS
*Nov 2022 Analysis / Design
XRN
5206
5237
XRN
5146
XRN
5038
XOS Change Fund 21/22
PAC
BER
CCR
Scope
CCR
CCR
PAC XRN4876
BER
CCR
Complete
Potential risk to plan
Plan At Risk
Key:
Approval on track
Approval at risk
Approved
Nov 20 PIS
CCR
XRN
4780C
XRN
5231
BER
EQR 5379 5231
XRN
5183
BER
5183
* Subject to no delays/impact from CSSC implementation
* Feb 23 & June 23 Release development and scoping
EXTERNAL(MT/UEPT/E2E/Defect Mgmt)
Planning
Transition
Go Live Range
XRN
4780C

## Slide 8: Section 3: Capture

## Slide 9: New Change Proposals – Initial Review
XRN / Title | Voting |  |  |  | DSC Service Area
 | Shipper | DNO | IGT | NTS | 
XRN5419 Amendments the DSC Service Description Table to support REC | For Information |  |  |  | N/A
XRN5431 Temporary community access to pre-COVID AQ values for Shippers | Y |  |  |  | Service Area 15: Value Added Services

## Slide 10: XRN5419 Amendments the DSC Service Description Table to support REC
Voting Parties
DSC Service Area: | N/A
Link to Change Proposal | Link to CP
Change Details
Sponsor Representative | Xoserve
Change Description
The function and role of SPAA closed as of the 1st September 2021 as part of the transition to REC, henceforth all the SPAA obligations will be governed under REC A piece of work has been carried out to identify any services within the DSC Service Description Table that have either transitioned to REC or can be removed as they will no longer be required and the SDT has been amended to reflect the proposed changes For the lines below, we are seeking approval that the lines can be removed For the lines that we are seeking approval to amend the reference numbers to align with REC – Please see the Change Proposal
Change Type | Documentation
Priority Score | Medium
Customer Class | Voting Party?
Shipper | N/A
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
For Information – This CP will go to October CoMC for approval | 

## Slide 11: XRN5431 Temporary community access to pre-COVID AQ values for Shippers
Voting Parties
DSC Service Area: | Expected to be a Specific Service (SA22)
Link to Change Proposal | Link to CP
Change Details
Sponsor Representative | Xoserve
Problem Statement
COVID restrictions may have temporarily impacted the AQ of a Supply Meter Point (SMP) and Shippers currently can’t access the pre-COVID AQ value.
Change Type | Non Regulatory
Priority Score | High
Customer Class | Voting Party?
Shipper | Y
Distribution Network Operators (DNOs) | N/A
National Grid Transmission | N/A
IGT’s | N/A
Change Description
A request has been received from a number of Shippers to access specific historic AQ that will assist in identifying whether there has been any temporary impact to the AQ as a result of COVID restrictions. This data has been requested by the Shipper so that it can be considered in discussions with the consumer and to help validate the accuracy of the current AQ due to uncertainty arising around the current AQ due to the impacts of the Pandemic. This access would be for a defined period, so these parties may obtain a “pre-COVID AQ” value for SMPs. The Pre-COVID AQ value would be determined as the ‘Rolling AQ’ that was effective on 1st April 2020 – having been derived as part of the March 2020 AQ Calculation or earlier. It is anticipated that this service will conclude on 01 October 2022 Disclosure Request Report; DRR-SEP21-01 was approved by Contract Management Committee (CoMC) at the September Extraordinary meeting. This allows the CDSP to release the Rolling AQ that was effective on 01 April 2020 to a Shipper where they have requested it. This Change Proposal has been raised in order to put in place the process to deliver this service to Shippers.

## Slide 12: Change Update
XRN 5235 Request for access to SOQ data & capacity figures which influence transportation charges

## Slide 13: XRN 5235 Request for access to SOQ data & capacity figures which influence transportation charges
Please note: XRN 5235 was originally raised under the title:
Include SOQ in the “UIG Additional National Data” report (Originally introduced by XRN 4806).
On consultation with the CP proposer the title was amended to better reflect the scope of the change.

## Slide 14: Change Overview
Gazprom raised CP XRN 5235 to request access to aggregated SOQ and AQ data to better understand how capacity levels have been changing and how this might affect the annual Distribution Network Transportation Charges.
A request for historical data was also included within the CP to allow Shippers to compare and contrast with the previous year/s’ data and associated charges.
Our service provider is currently working on solution options for this CP. The aggregation level is yet to be determined and will be taken to CoMC for approval.

## Slide 15: What we need to know is?
Is there still sufficient interest from other DSC customers to progress XRN 5235 as a DSC funded Change Budget?

## Slide 16: 3.2 Change Proposals – Post Solution Review for Approval
XRN5377 Addition of ‘Class’ field to supply point data reports
XRN5144 Enabling Re-assignment of Supplier Short Codes

## Slide 17: XRN5377 Addition of ‘Class’ field to supply point data reports
Proposed Release Link to Change Proposal Change Pack Comm Ref Voting Funding | DSG/ Xoserve Preferred Option | Solution Summary Outcome and implementation date outcome |  |  |  | Comments
 |  | Organisation | Approve | Defer | Reject | 
Proposed delivery: ad-hoc Link to CP Link to Change Pack ref: 2898.3 – MT PO Voting: DNO High Level Solution Cost: Option 1: £0 Funding: MTB DSC Service Area 9: Customer Reporting (all forms) | Option 1 - Xoserve |  |  |  |  | No Representations Received

## Slide 18: XRN5144 Enabling Re-assignment of Supplier Short Codes
Verbal Update to be presented by David Addison

## Slide 19: section 4. Design & Delivery

## Slide 20
MDD Market Participant Identify Approach Document
Functional Changes |  |  |  |  | 
Change Pack ref: 2898.2 - MT – PO Implementation: TBC following approval Voting: N/A Approval to be sought at CoMC in October. | Solution & Implementation Summary outcome |  |  |  | Comments
 | Organisation | Approve | Defer | Reject | 
 | EDF Energy | X |  |  | Approve with the following comments: Section 3.1 table – there are four footnotes showing in table but footnote 1 is not shown on this page Xoserve Response: This has been noted Section 4.3 - there is no mention of where a party wishes to reallocate an active MPID to another of it's legal entities? Xoserve Response: As defined in section 4.3 of the MDD Verification document, where a Meter Point is still active a SSC can not be reallocated. Section 5.4 'All Market Participants will be invited to make representations.' - are we getting such notifications as we thought we had to check website regularly for any changes? 'For DSC parties this will be through the DSC Contract Manager' - i don't recall seeing these notifications? Xoserve Response: These have been issued via email since the closure of SPAA forum as well as still being published on the website here: https://www.xoserve.com/services/industry-reference-values/ We can confirm you are on the distribution list to receive these notifications, (the last notification being sent on 14th September). If you have any further issues, please contact xoserve.customer.lifecycle.team@xoserve.com.
 | Scottish Power | X |  |  | Happy to approve as most appear to be cosmetic changes, however, the only point is that any references to MAM within the document will need to be amended to MEM. Xoserve Response: We can confirm that any reference to MAM will be staying as MAM as this is defined in UNC.
Design Change Pack

## Slide 21: Standalone Change Documents for Approval (BER, CCR, EQR)
BER for XRN5393 Implementation of NTS Capacity related UNC Modifications
  Voting – NTS

## Slide 22: XRN5231 Provision of a FWACV Service
BER for XRN5231 Provision of a FWACV Service
  Voting – DNO & NTS

## Slide 23: XRN5231 Flow Weighted Average CV
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Overall Status set to Amber due multiple phases progressing in parallel and the need to baseline the project phases following design completion, funding approval & outstanding clarifications/decisions required from National Grid and DNs. Start Up and Initiation Phase progressing in parallel with Design Design Change Pack to be published on 1st October, approval to be sought at October Committee BER to be published to seek approval at the October 21 ChMC Proposed Project Engagement Strategy to be published to NG and DN outlining how the project will engage through project delivery phases to seek support/approval Testing, Dual Run and Market Trials dates to be baselined in conjunction with customer engagement sessions over the coming weeks Change due to be implemented by March 2022 Decision In October ChMC Approval of BER Document |  | 
Risks and Issues | There is a risk that until the transition & cutover approach is agreed between Xoserve, National Grid & DNs to confirm the length of Post Implementation Support and what support dependencies are required from National Grid as the existing service provider. There is a risk that National Grid have served notice to terminate the current FWACV service on the 31st March 2022 and the project plan does not meet an implementation date of the new service from the 01st April 2022, resulting in the need to negotiate an extension of the service by National Grid. |  | 
Cost | BER is being presented for a decision to proceed at October’s ChMC for the scope defined |  | 
Scope | XRN5231 Flow Weighted Average (CV) XRN5282 PRCMS Processing (Gemini Consequential Change – Part A) |  | 
Slide updated on 28th September for FWACV
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 24: XRN5289 – November 21 Major Release
Project Update
Data Cleanse Approach/Plan
Deep Dive on 4780C Change Assurance Report & Return to Green Plan
Slide updated on 20th August 2021

## Slide 25: XRN5289 – November 21 Major Release - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule | Risks and Issues |  | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | User Acceptance and Regression testing is in progress and being re-planned due to below issues for remaining testing Implementation Dress Rehearsal planned for 30th September - 1st October Performance Testing due to commence 4th October Decision In October ChMC: No decisions are required this month. |  |  | 
Risks and Issues | Issue (RTC65631) - ​Increase in the number of BAU defects being found impacting XRN5072, XRN5007 and XRN5180 during testing. Mitigation, defects are currently all planned to be deployed prior to exiting test Issue (RTC66115) - MAP ID changes have not been delivered by third party in time and is now impacting the timelines |  |  | 
Cost | Forecast to complete delivery against approved BER |  |  | 
Scope | In Scope: XRN4941 MOD0692 - Auto updates to meter read frequency XRN5007 Enhancement to reconciliation process where prevailing volume is zero​ XRN5072 Application and derivation of TTZ indicator and calculation of volume and energy – all classes​ XRN5142 New allowable values for DCC Service Flag in DXI File from DCC​ XRN5180 Inner tolerance validation for replacement reads and read insertions​ XRN4780C Inclusion of Meter Asset Provider Identity (MAP Id) in the UK Link system (CSS Consequential Change) Descoped: XRN5091 Deferral of creation of Class change reads at transfer of ownership​ XRN5186 MOD0701 Aligning capacity booking under the UNC and arrangements set out in relevant NExAs​ XRN5187 MOD0696 Addressing inequalities between capacity booking under the UNC and arrangements set out in the relevant NExAs |  |  | 
Slide updated on 24th September 2021
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 26: Data Cleanse Approach/Plan

## Slide 27: Data Cleanse Background
November 2021 Release project is a major UK Link release consists of 6 changes, 4 of these changes require a data cleansing where existing UK Link data needs to be profiled and cleaned as part of project cutover/PIS activities.
These slides cover the high-level data cleansing approach for all of November 2021 changes and aims to provide the approach involving list of activities, dependencies and schedule for each of the changes in scope of data profiling and cleansing of this release.
The list of changes where data profiling and cleansing is identified as below:
# | XRN Reference | Description | Data Profiling & Cleansing Required | Business Process Area
1 | 4941 | MOD0692 - Auto updates to meter read frequency | Y | SPA
2 | 5007 | Enhancement to reconciliation process where prevailing volume is zero | Y | Metering
3 | 5072 | Application and derivation of TTZ indicator and calculation of volume and energy – all classes | Y | Metering
4 | 5142 | New allowable values for DCC Service Flag in DXI File from DCC | Y | SPA

## Slide 28: November 21 Data Cleansing - Proposed Timeline
High Level Timelines for Data cleansing planned during the PIS period are shown below.
These timelines will be finalised as part of Performance Test sign off from Technical Operations based on final volumes for cleansing, job run times and available time slot to cleanse the data in Production environment.
Any outbound files impacted by the below will follow the standard batch schedule

## Slide 29: UK Link November 21 – Deep Dive on 4780C Change Assurance Report & Return to Green Plan
September 2021

## Slide 30
Project | Date | Change Assurance Type | Overall RAYG
N21 | 10/09/2021 | Deep Dive – 4780C | 
CA1 |  |  | CA2 |  |  | CA3 |  |  | CA4 |  | 
Total 0 | Closed 0 | Open 0 | Total 4 | Closed 2 | Open 2 | Total 5 | Closed 3 | Open 2 | Total 3 | Closed 3 | Open 0
Topic | RAYG | Summary
Business Case |  | This slide calls out key findings from the independent Change Assurance deep dive on XRN4870C. The activity already underway to return this change to a Green RAG status is captured on subsequent slides. At time of slide submission, 8 from the total 12 findings have been closed, with the remaining 4 findings expected to be closed by 15th October This change 4780C is a CSSC change that is being delivered in November 21 release as this needs to be live before CSSC goes live and that there is an obligation on MAMs and CDSP to adhere to in the REC code from 7th November. There are various risks highlighted in this report due to the short timelines and complexity of bringing in this new service by 5th November.. Key Findings After being approved into scope at a relatively late point in the project lifecycle, the project needed to complete several activities in preparation for this change, such as: Scope and solution - Aligning the requirements to the agreed solution, configuration of the new service, completion of elements of design Planning and Customer - testing of the configuration with MAM/MAPs, performing the end to end testing, defining the support model and Customer training activities, Governance - risks/issues could have been highlighted earlier to the governance group to manage the direction of this delivery
Sponsorship |  | 
Governance |  | 
Scope & Solution |  | 
Team & Skills |  | 
Planning |  | 
Customer |  | 
Other - Information Security |  | 
Other – Suppliers |  | 
Other - Testing |  | 
Other – Environments |  | 
Other – People Change & Service Transition |  | 

## Slide 31
4780c Deep Dive - Return to Green Plan
Deep dive requested when 4780c was included in scope of Nov 21 release
12 findings reported as a result of the deep dive produced 10th Sept; with an overall status of Amber
Target resolution dates are to be agreed between project and Change Assurance (CA) team
Progress being monitored by the CA team
All findings are on track to be resolved by the project by 1st October; with the exception of 1 CA3 finding by 15th October
Next steps: A Stage Gate check is planned against Nov-21 at pre implementation w/c 25th October
CA Category | # Reported | Closed by 27th Sept | Remaining | Pending CA Assurance | Latest Closure Date
CA1 | 0 | - | - | - | -
CA2 | 4 | 2 | 2 | - | 1st Oct 21
CA3 | 5 | 3 | 2 | - | 15th Oct 21
CA4 | 3 | 3 | - | - | 1st Oct 21

## Slide 32
Lessons Learned from Key Themes from Deep Dive
Key Theme | Action | Measure | Date
Planning / RAID Management | Greater focus on planning and associated RAID management | Further coaching to be made available to portfolio resources to ensure understanding of critical dependencies and impact to plan | 30th Oct 2021
Scope / Governance | Ensure all changes go through Capture and adhere to governance process | Understanding and articulating risk associated to late inclusion in a release | 30th Oct 2021
Customer Engagement | Customer engagement is appropriately planned | Early engagement with Customers to ensure they can meet their obligations | 30th Oct 2021
3rd Party Engagement | 3rd party supplier engagement is appropriately planned and follows internal procurement process | Early engagement with 3rd parties; to ensure project deliverables are achieved in line with plan | 30th Oct 2021
Dependencies / Solution | Ensure approval of functional / non functional requirements prior to commencing detailed design | Ensuring project plan is in place and dependencies are adhered to | 30th Oct 2021

## Slide 33
Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme
Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects

## Slide 34: XRN5253 June 21 Major Release - Status Update
 | Overall Project RAG Status |  | 
 | Schedule | Risks and Issues | Cost
RAG Status |  |  | 
Status Justification |  |  | 
Schedule | Project on track Post Implementation Support (PIS) period 2 to commenced on 27/09/21 1st usage being tracked PIS due to complete on 28th Oct Decision In October ChMC None |  | 
Risks and Issues | None applicable |  | 
Cost | Forecast costs on track to complete within approved BER |  | 
Scope | In Scope: XRN5093 - MOD0711 – Update of AUG Table to reflect new EUC bands Descoped: XRN4992 - MOD0687 – Creation of new charge to recover last resort supply payments (Descoped at extraordinary ChMC on 26th October 2020) XRN4941 - MOD0692 - Auto updates to meter read frequency (Descoped at ChMC on 11th November 2020) |  | 
Slide updated on 24th September 2021
Complete
On Track
At Risk
Overdue
Not Baselined

## Slide 35: XRN5371 - Minor Release Drop 10 - Status Update
 | Overall Project RAG Status |  |  | 
 | Schedule |  | Risks and Issues | Cost
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Implementation successfully completed on 04/09/21 Post Implementation Support successfully completed 24/09/21, no defects raised Production of Change Completion Report in progress – to be submitted to November ChMC Decision in October ChMC: None |  |  | 
Risks and Issues | None applicable |  |  | 
Cost | On track to complete within approved spend |  |  | 
Scope | XRN5309 - FSG Automation of FSR Process XRN5188 - MAP ID Data Upload to UK Link XRN5246 - Confirmation File Performance improvements |  |  | 
Complete
On Track
At Risk
Overdue
Not Baselined
Updated: 24th Sept 21

## Slide 36: Post CSS Major Releases – For Information
In November Change Management Committee we will be asking for your approval of an EQR to take all the changes currently “ready” through to the end of the Detailed Design Phase
The conclusion of this activity will provide the right level of information (Detailed Design Change Packs, Detailed Impact Assessment and costs) for Xoserve and Customers to recommend / decide which industry implementation date is appropriate for each Change Proposal.
Xoserve will then conduct Build, Test and Implementation according to the implementation date(s) funded by approved BERs
This approach allows for work on these Change Proposals to be progressed during CSS related change freeze.

## Slide 37: Candidate Changes
XRN | Title | Funding
4900 | Biomethane/Propane Reduction | Decarbonisation
4978 | Notification of Rolling AQ value (following transfer of ownership between M-5 and M) | Shippers
4990 | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | Shippers
5091 | Deferral of creation of Class Change reads at transfer of ownership | Shippers
5186 | MOD0701 – Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | DNs / Shippers
5298 | H100 Fife Project – Hydrogen Network Trial | Decarbonisation

## Slide 38: NG TRANSMISSION CHANGE HORIZON PLAN 0 - 2 YEARS AUG 2021 - JULY 2023
August 2021

## Slide 39
Programmes & Projects 2021-2023 |  |  |  |  |  |  |  | 2022 |  |  |  |  |  |  |  |  |  |  |  | 2023
 |  |  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | 
MAJOR RELEASES | Regulatory / Customer Requested Change | PM Matthew Rider | MOD0745 - Setting of Auction Bid Parameter |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | MOD0728B – UK Link & Gemini Delivered as part of CP5341 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Sustain | PM Nicky Patmore | Gemini Customer Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | UK Link Consequential Changes |  | CSS Cons Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | CSS Cons Change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Gemini Change Programme Sustain | PM Manisha Bhardwaj | Single Sign on Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | PM Matthew Stephens | API Enhancements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | Site Minder Upgrade |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NG TRANSMISSION CHANGE HORIZON PLAN 0-2 YEARS SEP 2021 – AUG 2023
Implementation
19th Sept 21
Implementation
26th Sept 21 (C)
Build/Test – Aug to Sept 21
Design to PIS – Oct 21 to Jan 22 – Indicative timeline
Design to PIS – Sept 21 to Apr 22 – Indicative timeline
PIS July - Sept 21
Gemini Implementation
19th Sept 21
Pre-Implementation - Sept to Oct 21
Content: External Test Phase Jul - Dec 21
Build/Test – Aug to Sept 21
PIS Gemini - Sept to Dec 21
PIS UKL - Sept to Nov 21
Design to PIS – Sept 21 to Dec 21– Indicative timeline
KEY RISK & % = Certainty of Scope | 
 | Approved on Track
 | Approved
 | Approval at Risk
 | Change Completion Report
 | External User Activity
KEY – Project Status
On Track
Complete
Potential Risk to Plan
Plan at Risk

## Slide 40: CSSC Programme Dashboard
October 2021

## Slide 41
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates Transition: A revised transition test schedule released by the Programme has been reviewed and we have feedback our comments. We continue to contingency plan the impacts of a non Monday Go Live. This activity includes scenario planning that will be incorporated into the transition test plan. The Programme is currently consulting with the Industry on the planned Transition and Go Live. We will be submitted our view and preferred range of dates that minimises impacts to our customers. CSS Go Live will not be announced until January 2022. Internal & External Testing: All testing activities are on track. UEPT and E2E continues. There are no open defects against the CSSC programme, at the point of creation of this pack. Non-critical defects that have been identified have been fixed Business Change: Internal activities continue to plan including Target Operating Model set up. Detailed analysis workshops with business SME’s have concluded to review business exceptions. Workshops continue with Customer training team to support business readiness and communication activities. Data Migration: REL Cycle 4b completed and submitted to Landmark for their processing 1 week early. An interim MDD process proposal has been walked through by DCC and the SI. This process will replace the provision of MDD data during transition via API’s. The enduring process of providing the MDD data to REC is being discussed and will be in place post Programme Go Live |  |  |  | Environments: Continue to support and review environment requirements across Programme landscape. Review environment usage and requirements in conjunction with Cloud Programme DES: Complete outstanding test scrips UK Link APIs: Complete outstanding testing Transition: Internal planning activities and rehearsal planning continues in conjunction with Cloud Programme Testing: Continue UEPT & E2E testing. Review programme CR’s and continue defect fixes to Programme release plan
Programme Update

## Slide 42: UK Link Cloud Programme
October 2021

## Slide 43: UK Link Cloud Programme Update
The programme of work to migrate the UK Link platform to the cloud is progressing well with build and test activities continuing to plan
Our initial rounds of functional, performance and penetration testing have been completed
The build of the target production environment is underway which will be followed by further testing phases and dress rehearsals to commence in November
UK Link portal development and testing also progressing to plan. In addition business change activities such as the cloud operating model and associated cutover activities are in progress
The one area that has been a challenge has been in the migration of the data in an appropriate time frame, to limit customer impact

## Slide 44: Data Migration
As part of the transition process we need to migrate approximately 26TB of ISU data during our outage window using an SAP approved migration process
Initial tests took over 120 hours to successfully complete the migration, we did not anticipate the activity to take this period of time
Substantial refining and re-testing of the process has been carried out and this time has reduced to 62 hours
In order to provide sufficient time during the transition window to complete all activities and ensure a successful transition we are working to understand what this means on a process by process basis. Planning indicates that this could take place on the UK Link system over a four day period (Fri-Mon) during mid February 2022. We are still fully assessing to minimise impacts
Whilst this option is viable, we have also sought to identify a range of alternate migration approaches in order to provide a range of options
Only one viable alternate approach has been identified – a proprietary migration approach that would be conducted by SAP and is described on the following slide

## Slide 45: Data Migration
SAP have offered a solution which will allow us to carry out the needed data migration and associated activities over a single weekend therefore reducing the impact to customers
This approach has been utilised successfully for many large scale SAP migrations and has required Xoserve to engage SAP directly to work with us to execute.
The approach involves a number of test cycles and dress rehearsals to provide confidence in the process & technology the first of which is due to complete at the end of October. In order to build, test and assure this process we would need to target a go live cutover date of 12/13th March 2022
This timeline brings MTC project very close to the currently proposed start of CSS transition activities which with current timelines are due to commence on 26th March
On that date Xoserve and other Parties Under Integration (PUIs) will need commence a number of key activities in support of the central programme including the provision of a Data Extract from UK Link and bringing an outbound API live
Testing, dress rehearsals and transition will therefore be done in alignment with the Xoserve CSSC programme to ensure any risk to their transition activities is understood and mitigations are in place

## Slide 46: Data Migration - Summary
The reason for presenting this information is to talk you through the two migration options open to us and to keep you informed as we progress with our analysis
We are doing our utmost to find the best window to implement prior to CSS Go Live. It will be much harder to implement post CSS
We are supporting CSS performance and migration testing activities and these require ISU to be in the cloud to adhere to the Programme performance and non-functional requirements
To not implement would increase costs for both Programmes as we would incur further licencing costs as well as the continuation of Programme teams
It would also be much harder to secure an implementation window within an Industry release cycle as it would have to be approved via both REC and DSC
We are continuing conversations with Ofgem and DCC in relation to the Switching Programme Go Live date. It should be noted the Central Programme is currently consulting with industry (from October 1 - 22) on the planned Transition and Go-Live. Xoserve will be submitting it’s views and preferred range of dates that minimise impact to its customers. The final date for CSS Go Live will not be announced until January 2022

## Slide 47: Data Migration - Summary
We will continue to analyse both options throughout October to understand the best migration solution. We will provide checkpoint updates to confirm the following:
  Confirmation of successful test cycle for the SAP solution
  Mitigation options to support CSSC data export transition activities at the end of March should there be any issues with the move to cloud
  Combined dress rehearsal and transition plan for move to cloud and CSSC cutover
We would therefore be in a position to share a proposed go live date and solution by w/c 1st November

## Slide 48: CMS Rebuild Update
Verbal update presented by Emma Lyndon

## Slide 49: Section 6: Any Other Business

## Slide 50: REC Change Proposals

## Slide 51: REC Change Proposal
Ref | Title | Change Summary | Stage | Position | Additional Comments
R0001 | Amendment to DCC Service Flag (DI51130) Data Item | SEC Modification Proposal 077 proposes to update the values, and business rules, of the DCC Service Flag Data Item. This modification has been approved for implementation on 4th November 2021 by the SEC, and a consequential change is required to the Data Specification to reflect this. | Initial Review | The CDSP would like to express it’s support for R0001. This change has been on our radar for a number of months, as communicated under SEC MP077 and we have been working with DSC customers in delivering the changes required to UKL Systems to facilitate the proposal (under XRN5142) and is in scope of our UK Link November-21 Major Release delivery. | None
R0002 | Review of Data Specification Category in REC Baseline Statement | The Data Specification was not included in the Switching Programme Change Requests that gave effect to REC V2.0. Therefore, the Data Specification was not formally designated as part of REC V2.0 and has temporarily been added to the REC Baseline Statement as a Category 3 product. The Category 3 change process is not appropriate for these, as changes to Category 3 products should not cause a material impact to parties and stakeholders. Proposal: Standards Definition, Market Message Catalogue, Data Item Catalogue and Data Access Matrix should be designated as part of the REC itself, as Category 2 products. | Initial Review | The CDSP agree with the proposal of amending the categories of change under the Change Management Schedule. We expect that this proposal will have limited impacts to the CDSP as the majority of interfaces that the CDSP contribute towards the EMAR are controlled under the existing DSC and UNC. | None

## Slide 52: Project 1Stop – October Update
Megan Troth

## Slide 53: Background
The new iteration of the Xoserve website was developed in November 2018.
Since this implementation, based on customer feedback, we have been looking to identify various ways in which we can improve the change pages and the overall customer journey, particularly in relation to change (both DSC and Investment).
Project 1Stop has been created in order to completely understand of our customer’s needs, alleviate their pain points, and to create an overall more positive experience when navigating through Xoserve change information.

## Slide 54: October Update
Now the top three User Stories have been prioritised, we are beginning to get to work on improving the customer experience on our website.
We have previously received feedback from customers that the way to Change Proposals are displayed on our website can sometimes be quite unclear and therefore difficult to find exactly what they are looking for.
With that in mind, we are now focusing on giving our CPs an overhaul on the website. This includes updating the following on our website CP pages…

## Slide 55: Change Proposal Pages – Website Updates
  Split out CP (and keep original) into specific sections of a Change proposal separated out as documents of their own, e.g. different Change Packs & DSG Discussions. We will also keep the original CP as an option with all sections included as some customers may wish to have everything all in one place.
  Include Finance documents on parent CP page for parent release CPs (and link to these from the individual CPs), and include financial documents directly on the CP pages for standalone releases
  Include link to parent CP and/or release page on individual CP pages
We are focusing our attention on any CP that is currently live (this includes CPs in Initial Review, Capture, Solution Consultation and In delivery).

## Slide 56: Next Steps
We will move our focus onto ensuring that Release pages become clearer, more concise and easier to navigate
A further update on our progress of this will be given at the next ChMC meeting. A dedicated page for Project 1Stop has now been created where all the latest updates of progress can be found.

## Slide 57: APPENDIX

## Slide 58: Outages
Outages |  |  |  |  |  |  | 
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
 |  | Start Date | Start Time | End Date | End Time | Brief Description | 
XRN 5339 | EFT | 27/02/2022 | TBC | 27/02/2022 | TBC | This change will be to cutover from the existing EFT PROD to the newly built and upgraded EFT PROD, to keep the application in support. This extended outage will be on a Sunday and utilise the maintenance window for EFT to cause less impact to the industry. During the extended outage any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. Please be aware that the EFT cutover Contingency Dates will be carried out on the following weekend, 6th March. | 13/10/2021
XRN 5339 | EFT | 13/03/2022 | TBC | 13/032022 | TBC | As part the Enhanced File Transfer (EFT) project we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgrade EFT. As EFT is a multiple site application we will fail over to one site then failback to service normal and test the other site the following week. Please be aware that the EFT DR Contingency Dates will be carried out on the following weekend. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. | 13/10/2021
XRN 5339 | EFT | 20/03/2022 | TBC | 20/03/2022 | TBC | As part the Enhanced File Transfer (EFT) project we will conduct Disaster Recovery (DR) testing. The EFT DR test will prove and confirm the procedures, resilience and capability of the newly upgrade EFT. As EFT is a multiple site application we will have failed over, then failed back one site on the previous week, to complete the DR testing this weekend we will DR test the remaining site. Please be aware that the EFT DR Contingency Dates will be carried out on the following weekend. Any files that would be processed by EFT during this window will remain safely in their respective Folders, once EFT is back online, all file transfers will be synced and issued. | 13/10/2021

## Slide 59: Data Cleanse Approach/Plan

## Slide 60: November 21 Data Cleansing - Proposed Timeline
High Level Timelines for Data cleansing planned during the PIS period are shown below.
These timelines will be finalised as part of Performance Test sign off from Technical Operations based on final volumes for cleansing, job run times and available time slot to cleanse the data in Production environment.
Any outbound files impacted by the below will follow the standard batch schedule

## Slide 61: Data Cleansing Approach – XRN4941
This change will allow the CDSP to update the Meter Read Frequency (MRF) for Class 4 Supply Meter Point’s (SMP) under the following circumstances:
  Where a Supply Meter Point’s AQ value is amended to 293,000 kWh or above on the Supply Point Register and does not currently have a monthly Meter Read Frequency
  Where a Supply Meter Point has AMR Meter installed on the Supply Point Register and does not currently have a monthly Meter Read Frequency
  Where a Supply Meter Point is operational smart meter where a DCC Service Flag is ‘Active’ on the Supply Point Register and does not currently have a monthly Meter Read Frequency
In the above circumstances, the Meter Read frequency of the supply meter points with product class 4, will be amended to monthly by the CDSP.
We are expecting up to 4 million MRF’s this will be shared with the customer advocates who will share the information with all parties
# | List of Activities | Dependencies | Remarks
1 | Final Data profiling in Production before running the Historic cleansing for Class 4 non-monthly MRF sites for: 1. AQ >=293000, 2. DCC_STAT = A, 3. AMR device | SQL queries will be developed & run to identify the exact volumes (these will be first run as part of PT) | These will be run nearer to Go-Live Estimated Volumes for cleansing are up to 4M (AQ ~ 10K, DCC ~ 3M, AMR ~ 1M)
2 | Identify Inflight workflows where Auto MRF update should be taken care post old confirmation workflow is LIVE | SQL queries developed & run to identify the exact volumes (Run prior to historic job) | Confirmation in ‘CO’/ Contract change workflow at D-2.
3 | Unsolicited SCR in regular intervals for historic load |  | Adhoc SCR trigger for bulk load

## Slide 62: Data Cleansing Approach – XRN5007
The change is raised to address the issue being experienced currently where a period has been reconciled to a zero position and then a valid read related to that period is received and re-reconciliation takes place. At this point a divide by zero error is encountered as the prevailing metered volume is zero, and the MN09 exception is generated. The scenarios that have been identified as causing this are:
  Re-reconciliation of a zero reconciled period triggered by a site visit or replacement reading
  A Breaking Rec (where a previously reconciled period is split as a result of an inserted read) on a non-consuming period.
# | List of Activities | Dependencies | Remarks
1 | Any MN09 sites with existing data issues or new exception will be shared with Tech Ops / Bus Ops for standard resolution steps. |  | To be determined as result of PT
2 | In case of high MN09 volumes, invoicing volumes to be generated for that billing month will be agreed with Business Ops which can be accommodated for MN09 closure for a particular month | Business Operations to determine the split based on Pre-prod statistics | 

## Slide 63: Data Cleansing Approach – XRN5072
Since Nexus implementation, there have been a number of scenario specific defects raised concerning the use of the TTZ indicator provided in the Meter Reading files and how the subsequent volume and energy is then being calculated. The TTZ indicator confirms whether the meter readings provided have clocked (gone through the zeros) since the last actual read and the means to derive consumption. However, through the defects raised and analysis of these issues, inconsistencies and errors in the use of TTZ and derivation of consumption have been seen.
In the instances where the application of TTZ is incorrect, system then creates a reduced/increased volume and energy, it has knock on effects to the AQ and downstream processes such as EUC (End user category) assignment, daily allocation and calculation of unidentified gas.
This change will need to ensure that the TTZ indicator received in meter reading files is correctly applied in the calculation of volume and energy. This change does not impact the TTZ derivation logic for RGMA flows.
In addition to the enduring solution, this change will also cleanse the existing data where volume calculated incorrectly due to incorrect application of TTZ indicator for identified scenarios. This covers below:
  Option to pause and resume in case of any critical BAU activity in priority
  Identify initial and final volumes for volume correction/Consumption Adjustment (CA)

## Slide 64: XRN5072 – List of Data Cleansing Activities Production
# | List of Activities | Dependencies | Remarks
1 | Run Data profiling program in Production based on agreed run time and Volumes for each of the trigger type in PIS period | Indicative volumes will be available in PT | Batch run time, no. of parallel work processes & schedule be determined in PT
2 | Feed the identified Data cleansing sites to internal Consumption Adjustment tool for volume correction |  | To be determined as result of PT
3 | Next steps to correct the data Bill doc reversals Consumption Adjustment with reason ‘Others’ (‘Remarks’ - N21 release – TTZ Vol correction) Rolling AQ correction Formula AQ correction Financial adjustment |  | Existing BAU tools to be used to correct the data

## Slide 65: Data Cleansing Approach – XRN5142
This change removes the allowable values of “S” - Suspended and “W” – Withdrawn and replace them with values of “N” – Non-Active and “I” – InstalledNotCommissioned.
In addition to the enduring solution, this change will also ensure that all data using the DCC service values is cleansed for the current data set in the system. This activity will be performed collaboratively with inputs from the DCC. This covers below:
  For data cleansing, DXI files to be received from DCC with new values ‘N’ & ‘I’ for identified sites
  UKLink existing BAU job to be utilised to process the data cleansing
  In case PT results shows that DXI volumes are to be processed over multiple intervals, then timings to run the job for each day will be agreed with Tech-Ops as part of PT result assurance.
  Option to pause and resume in case of any critical BAU activity in priority
  Dependency on DCC to send the data to UKLink via DXI file to initiate the data cleansing activity (Approx. volumes = 60K)
# | List of activities | Dependencies | Remarks
1 | DXI file will be processed for cleansing post go live | DCC issue updated DXI file | To be determined from PT results
2 | New values will be available to view in DES |  | 

## Slide 66
# | List of Activities | System | Dependencies | Start Time | End Time | Remarks
1 | Final Data profiling before running the Historic DCC cleansing for Sites with DCC_Flag = A, S or W in production | SAP ISU | DCC to provide the stats during PT. | TBD | TBD | Table statistics
2 | Utilise the existing BAU schedule for DXI file processing for data cleansing for new DCC_SERVICE_FLAG values | SAP ISU | Final Volumes will be determined nearer to Go-Live (Current estimate is 60K sites to be cleansed ) | TBD | TBD | Batch run time, no. of parallel work processes & schedule will be determined in PT
3 | Hold/Pause the job if required for any BAU critical activity | SAP ISU | Final counts for cleansing | TBD | TBD | To be determined as result of PT
4 | New values to be extracted to BW as part of daily BW jobs | SAP BW | DCC data cleansing completion | TBD | TBD | 
5 | Report the successful, unsuccessful, next steps for historic cleansing statistics for each of the DCC_STAT status | SAP ISU | Completion of data cleansing run | TBD | TBD | Daily and Final counts
XRN5142 – List of Data Cleansing Activities Production

## Slide 67: Portfolio POAP

## Slide 68: CSSC Programme Dashboard
October 2021

## Slide 69
Programme Health – RAG |  |  | Return to Green Plan | 
Overall Programme Status | Previous | Current | The programme remains at a Green status and all Programme activities remain on track with all key internal and eternal milestones being met | 
Programme Plan | Previous | Current |  | 
Risk Profile | Previous | Current |  | 
Resources | Previous | Current |  | 
Executive Summary |  |  |  | Upcoming Activities & Milestones (Next Month)
Key Programme Updates Transition: A revised transition test schedule released by the Programme has been reviewed and we have feedback our comments. We continue to contingency plan the impacts of a non Monday Go Live. This activity includes scenario planning that will be incorporated into the transition test plan. The Programme is currently consulting with the Industry on the planned Transition and Go Live. We will be submitted our view and preferred range of dates that minimises impacts to our customers. CSS Go Live will not be announced until January 2022. Internal & External Testing: All testing activities are on track. UEPT and E2E continues. There are no open defects against the CSSC programme, at the point of creation of this pack. Non-critical defects that have been identified have been fixed Business Change: Internal activities continue to plan including Target Operating Model set up. Detailed analysis workshops with business SME’s have concluded to review business exceptions. Workshops continue with Customer training team to support business readiness and communication activities. Data Migration: REL Cycle 4b completed and submitted to Landmark for their processing 1 week early. An interim MDD process proposal has been walked through by DCC and the SI. This process will replace the provision of MDD data during transition via API’s. The enduring process of providing the MDD data to REC is being discussed and will be in place post Programme Go Live |  |  |  | Environments: Continue to support and review environment requirements across Programme landscape. Review environment usage and requirements in conjunction with Cloud Programme DES: Complete outstanding test scrips UK Link APIs: Complete outstanding testing Transition: Internal planning activities and rehearsal planning continues in conjunction with Cloud Programme Testing: Continue UEPT & E2E testing. Review programme CR’s and continue defect fixes to Programme release plan
Programme Update

## Slide 70: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | DES & Secondary API | UEPT/E2E support continues. Defects raised via external testing phases have been fixed and release within the Programme releases.
 |  | Testing | UEPT and E2E continues well. At the point of writing this, no significant defects have been seen. Programme CR’s continue to be assessed
 |  | Service Management | CR-D072 has now been approved. Operational readiness activities are ongoing
 |  | Batch | Testing support underway for UEPT/E2E activities. A Change Pack has been shared with the Industry and will be presented at Change Management Committee meeting for approval ahead of updating the Gemini Business Requirements Document.
 |  | Gemini | Conversations are ongoing with customers in relation to concerns for Gemini timings as a result of Switching Programme requirements as defined in DB4. Gemini team have raised concerns as to date the Gemini ACT file has not been testing in the Programme E2E phase. We will be reaching out to the SI to encourage this process to be tested
 |  | Reporting | An internal CR has been raised and being progressed to incorporate the impact of one newly identified report that will need changes. Any new reporting requirements are assessed by the consequential reporting team
 |  | UK Link | There are a number of change requests that have been approved by the Control Board and are now in the Build phase. Technical Exception workshops have started with business SMEs following the completion of the business exceptions review

## Slide 71: Green Workstream Updates
RAG Previous MONTH | RAG Current MONTH | WORK STREAM | SUMMARY
 |  | REC | REC version 3 consultation is complete.
 |  | Data | Following a MDD data cleansing cycle we are working closely with customers. Preparation are underway for REL cycle 4b data to be extracted from UK Link. Planning for Analysis reports cycle 6 and REL Cycle 5 has commenced
 |  | Environments | All activities continuing to track to plan for all upcoming activities. Environment readiness for Transition is in progress. Environment requirements will continue to be assessed in line with the Cloud Programme for combined activities.
 |  | MAP C (XRN-4780C) | Detailed delivery updates are being provided as part of November 21
 |  | SoLR (XRN-5144) | Engagement continues with Ofgem. SoLR representation has been provided by the Industry following consultation requests via the Ofgem design forum and ChMC. All feedback is being reviewed with feedback being provided to both forums.

## Slide 72: Key Programme Risks (1/2)
RTC | RAG | Workstream | Description | Mitigation Strategy | Latest Update | Resolution Date
65426 |  | Transition & Cutover | There is a risk that the Go Live assumption day of Monday may get changed because various variables (factors) are being looked at by OFGEM leading to rework on Transition plan and related activities. | The Go-live principles have been approved at Delivery Group. Xoserve's concerns have been logged with Ofgem | Impact of non-Monday Go-live on Xoserve's Transition testing has been fed back to Ofgem. Internal contingency planning is underway | 30/09//21
65156 |  | Transition & Cutover | There is risk that the change freeze scope could impact Transition because the scope of Programme Change Freeze from 03/01/22 is not clearly defined leading to impacts during actual Transition | Work with the SI to collectively define the scope of Change Freeze | Internal discussions are ongoing within Ofgem to define the scope of this Change Freeze | 30/09/21
64171 |  | Transition and Cutover | There is a risk that the SoLR process might kick off during the transition period because of a supplier going out of business at that time leading to Landmark needing to cater to additional volumes and also the potential for additional requirements for PUIs to undertake to ensure Transition timelines are maintained | Raise the risk with Ofgem and SI to understand what non-functional considerations have been applied to enable Landmark to manage the increased volumes Raise with the SI to include a transition test scenario if relevant to mitigate this possibility | There is a potential that SoLR related implications during Transition may be considered for Transition Testing. Currently expected to be discussed in September. Dates have been aligned accordingly | 30/09/21
65122 |  | Transition and Cutover | There is risk that additional Transitional changes could change scope of Transition because more changes are identified as Transition planning continues at the Central Programme level leading to changes to the Transition plan and Xoserve planned activities. | Xoserve are actively involved in all Programme work groups to monitor and mitigate this risk. | The impact of CR-D059 on Transition is being assessed | 30/09/21
64513 |  | Data | There is a risk that data cleansing requirements may not be met because Xoserve are not responsible for the data in UK Link, and can't compel shippers / GTs / iGTs to correct their data leading to incorrect data at the point of go live. | Communicate requirements through DSG and track progress | MDD data cleansing is with Customer Advocates to process. Additionally, further work is ongoing on REL reports | 30/12/22

## Slide 73
High Level Plan

## Slide 74: Switching Programme CR Position – CRs impacting Xoserve
CR Name | CR Ref | High Level Cost IA Cost | Date Raised | Status
Programme Plan Re-Baseline | CR-D002 | £0.00 | 07/11/2019 | Approved - Complete
Updates to the CSS Physical Interface Design (PhID). | CR-D008 | £17,250.00 | 22/01/2020 | Approved - Internal CR Created
CSS_Exception_Handling_Strategy_v0.2 | CR-D014 | £0.00 | 26/02/2020 | Approved - Internal CR Created
Provide_CSS_RegistrationID_to_PUI_and_LPs | CR-D016 | £12,643.00 | 07/08/2020 | Approved - Internal CR Created
Licence Exempt Network Customer Identifier – ABACUS Data Model update | CR-E51 | £0.00 | 29/10/2019 | Approved - Complete
Amendments to the DMS artefact suite | CR-D019 | £6,500.00 | 16/03/2020 | Approved - Internal CR Created
Migration of Terminated Gas RMPS | CR-D022 | £0.00 | 10/06/2020 | Approved - Internal CR Created
Amendments to the NC-0079 for REL (Retail Energy Location) Data Migration and Reconciliation | CR-D024 | £20,000.00 | 06/07/2020 | Approved - Internal CR Created
DMS - PHID Alignment Parties | CR-D026 | £0.00 | 06/07/2020 | Approved - Internal CR Created
Request For a New or Upgraded DMT Environment | CR-D027 | £256,009.00 | 07/08/2020 | Approved - Internal CR Created
Enable TLS connection pooling for all directly connected parties to CSS] | CR-D028 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
Message Header Format for PKI Certificate Identification] | CR-D029 | £2,500.00 | 13/07/2020 | Approved - Internal CR Created
SIT Functional Test Re Plan Enabling Parallel Testing | CR-D030 | £56,000.00 | 20/07/2020 | Approved - Internal CR Created
DM_Validation Catalogue_Shipper_Effective_Date_Change_ | CR-D032 | £0.00 | 03/08/2020 | Approved - Internal CR Created
Compression During Data Migration | CR-D034 | £500.00 | 09/09/2020 | Approved - Internal CR Created
Uplift to the CSS Interface Specifications | CR-D038 | £70,000.00 | 07/10/2020 | Approved - Internal CR Created
Uplift to Business Data Validation Rules | CR-D039 | £20,000.00 | 25/09/2020 | Approved - Internal CR Created
Programme Plan Re-Baseline | CR-D042 | £14,913,000.00 | 28/09/2020 | Approved - Internal CR Created
Changes to Support Energy Company Data | CR-D059 | £37,500.00 | 03/08/2021 | Awaiting Decision
Operational Choreography Detection 0.5 | CR-D060 | £308,205.00 | 25/01/2021 | Awaiting Decision
Operational Choreography Rectification 0.3 | CR-D061 | £0.00 | 25/01/2021 | Awaiting Decision
Amendment of Data Migration Solution to Protect Programme Timescales - Removal of Transition Stage 1 Delta files | CR-D062 | £83,490.00 | 25/02/2021 | Approved - Internal CR Created
Change to Management of In-Flight Switches Approach | CR-D071 | £0.00 | 15/03/2021 | Approved - Internal CR Created
Increase Cadence of Data cuts | CR-D080 | £24,600.00 | 10/05/2021 | Approved - Internal CR Created
Amendment to Assumptions as a result of analysis undertaken during CP1 v0.4] | CR-D083 | £0.00 | 24/05/2021 | Approved - Complete
TT Remediation & Paper-Based Testing Workshop | CR-D095 | £34,000.00 | 23/08/2021 | Pending PIA
Continuation of support for UEPT | CR-D098 | £308,000.00 | 03/08/2021 | Awaiting Decision
Documentation only updates to NCT-0134 DMT Live Rehearsal Test Plan and NCD-0012 Data Migration Solution Design Catalogue | CR-D103 | £0.00 | 17/08/2021 | Pending PIA
Elaborations for Service Management Requirements DB4 | CR-D104 | £0.00 | 17/08/2021 | Pending SI Response

## Slide 75: Switching Programme CR Position – CRs not impacting Xoserve ((Cost Implication)
CR Name | CR Ref | Date Raised | Status
Non_Mandatory_MPAS_Metered_Indicator_v0.4 | CR-D001 | 27/01/2020 | Complete - No Xoserve Impact
REC Manager Procurement Timelines | CR-D003 | 02/12/2019 | Complete - No Xoserve Impact
MPAS Related MPAN Disconnection | CR-D004 |  | Withdrawn
Introduction of Validation Message to Logical Mode | CR-D005 | 25/11/2019 | Withdrawn
Modification of Related MPAN Cleanse Checkpoint Milestones | CR-D006 | 27/11/2019 | Complete - No Xoserve Impact
ABACUS Corrections and Re-alignments | CR-D007 | 04/12/2019 | Complete - No Xoserve Impact
ECOES REL API Webmethod | CR-D009 | 17/12/2019 | Complete - No Xoserve Impact
CSSIA Uplift to Implement IG Recommendations | CR-D010 | 17/12/2019 | Complete - No Xoserve Impact
Update 3 E2Es to align to CSSIA | CR-D011 | 10/06/2020 | Complete - No Xoserve Impact
CSS_Physical_Interface_Design_Updates_mpxn_v0.2 | CR-D012 | 30/01/2020 | Complete - No Xoserve Impact
Messaging_Requirements_Revisions_REC_Code_Manager_and_CSS_v0.1 Clean | CR-D013 | 28/01/2020 | Complete - No Xoserve Impact
Amendment_of_Xoserve_Consequential_Change_Milestone_Delivery_Dates_v0.2[DRAFT] | CR-D015 | 26/02/2020 | Withdrawn
CSS_Handling_of_MPAS_Business_Dates_v0.2[DRAFT] | CR-D017 | 20/07/2020 | Complete - No Xoserve Impact
Confirmation_Responses_to_Outbound_Synchronisations_v0.2[DRAFT] | CR-D018 | 02/03/2020 | Withdrawn
Regulatory Workstream – Programme Milestones Refresh | CR-D020 | 16/03/2020 | Withdrawn
Remove MPAS Interface | CR-D021 | 29/04/2020 | Withdrawn
DSP_Specific_ SIT_ Functional_Exit_Criteria | CR-D023 | 29/05/2020 | Complete - No Xoserve Impact
Changes to support enhanced Solar arrangements | CR-D025 |  | Withdrawn
CSS Role-based access control (RBAC) | CR-D031 | 24/07/2020 | Withdrawn
A Quality Analysis Activity of the Data being used for the DMT Non-Functional Test Phase​​ | CR-D033 |  | Withdrawn
CSS Change from UTC to Local Time | CR-D035 | 22/09/2020 | Complete - No Xoserve Impact
Xoserve CR for DES AI Removal | CR-D036 | 24/09/2020 | Complete - No Xoserve Impact
Provide_CSS_RegistrationID_to_LPs | CR-D037 | 06/10/2020 | Complete - No Xoserve Impact
UEPT Tranche Regulatory Change | CR-D040 | N/A | Complete - No Xoserve Impact
NCT-0073 Functional Script Master Changes | CR-D041 | 25/09/2020 | Complete - No Xoserve Impact
Update to the End to End Testing Plan | CR-D043 | 05/10/2020 | Complete - No Xoserve Impact
Request For a New DMT Environment for DMT Live Rehearsal | CR-D044 | 23/10/2020 | Complete - No Xoserve Impact
NC-0079 Adding Post Load Integrity Check Document | CR-D045 | 09/11/2020 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-0046 | 09/11/2020 | Complete - No Xoserve Impact
Correctional Changes to MAD Log v2.0 & POAP v2.0 | CR-D047 | 13/11/2020 | Complete - No Xoserve Impact
Changes to Data Milestones in MAD Log v2.0 & POAP v2.0 | CR-D048 | 09/11/2020 | Complete - No Xoserve Impact
Consequential Changes to Testing Milestones in MAD Log | CR-D049 | 13/11/2020 | Withdrawn
CSS Environments for Faster Switching Enduring Service | CR-D050 |  | Withdrawn
Changes to Data Validation Rules | CR-D051 | 30/11/2020 | Complete - No Xoserve Impact

## Slide 76: Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)
CR Name | CR Ref | Date Raised | Status
Additional and Further Correctional Changes to MAD Log v2.0 | CR-D052 | 05/12/2020 | Complete - No Xoserve Impact
Additional Onward Dependencies for MAD Log | CR-D053 | 18/12/2020 | Complete - No Xoserve Impact
Changing from GetOrganised to Landmark SFTP for SI receiving files | CR-D054 | 18/12/2020 | Complete - No Xoserve Impact
Amendments to the Data Cleansing Catalogue | CR-D055 | 18/12/2020 | Complete - No Xoserve Impact
MAD Log Changes for UIT Environment Verification | CR-D057 | 25/01/2021 | Complete - No Xoserve Impact
Discontinuance of Xoserve Consequential Change Market Trials | CR-D058 | 25/01/2021 | Complete - No Xoserve Impact
Uplift to SMS CoCo | CR-D063 | 29/01/2021 | Complete - No Xoserve Impact
Changes to SIT Functional Test Scenarios | CR-D064 | 29/01/2021 | Complete - No Xoserve Impact
Uplift to the Code of Connection | CR-D065 | 29/01/2021 | Complete - No Xoserve Impact
In-Flight Reg ID Dissemination | CR-D066 |  | Withdrawn
Uplift to the CSS Business Data Validation Rules Doc | CR-D067 | 19/03/2021 | Complete - No Xoserve Impact
Uplift to the CSS Interface Specification | CR-D068 | 15/03/2021 | Complete - No Xoserve Impact
REL Dissemination to iDNO and DNO | CR-D069 | 15/03/2021 | Complete - No Xoserve Impact
Removal of UEPT Stage 1 Data Allocation and Verification for Tranche 3 and 4 Participants and delivery acceleration of Stage 2 Data Allocation | CR-D070 | 05/03/2021 | Complete - No Xoserve Impact
Re-align Switching Programme Response SLAs with Xoserve response SLAs | CR-D072 | 07/05/2021 | Complete - No Xoserve Impact
Changes to MAD Log v2.2 to rectify incorrect milestone descriptions | CR-D074 | 29/03/2021 | Complete - No Xoserve Impact
Update Service Management Baseline Requirement | CR-D076 | 20/04/2021 | Complete - No Xoserve Impact
Amend the Transition Testing Milestones TR210 & TR220 for PUI Production Data Cuts v0.4 | CR-D078 | 14/05/2021 | Complete - No Xoserve Impact
Removal of SMS005 from UEPT Test Scenarios v0.2 | CR-D081 | 14/05/2021 | Complete - No Xoserve Impact
Engagement for Early E2E Testing v0.2 | CR-D082 | 14/05/2021 | Withdrawn
Change to Transition Stage 3 File-Based Migration Sequencing v0.2 | CR-D084 | 26/05/2021 | Complete - No Xoserve Impact
Request for an additional Data Reconciliation Activity at the end of DMT Live Rehearsal Cycle 2 v0.2 | CR-D086 | 01/06/2021 | Withdrawn
Update to UIT E2E Plan and Artefacts to incorporate the additional scope identified on the outcome of REL Gap Analysis v0.7 | CR-D087 | 17/06/2021 | Complete - No Xoserve Impact
Elevation of L2-TR070 (Transition Stage 1 Start) to a L1 milestone | CR-D088 | 04/06/2021 | Complete - No Xoserve Impact
NC-0107 Master Handover Pack Purpose Change | CR-D089 | 04/06/2021 | Complete - No Xoserve Impact
REC Code Manager Market Intelligence Reporting | CR-D090 | 11/06/2021 | Complete - No Xoserve Impact
Removal of Transition Test Artefacts | CR-D091 | 24/06/2021 | Complete - No Xoserve Impact

## Slide 77
CR Name | CR Ref | Date Raised | Status
Feasibility study on potential to update Domestic Premises Indicator (DPI) electricity flags to reflect license status during transtion stages, 1, 2 & 3 | CR-D093 | 28/06/2021 | Complete - No Xoserve Impact
Changes to Operational Testing | CR-D094 | 28/06/2021 | Complete - No Xoserve Impact
Changes to milestone date for L3-TE720 | CR-D096 | 29/07/2021 | Complete - No Xoserve Impact
Further consquential changes to DB4 and related artefacts following CR-D071 v0.2 | CR-D100 | 06/08/2021 | Complete - No Xoserve Impact
CSS Stage 1 ECOES Interface Specification Uplift to v2.0 | CR-D102 | 17/08/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D103 | 17/08/2021 | Complete - No Xoserve Impact
Addition of assumption on MAD Log in relation to earliest possible Go-Live date | CR-D107 | 15/09/2021 | Complete - No Xoserve Impact
Change to Data Migration and Transition artefacts following the completion of CR-D09 | CR-D108 | 15/09/2021 | Complete - No Xoserve Impact
Change to EES requirements to bring REL search and retrieval into closer alignment with GES and assessment of programme | CR-D109 | 15/09/2021 | Complete - No Xoserve Impact
Changes and additions to PIWG and CWG governed MAD Log v2.4 milestones to address timing and clarity issues | CR-D110 | 22/09/2021 | Complete - No Xoserve Impact
Switching Programme CR Position – CRs not impacting Xoserve (Cost Implication)